PROJECT PLAN

Rosedale Public Library Replacement · CP-2431 · Version 3.0

| Project | Rosedale Public Library Replacement | Project no. | CP-2431 |
| --- | --- | --- | --- |
| Client | City of Rosedale | Location | 412 Marchmont Avenue, Rosedale |
| Delivery method | Design-bid-build | Plan version | 3.0 · 31 Aug 2026 |
| Prepared by | D. Okonkwo, Client-Side Project Manager | Approved by | M. Halloran, Director of Community Services |

| 1. PROJECT SUMMARY |  |
| --- | --- |
| In one paragraph | The City of Rosedale will replace the Rosedale Public Library on its existing site, under a design-bid-build contract, for an approved $29.50M. The plan runs from 2 Jun 2025 to closeout in Apr 2030, with substantial completion certified 21 Feb 2029. Forecast cost on the works is $28.01M, which leaves $1.49M of the approved budget as contingency. The plan is 5% complete by value. Two things currently threaten it: construction documentation is behind, and the main works contract has passed the date it had to be awarded to hold the construction start. Both are in section 9. |

| Approved budget $29.50M | Forecast on the works $28.01M | Contingency left $1.49M | Drawn so far 5% of $1.56M |
| --- | --- | --- | --- |
| First activity 2 Jun 2025 | Substantial completion 21 Feb 2029 | Complete by value 5% | Phases 7 |

| 2. BACKGROUND AND JUSTIFICATION |  |
| --- | --- |
| The need | The Marchmont Avenue branch opened in 1961 and serves 214,000 visits a year against a design capacity of about 90,000. The roof, the HVAC system and the electrical service are all beyond their service life, and the building does not meet current accessibility requirements. Three of the eleven public spaces are closed. |
| The options considered | Four: refurbish in place; refurbish and extend; replace on the existing site; replace on the Council-owned site at Feldman Park. Refurbishment in either form was costed at 70 to 80 percent of replacement and would have delivered a building with the same floor plate and the same accessibility constraints. |
| The option chosen, and why | Replacement on the existing site. It keeps the branch in its catchment, avoids the land transaction and the rezoning that Feldman Park would need, and delivers the full program. It carries one significant disadvantage, which is that the existing building has to be kept open until a temporary branch is available - and that constraint drives the sequence in section 4. |

| 3. SCOPE |  |
| --- | --- |
| In scope | Not in scope |
| The right-hand column is the one that gets read in a dispute. |  |
| A new 36,600 sq ft single-story library on the Marchmont Avenue site | The temporary branch lease and its fit-out, funded and delivered separately |
| Demolition of the existing 1961 building and its 1978 annex | The Marchmont Avenue road and intersection works under the Streets program |
| Eleven public spaces, including two program rooms and a makerspace | Any acquisition or disposal of land |
| Fit-out, loose furniture, shelving and the public technology fleet | The library's operating budget, staffing and program design |
| Relocation of the collection to and from the temporary branch | Public art beyond the commissioned piece named in section 7 |
| External works, parking to the adopted ratio, and landscape | Digital collection licensing and the library management system |
| All statutory approvals, utility connections and commissioning |  |

| 4. WORK BREAKDOWN |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Phase | Description | Start | Finish | Budget | Done |
| Phases overlap, so their durations do not sum to the project duration. Percent done is weighted by budget. |  |  |  |  |  |
| Business case | Needs analysis, options study, Council approval and confirmation of the appropriation. Complete. | 2 Jun 2025 | 3 Sep 2025 | $85,000 | 100% |
| Design | Concept design, community consultation, design development and construction documentation. Documentation is the current critical activity and is behind - see section 9. | 4 Sep 2025 | 2 Sep 2026 | $1,895,000 | 70% |
| Approvals | Development application, development approval and the building permit. The permit is the gate on the main works contract award. | 18 May 2026 | 23 Nov 2026 | $67,000 | 67% |
| Procurement | An early works package advertised separately so site work can start under its own permit, then the main works bid package, evaluation and award. | 18 May 2026 | 14 Jan 2027 | $40,000 | 0% |
| Construction | Site establishment and demolition, substructure, superstructure and roof, envelope, services rough-in, fit-out and external works. Envelope and services run in parallel from the completion of the roof. | 15 Jan 2027 | 29 Dec 2028 | $24,700,000 | 0% |
| Commissioning | Systems commissioning, collection move-in and shelving install, and certification of substantial completion. | 3 Oct 2028 | 21 Feb 2029 | $1,020,000 | 0% |
| Handover | Certificate of occupancy, operations and maintenance handover, the warranty period and the closeout report. | 22 Feb 2029 | 11 Apr 2030 | $130,000 | 0% |

| 5. KEY DATES |  |  |  |  |
| --- | --- | --- | --- | --- |
| Milestone | Baseline | Current | Move | Status |
| Move is in working days. The building permit is the gate on everything after it, so one slip carries through. |  |  |  |  |
| Business case approved by council | 12 Aug 2025 | 12 Aug 2025 | - | On baseline |
| Capital funding confirmed | 3 Sep 2025 | 3 Sep 2025 | - | On baseline |
| Building permit issued | 30 Oct 2026 | 23 Nov 2026 | +15 days | Behind baseline |
| Construction contract awarded | 15 Dec 2026 | 14 Jan 2027 | +20 days | Behind baseline |
| Notice to proceed issued | 22 Dec 2026 | 22 Jan 2027 | +20 days | Behind baseline |
| Substantial completion certified | 23 Jan 2029 | 21 Feb 2029 | +20 days | Behind baseline |
| Certificate of occupancy issued | 13 Feb 2029 | 14 Mar 2029 | +20 days | Behind baseline |
| Project closeout report | 14 Mar 2030 | 11 Apr 2030 | +20 days | Behind baseline |

| 6. BUDGET |  |  |  |
| --- | --- | --- | --- |
|  | Budget | Forecast | Variance |
| Contingency sits INSIDE the approved $29.50M, not on top of it. 5% is drawn against a 50% re-plan trigger; what is left is 6% of the $26.50M of work still to come, which is the number to watch. |  |  |  |
| Business case | $85,000 | $85,000 | on budget |
| Design | $1,895,000 | $1,941,500 | +$46,500 |
| Approvals | $67,000 | $92,000 | +$25,000 |
| Procurement | $40,000 | $40,000 | on budget |
| Construction | $24,700,000 | $24,700,000 | on budget |
| Commissioning | $1,020,000 | $1,020,000 | on budget |
| Handover | $130,000 | $130,000 | on budget |
| Contingency | $1,563,000 | $1,491,500 | -$71,500 |
| TOTAL | $29,500,000 | $29,500,000 | on budget |

| 7. PROCUREMENT AND LONG-LEAD ITEMS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Package | Type | Needed for | Weeks | Award by | Status |
| Award by is worked backwards from the activity the package feeds, less the lead time in calendar weeks. A passed award date moves every date after it. |  |  |  |  |  |
| Design team | Consultant | Concept design | 8 | 5 Sep 2025 | Awarded |
| Planning consultant | Consultant | Development application lodged | 4 | 20 Apr 2026 | Awarded |
| Early works contractor | Contract | Site establishment and demolition | 10 | 16 Nov 2026 | In market |
| Main works contractor | Contract | Site establishment and demolition | 30 | 29 Jun 2026 | In market - DATE PASSED |
| Structural steel | Long lead item | Superstructure and roof | 26 | 24 Dec 2026 | Scope being written |
| Air handling units | Long lead item | Services rough-in | 34 | 22 Apr 2027 | Not started |
| Medium voltage switchgear | Long lead item | Services rough-in | 40 | 11 Mar 2027 | Not started |
| Commissioning agent | Consultant | Systems commissioning | 12 | 11 Jul 2028 | Not started |
| Library shelving and furniture | Supply and install | Collection move-in and shelving install | 16 | 18 Aug 2028 | Not started |
| Public art commission | Supply and install | External works and landscape | 30 | 7 Mar 2028 | On hold |

| 8. ROLES AND RESPONSIBILITIES |  |  |
| --- | --- | --- |
| Role | Who | Decision authority |
| Decisions, not activities. The full responsibility matrix, and the meeting and reporting structure that sits behind these decisions, belong in the Project Execution Plan. |  |  |
| Council | The governing body | Approves the budget and any increase to it. Approves a change to the approved floor area or the number of public spaces. |
| Project Sponsor | M. Halloran, Director of Community Services | Owns the business case. Approves drawdown from contingency and any change order above $250,000. |
| Client-Side Project Manager | D. Okonkwo | Owns this plan and the dates in it. Approves change orders up to $250,000. Calls a re-plan when a trigger in section 11 is met. |
| Design Manager | S. Bhatt | Owns the design deliverables and the documentation program. Accepts design submissions. |
| Commercial Manager | R. Iversen | Owns the estimate, the bid process and the contract. Recommends award. |
| Library Services Manager | T. Yee | Owns the operational requirement, the fit-out and the move-in sequence. Accepts the building for service. |
| Facilities Manager | A. Delacroix | Accepts the operations and maintenance handover and owns the asset from that point. |

| 9. KEY RISKS |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Risk | Consequence | Response | Owner |
| These are the risks that could change this plan, not the risk register. Any H materializing is a re-plan trigger under section 11. |  |  |  |  |
| H | Building permit takes longer than the 90 working days assumed | Main works award and the construction start both move, and the fall program date in section 11 is at risk | Early works package advertised separately so site establishment and demolition can proceed under its own permit | Planning consultant |
| H | Construction documentation is 40 percent complete against a plan of 100 percent | The main works bid package cannot be issued, and every date after it moves | Additional documentation resource authorized; documentation status reported weekly to the Sponsor until it is complete | Design Manager |
| H | Main works bids come in above the estimate | A budget increase, or scope has to be cut after bids are in | Priced alternates in the bid package - the makerspace fit-out and the parking lot surface - so scope can come out without rebidding | Commercial Manager |
| M | Medium voltage switchgear lead time exceeds the 40 weeks assumed | Services rough-in and commissioning move, and substantial completion with them | Switchgear awarded ahead of the main works contract as an owner-supplied item | Procurement |
| M | Ground conditions differ from the geotechnical report of record | Substructure cost and duration both increase | Contingency held at the full amount until substructure is complete; no drawdown for any other purpose before then | Client-Side Project Manager |
| M | Temporary branch is not open before the existing building has to close | A gap in service, and the collection has nowhere to go | Move-in sequence reviewed monthly against the construction date; demolition cannot start until the temporary branch is operating | Library Services Manager |

| 10. ASSUMPTIONS AND CONSTRAINTS |  |
| --- | --- |
| Assumptions | Constraints |
| An assumption is believed and not confirmed; a constraint is fixed and the plan works inside it. |  |
| Development approval carries no condition that requires a design change. | Funding is capped at the approved amount. There is no further appropriation this cycle. |
| The geotechnical report of record is representative of the whole building footprint. | The existing branch must stay open until the temporary branch is operating. |
| Escalation of 3.5 percent a year is included to the midpoint of construction, and no further allowance is made. | Work within 65 ft of the school property line is restricted to school vacation periods. |
| Contingency is sufficient for the works remaining. It is inside the approved budget, not on top of it, and section 6 states what is left. | The adopted energy standard applies in full and is not tradeable against cost. |
| The second-year appropriation is confirmed before the main works contract is awarded. | Substantial completion is required before the start of the fall program year. |
| The site is available from the notice to proceed with no relocation beyond the temporary branch. | The collection cannot be in transit for more than eight consecutive weeks. |
| No hazardous material is present beyond the asbestos already surveyed in the 1978 annex. |  |

| 11. RE-PLAN TRIGGERS |  |
| --- | --- |
| Agree these while everything is on track. Meeting a trigger reissues this plan at the next version; it does not abandon it. |  |
| Cost | Forecast final cost exceeds the approved budget, or contingency drawdown passes 50 percent before substantial completion is certified. |
| Time | Substantial completion moves more than 20 working days from the baseline in section 5. |
| Scope | A change alters the approved gross square footage, the number of public spaces, or any statutory requirement. |
| Procurement | A long-lead award date in section 7 passes without an award. |
| Risk | Any risk rated H in section 9 materializes. |

| 12. SUPPORTING DOCUMENTS |  |  |
| --- | --- | --- |
| What you need | Where it lives |  |
| The task-level schedule | Construction Plan Template | This plan carries phases and milestones; that file carries the tasks under them. |
| The milestone chart and the Gantt view | Project Milestone Chart Template | Section 5 is the table. That file is the picture of it. |
| The scope statement in full | Project Scope Template | Section 3 is a page. A clause-by-clause scope statement is its own document. |
| The cost build-up | Construction Estimate Template and Basis of Estimate Template | Section 6 states what each phase costs. The estimate states how. |
| The full risk register | Risk Mitigation Plan Template | Section 9 carries the risks to this plan. The register carries all of them. |
| How the project will be governed | Project Execution Plan and Project Initiation Document | This plan states what will be done, not how it will be managed. |
| The running records during delivery | RFI Register, Issue Register and Change Log | Questions, issues and approved changes belong in those three. |

| REVISION HISTORY |  |  |  |
| --- | --- | --- | --- |
| Version | Date | Description of change | By |
| A plan that is edited in place stops being a reference of record. Bump the version, date it, and say what changed. |  |  |  |
| 1.0 | 1 Jul 2025 | Issued for business case approval | D. Okonkwo |
| 2.0 | 31 Mar 2026 | Reissued at completion of design development. Budget updated to the developed design estimate; procurement strategy split into an early works and a main works package. | D. Okonkwo |
| 3.0 | 31 Aug 2026 | Reissued with the construction documentation delay recorded, milestones from the building permit onward shown against baseline, and the main works award date flagged as passed. | D. Okonkwo |

APPROVAL

| Prepared by |  |  | Recommended |  |  | Approved |  |
| --- | --- | --- | --- | --- | --- | --- | --- |

Approval of this plan authorizes the work, the dates and the budget described in it. It does not authorize any change to them - see section 11.

| HOW TO USE THIS TEMPLATE |  |
| --- | --- |
| A project plan is not a project management plan | This document states WHAT will be done: scope, phases, dates, budget, procurement, risks, who decides. A project management plan states HOW it will be managed: the change control procedure, the reporting cadence, who signs which form. If you find yourself writing a procedure in here, it belongs in the Project Execution Plan instead. |
| Fill the document control block and section 1 first | If the one-page summary cannot be written, the plan is not ready to be written either. Everything after section 1 is the evidence for it. |
| Say what is not in scope | Section 3 has two columns and the right-hand one is the one that gets read in a dispute. A plan that lists only inclusions has not drawn a boundary. |
| Keep it at plan altitude | Phases and milestones, not tasks. The moment this document carries a task list it will disagree with the schedule that also carries one, and the reader will not know which is current. |
| Write the assumptions down even when they feel obvious | Section 10 separates assumptions from constraints on purpose. An assumption that turns out to be wrong is the most common reason a plan is re-planned, and an unwritten one cannot be tested. |
| Agree the re-plan triggers before you need them | Section 11 is easy to agree while everything is on track and almost impossible to agree once something has slipped. |
| Reissue the whole plan, versioned, rather than patching it | Bump the version, date it, and record what changed in the revision history. A plan that is edited in place stops being a reference of record. |

IMPORTANT This is a template and a worked example, not advice. The project, the people, the figures and every date in it are invented and illustrative. A project plan is a planning and approval document: it does not vary a contract, grant an extension of time, approve a payment or establish an entitlement, and where anything in it differs from an executed contract the contract governs. Replace the content with your own, have the cost and program figures verified by whoever is accountable for them, and have anything that may become a claim reviewed before you issue it.