## Gate Dashboard
PROJECT STAGE GATE TEMPLATE
Yellow cells are inputs. White cells calculate.
PROJECT DETAILS
Project Name |  |  |  | Project No.
Client |  |  |  | Project Manager
Project Sponsor |  |  |  | Estimated Project Value ($)
Current Stage |  |  |  | Report Date
Stage Name
STAGE AND GATE STATUS
Stage | Stage Name | Stage Status | Gate | Gate Review Date | Knockouts Failed | Weighted Score | Recommendation | Gate Decision | Deliverables Complete | Open Actions | Next Review
1 | Feasibility |  | Gate 1 — Proceed to Concept
2 | Concept Development |  | Gate 2 — Approve Business Case
3 | Detailed Design |  | Gate 3 — Commit to Delivery
4 | Execution |  | Gate 4 — Accept for Service
5 | Closeout |  | Gate 5 — Close and Realise Benefits
SUMMARY
Gates Passed
Knockouts Failed
Deliverables Complete
Open Actions
Visit mastt.com

## Schedule Dashboard
SCHEDULE DASHBOARD
SCHEDULE SUMMARY
Project |  |  |  |  | Today |  | 2026-09-16 |  |  |  | Complete
Current Stage |  |  |  |  | Variance to Baseline | [5 empty] | In Progress
Baseline Completion |  |  |  |  | Activities |  | 5 |  |  |  | Overdue
Forecast Completion |  |  |  |  | Behind Baseline | [5 empty] | Not Started | 5
STAGE TIMELINE
Months per Column |  |  |  | ■ Today
No. | Stage | Status | Activities | Complete | Start | Baseline Finish | Forecast Finish | % Complete | Duration (days) | Delay / Gain
1 | Feasibility |  | 1
2 | Concept Development |  | 1
3 | Detailed Design |  | 1
4 | Execution |  | 1
5 | Closeout |  | 1
Activities Due
Activities Complete
ACTIVITY SCHEDULE |  |  |  | ✔ Complete |  | ◆ In Progress |  | ◆ Overdue |  | ◇ Not Started
Icon | Activity | Stage | Key Milestone | Status | Start Date | Baseline Date | Planned Date | Actual Date | Forecast Date | Delay / Gain
★ | Gate 1 — Proceed to Concept | Feasibility | Yes | Not Started
★ | Gate 2 — Approve Business Case | Concept Development | Yes | Not Started
★ | Gate 3 — Commit to Delivery | Detailed Design | Yes | Not Started
★ | Gate 4 — Accept for Service | Execution | Yes | Not Started
★ | Gate 5 — Close and Realise Benefits | Closeout | Yes | Not Started
Visit mastt.com

## Stage Definitions
STAGE DEFINITIONS
STAGES AND GATES
Stage | Stage Name | Gate | Gate Purpose | Gateway Review Equivalent | Gate Owner
1 | Feasibility | Gate 1 — Proceed to Concept | Confirm the service need and approve investigation of options | Gate 1 — Concept and Feasibility
2 | Concept Development | Gate 2 — Approve Business Case | Approve the business case and the preferred option | Gate 2 — Business Case
3 | Detailed Design | Gate 3 — Commit to Delivery | Approve release to market and commitment of funds | Gates 3 and 4 — Readiness for Market, Tender Decision
4 | Execution | Gate 4 — Accept for Service | Accept the completed works for service and handover | Gate 5 — Readiness for Service
5 | Closeout | Gate 5 — Close and Realise Benefits | Close the project and confirm benefits realisation | Gate 6 — Benefits Evaluation
DECISION THRESHOLDS
No. | Decision | Threshold (%) | Definition
1 | Go | 75 | All must-meet criteria met and weighted score at or above threshold
2 | Conditional Go | 60 | All must-meet criteria met; proceed with recorded conditions
3 | Hold | 40 | Must-meet criteria met; case not yet sufficient — resubmit by agreed date
4 | Recycle or Kill | < Hold | Below Hold threshold, or any must-meet criterion not met
SCORING SCALE
Score | Definition
0 | Not addressed
3 | Partially addressed — major gaps
5 | Addressed — notable gaps or unverified evidence
8 | Largely met — minor gaps
10 | Fully met with evidence
WEIGHTING
Weighting | Definition
1 | Minor
3 | Important
5 | Critical
Visit mastt.com

## Gate Criteria
GATE CRITERIA AND SCORECARD
Project |  |  |  |  | Report Date
Client |  |  |  |  | Project No.
GATE SUMMARY
Gate | Gate Name |  | Knockouts Answered | Knockouts Failed | Criteria Scored | Weighted Score | Recommendation
1 | Gate 1 — Proceed to Concept
2 | Gate 2 — Approve Business Case
3 | Gate 3 — Commit to Delivery
4 | Gate 4 — Accept for Service
5 | Gate 5 — Close and Realise Benefits
GATE CRITERIA
Ref | Gate | Criterion | Criteria Type | Weighting | Knockout Result | Score | Weighted Score | Maximum Score | Result | Evidence | Comments
1.1 | 1 | Service need or problem statement defined and endorsed by the sponsor | Must-meet
1.2 | 1 | Need evidenced by data, not assumption | Must-meet
1.3 | 1 | Funding for the next stage identified | Must-meet
1.4 | 1 | Alignment with organisational strategy and asset plans | Should-meet | 5
1.5 | 1 | Options identified, including do-nothing and non-asset options | Should-meet | 4
1.6 | 1 | Order-of-magnitude cost range established | Should-meet | 3
1.7 | 1 | Key risks, constraints and dependencies identified | Should-meet | 4
1.8 | 1 | Stakeholders identified and initial consultation held | Should-meet | 3
1
1
1
2.1 | 2 | Business case approved by the delegated authority | Must-meet
2.2 | 2 | Preferred option selected with options analysis recorded | Must-meet
2.3 | 2 | Budget approved and funding source confirmed | Must-meet
2.4 | 2 | Concept cost estimate with stage-appropriate contingency | Should-meet | 5
2.5 | 2 | Program achievable, with milestones and critical dependencies | Should-meet | 4
2.6 | 2 | Risk register established; major risks have treatments | Should-meet | 4
2.7 | 2 | Procurement and contracting strategy defined | Should-meet | 3
2.8 | 2 | Statutory approvals pathway identified and programmed | Should-meet | 3
2.9 | 2 | Benefits defined, measurable and owned | Should-meet | 3
2
2
2
3.1 | 3 | Design complete to the required level and independently reviewed | Must-meet
3.2 | 3 | Pre-tender estimate within approved budget | Must-meet
3.3 | 3 | Statutory approvals obtained, or programmed and accepted | Must-meet
3.4 | 3 | Tender and contract documentation complete and consistent | Should-meet | 4
3.5 | 3 | Contract risk allocation settled | Should-meet | 4
3.6 | 3 | Program baselined with float identified | Should-meet | 4
3.7 | 3 | Risk register updated; contingency set against it | Should-meet | 4
3.8 | 3 | Stakeholder and community engagement plan in place | Should-meet | 3
3.9 | 3 | Delivery governance, roles and resourcing confirmed | Should-meet | 3
3
3
3
4.1 | 4 | Works complete to contract requirements | Must-meet
4.2 | 4 | Statutory certificates for occupation or use in place | Must-meet
4.3 | 4 | Defects recorded with rectification program agreed | Must-meet
4.4 | 4 | Commissioning and testing complete; results accepted | Should-meet | 5
4.5 | 4 | Operations and maintenance documentation delivered | Should-meet | 4
4.6 | 4 | Operator training and handover complete | Should-meet | 4
4.7 | 4 | Final cost forecast within approved budget | Should-meet | 3
4.8 | 4 | Warranties, as-built drawings and manuals received | Should-meet | 3
4
4
4
5.1 | 5 | Final account agreed; financial closure complete | Must-meet
5.2 | 5 | Defects liability obligations closed or assigned | Must-meet
5.3 | 5 | Project records archived | Must-meet
5.4 | 5 | Benefits realised against the business case, or measurement plan in place | Should-meet | 5
5.5 | 5 | Lessons learned captured and shared | Should-meet | 4
5.6 | 5 | Post-implementation review complete | Should-meet | 4
5.7 | 5 | Stakeholder satisfaction assessed | Should-meet | 3
5
5
5
Visit mastt.com

## Deliverables
GATE DELIVERABLES
Project |  |  |  |  | Report Date
Client |  |  |  |  | Project No.
GATE SUMMARY
Gate | Gate Name |  | Deliverables | Complete | Not Required | % Complete
1 | Gate 1 — Proceed to Concept |  | 5
2 | Gate 2 — Approve Business Case |  | 7
3 | Gate 3 — Commit to Delivery |  | 7
4 | Gate 4 — Accept for Service |  | 6
5 | Gate 5 — Close and Realise Benefits |  | 5
DELIVERABLES
Ref | Gate | Deliverable | Responsible | Due Date | Status | Date Completed | Days Overdue | Document Reference | Comments
1.1 | 1 | Strategic assessment / needs analysis
1.2 | 1 | Options paper
1.3 | 1 | Order-of-magnitude cost estimate
1.4 | 1 | Preliminary risk assessment
1.5 | 1 | Stakeholder map
1
1
1
2.1 | 2 | Business case
2.2 | 2 | Concept design report
2.3 | 2 | Concept cost estimate with contingency
2.4 | 2 | Risk register
2.5 | 2 | Master program
2.6 | 2 | Procurement strategy
2.7 | 2 | Benefits register
2
2
2
3.1 | 3 | Detailed design documentation
3.2 | 3 | Pre-tender estimate
3.3 | 3 | Tender and contract documents
3.4 | 3 | Baseline program
3.5 | 3 | Updated risk register and contingency assessment
3.6 | 3 | Statutory approvals
3.7 | 3 | Project management plan
3
3
3
4.1 | 4 | Practical completion certificate
4.2 | 4 | Commissioning and test reports
4.3 | 4 | As-built drawings and O&M manuals
4.4 | 4 | Defects list and rectification program
4.5 | 4 | Final cost forecast
4.6 | 4 | Handover plan
4
4
4
5.1 | 5 | Final account
5.2 | 5 | Post-implementation review
5.3 | 5 | Benefits realisation report
5.4 | 5 | Lessons learned report
5.5 | 5 | Archived project records
5
5
5
Visit mastt.com
Formulas:
Days Overdue = IF(OR([Complete]="",[Not Required]="Complete",[Not Required]="Not required"),"",IF(NOT(ISNUMBER([Complete])),"Due date is not a date",IF(TODAY()>[Complete],TODAY()-[Complete],"")))

## Gate Decisions
GATE DECISIONS AND APPROVALS
Project |  |  |  |  | Report Date
Client |  |  |  |  | Project No.
DECISION RECORD
Gate | Gate Name | Review Date | Recommendation | Gate Decision | Conditions | Conditions Due | Rationale | Decision Maker | Decision Date | Next Review | Scorecard Check
1 | Gate 1 — Proceed to Concept
2 | Gate 2 — Approve Business Case
3 | Gate 3 — Commit to Delivery
4 | Gate 4 — Accept for Service
5 | Gate 5 — Close and Realise Benefits
DECISION MATRIX
No. | Decision |  | Basis |  |  |  | Action
1 | Go |  | All must-meet criteria met; weighted score at or above the Go threshold |  |  |  | Proceed to next stage; release funding and resources
2 | Conditional Go |  | All must-meet criteria met; weighted score in the Conditional Go band |  |  |  | Proceed; each condition assigned an owner and due date and tracked to closure
3 | Hold |  | Must-meet criteria met; weighted score in the Hold band or evidence incomplete |  |  |  | Pause; no new commitments; resubmit at the agreed review date
4 | Recycle |  | Must-meet criterion not met or score below Hold; the case can be recovered |  |  |  | Return to current stage for rework; re-run the gate
5 | Kill |  | Must-meet criterion not met or score below Hold; the case cannot be recovered |  |  |  | Stop; close out commitments; archive records
APPROVAL WORKFLOW
Step | Role |  | Responsibility |  |  |  | Name | Organisation |  | Gates
1 | Project Manager |  | Prepare gate submission, deliverables and evidence
2 | Project Sponsor |  | Confirm the case; recommend a decision
3 | Independent Reviewer / PMO |  | Review evidence; challenge scores; confirm readiness
4 | Project Control Group / Steering Committee |  | Make the gate decision; set conditions
5 | Gate Owner |  | Approve the decision; authorise the next stage
6
7
SIGN-OFF
Gate | Gate Name | Prepared By |  | Date | Recommended By | Date | Approved By |  | Date | Signature
1 | Gate 1 — Proceed to Concept
2 | Gate 2 — Approve Business Case
3 | Gate 3 — Commit to Delivery
4 | Gate 4 — Accept for Service
5 | Gate 5 — Close and Realise Benefits
Visit mastt.com

## Gate Review Meeting
GATE REVIEW MEETING
Project |  |  |  |  | Report Date
Client |  |  |  |  | Project No.
MEETING DETAILS
Gate |  |  |  |  | Chair
Meeting Date |  |  |  |  | Minute Taker
Time |  |  |  |  | Location
Gate Name
ATTENDEES
No. |  | Name | Role | Organisation | Attendance
1
2
3
4
5
6
7
8
AGENDA
No. |  | Agenda Item | Lead | Duration (min) | Outcomes
1 |  | Purpose and decision required
2 |  | Stage summary
3 |  | Deliverables status
4 |  | Must-meet criteria
5 |  | Should-meet scorecard
6 |  | Cost, program and risk position
7 |  | Gate decision and conditions
8 |  | Actions and next gate
9
10
ACTION TRACKER
Ref | Gate | Action | Owner | Due Date | Status | Date Closed | Days Overdue | Comments
Visit mastt.com
Formulas:
Days Overdue = IF(OR([Organisation]="",[Attendance]="Closed"),"",IF(NOT(ISNUMBER([Organisation])),"Due date is not a date",IF(TODAY()>[Organisation],TODAY()-[Organisation],"")))

## How to use
HOW TO USE THIS WORKBOOK
Delete this sheet before you issue the document if you do not want it seen.
Sheets
- Gate Dashboard — project details entered once; status, scores, recommendations, deliverable completion and open actions read from the other sheets.
- Schedule Dashboard — each activity or milestone with its stage, start, baseline, planned and actual dates. Status, delay or gain, stage bars and the timeline calculate. The 24-column timeline scales itself from the earliest date to the latest.
- Stage Definitions — stage and gate names, decision thresholds, scoring scale and weighting. Every other sheet reads from here.
- Gate Criteria — must-meet knockouts (Yes/No) and weighted should-meet scores (0 to 10). The gate summary gives the recommendation.
- Deliverables — the evidence pack per gate, with responsibility, due date and status.
- Gate Decisions — decision record, decision matrix, approval workflow and sign-off.
- Gate Review Meeting — meeting details, attendees, agenda and action tracker.
Set-up
- Agree stages, gates, criteria, weightings and thresholds with the sponsor before the first gate review. Projects under about $10M typically run three gates — leave unused stages blank.
- The prefilled criteria, deliverables, roles and agenda are a starting set for an owner-side capital project. Edit, delete or add rows.
- Thresholds of 75, 60 and 40 percent are a common starting point, not a standard.
Decision rules
- One must-meet No gives Recycle or Kill regardless of score. The choice between Recycle and Kill is the decision makers'.
- Weighted score = sum of weighting x score ÷ sum of weighting x 10, over the criteria scored.
- The recommendation reads Incomplete until every knockout is answered and at least one criterion is scored.
- Scorecard Check on Gate Decisions flags a decision that differs from the recommendation. Record the rationale.
Housekeeping
- Sheets are protected without a password. Review > Unprotect Sheet lifts it.
- Enter dates as dates (30/06/2027). Days Overdue, Status and Delay / Gain depend on it.
- Schedule Dashboard: Forecast Date is the actual date if entered, otherwise the planned date, otherwise the baseline. Delay / Gain compares it with the baseline. A stage bar runs from the earliest start to the latest forecast date of its activities.
- Insert > Pictures to add your logo. The Mastt mark may be deleted.
- Delete this sheet before issuing.
Visit mastt.com