## Sheet1
Task | Description | Owner | Attendees | Notes
1 | Cathedral Conducts Client Kickoff Call | Cathedral | Cathedral /Client Marketing/IT | DT Recommends sending client survey questions to the client prior to kickoff meeting. Cathedral to send the client the data extract format document. Requirements for extracts, product code descriptions, file sizes are covered in the call. Cadence for data extract upload is established (monthly/daily). Sizes of files for each channel are established.
2 | Client Sends Product Codes/Descriptions to Cathedral | Client
3 | Client Uploads Data Extracts to Cathedral's FTP Site | Client
4 | Cathedral Sends Client Survey Handoff Form / Project Schedule to DeepTarget | Cathedral |  | Send completed Cathedral/DT Implementation Handoff form to support@deeptarget.com. Also send/include project schedule/timeline.
5 | Cathedral Sends Product Codes/Descriptions to DeepTarget | Cathedral |  | These files should come from the client and contain the product codes/descriptions for all deposit/certificate/loan types.
6 | Cathedral Uploads Client Data to DeepTarget's FTP Site | Cathedral |  | .csv files should be encrypted (PGP) before uploading to DT.
7 | DeepTarget Sets up Client Instance | DeepTarget |  | Client Instance is created, Cathedral Group is set up, Client/Cathedral users are added with appropriate permissions, set of quick start campaigns are created, data loader created, data load automation is set up. Stacks for testers are uploaded. Quick Start campaigns and images will be static for all clients; images (multiple sizes) for the quick-start campaigns are provided by Cathedral design team. Timeline for this is typically one week (unless there is an issue with the data files).
8 | DeepTarget Sends Application URL and Login Credentials to Client/Cathedral Users | DeepTarget
9 | DeepTarget Sends Client-Specific URL to Cathedral | DeepTarget |  | This is the URL to use to enable DeepTarget in the ePortal/Print system. The Cathedral-DeepTarget Implementation Setup Completion form will be used to communicate that Setup has been completed. This will be sent to a TBD email address.
10 | Cathedral Enables DeepTarget in System for Testers | Cathedral
11 | Cathedral Conducts Client Training | Cathedral | Cathedral / Client Users
12 | Cathedral Conducts Client Verification Testing | Cathedral | Cathedral / Client Testers
13 | Cathedral Notifies DeepTarget that Client is Ready for Go-Live | Cathedral | Cathedral / DeepTarget | DeepTarget uploads stacks for all end-users
14 | Cathedral moves Client to Live Production | Cathedral
15 | Project Complete