## Application Checklist
100 North Street, 7th Floor ¦ Baton Rouge, LA 70802-5264 800.450.8115 ¦ OpportunityLouisiana.com
Application Checklist
Before submitting your application, please review the checklist below to ensure all required sections and supporting documentation are complete. Incomplete applications will not be accepted. Applicants with missing information will be notified by Louisiana Economic Development.
APPLICATION
Applicant Overview
Review for Completion
Site
|  |  | x | Name and Contact Information
Budget
|  |  | x | Submit Detailed Budget and Calculations
|  |  | x | Proof of Funding Match
Submit Quote(s) for Eligible Site Costs
Timeline Overview
|  |  | x | Submit Detailed Budget and Calculations
Due Diligence Studies
|  |  | x | Submit Supplemental Documents
SUPPLEMENTAL DOCUMENTS
Letters of Support from the following (if not the eligible applicant):
|  |  | x | Regional Economic Development Organization
|  |  | x | State House Representative
|  |  | x | State Senator
| x | Legal Description of Property
| x | Deed of Current Ownership or Option to Purchase Property
| x | Parcel Map
| x | Aerial Map
| x | Topography Map
| x | Wetlands Map
| x | Floodplain Map
| x | Zoning Map
| x | Utility Map
Transportation Map
FEES & COMMUNICATION
Submit Application via Email to FastSites@la.gov
Ensure each email does not exceed 30MB to support successful delivery.
Applicant will receive email confirmation with assigned Application ID from FastSites@la.gov.
Application ID will be used to identify and track your submissions.
Submit additional Supplemental Documents via email to FastSites@la.gov (multiple submissions may be required).
Advance Fee
$250 due upon application submission.
Include Application ID on check memo line.
Mail check to:
Louisiana Economic Development
Attn: FastSites
P.O. Box 94185
Baton Rouge, LA 70804-9185
Questions, Contact FastSites Team
FastSites@la.gov

## Applicant Overview
100 North Street, 7th Floor ¦ Baton Rouge, LA 70802-5264 800.450.8115 ¦ OpportunityLouisiana.com
All shaded areas should be completed.
Eligible Applicant Primary Contact
Name: |  | Greg Richardson
Title: |  | Port Director
Organization: |  | Columbia Port Commission
Mailing Address: |  | 212 Jackson Street / P.O. Box 367
City, State, Zip: |  | Columbia, La 71418
Telephone: |  | 3185941657
Email: |  | greg@portcolumbia.com
Eligibility Requirements |  | Response
Is the applicant an eligible applicant? *Eligible applicants may include a local or regional economic development group, municipality, nonprofit organization, redevelopment authority, or public subdivision. |  | Yes, the Columbia Port Commission is a public subdivision of the State of Louisiana
Has the eligible applicant engaged with any public subdivisions regarding this site? If so, list the organizations involved. |  | NA
Is the site private or publically owned? |  | publically owned
Is there an option agreement associated with this site? *If so, describe the option terms, including the holder of the option and expiration date. Outline how the eligible applicant intends to execute the option. |  | No
Will the site be marketable within a priority sector? *Priority sectors include Agribusiness, Aerospace & Defense, Energy, Life Sciences, Process Industries and Technology. |  | Yes, as a regional public port with a emphasis on green energy industries
Is the site certified? |  | Yes, www.louisianasiteselection.com, www.portcolumbia.com documents fastsite LED Certification Site Document
Is the site located in a distressed community? *Lowest 25% of parishes for average wages per BLS, or defined as deeply distressed by federal New Markets Tax Credit Program. | Link | Yes, Caldwell Parish entire parish is classified as a fully distressed community
Will jobs be created as a result of this site's development? If so, indicate the estimated number of jobs, average wage and whether positions will be permanent or temporary. |  | Yes, jobs will be created, 10 permanent full time jobs, average wages $60,000
How does the eligible applicant intend to use awarded funds to improve the infrastructure of this site, including but not limited to: rail and road access, utility extension, wetland mitigation, demolition, expansion, or land purchase? |  | 1) Rail Expansion - The port has a LaDOTD PPP grant of $15 million to improve infrastructure at the Port of Columbia, of which $4.5 million is dedicated to constructing a railspur. The Port has also received a $1 million from DRA to assist with the railspur project. The Port has nearly $2 million in Capital Outlay but these funds are currently in Priority 5. The Proposed railspur project is $7 million, the Port needs $1.5 million to advance the project, The Port proposes utilizing LED's Fast Site program to close the infrastructure funding gap so that the rail construction project can be completed. In accordance with Program guidelines the requested funds will only be used for construction of the railspur.
Does the eligible applicant intend to deploy funds within 9 months of a fully executed contract? |  | YES
Has the eligible applicant identified matching funds totaling at least 50% of the total estimated project cost if the site is publically owned, or 80% if privately owned? *Other sources of LED funding may not be used to satisfy the applicant's required project contribution. |  | YES, LaDOTD PPP FOIK Infrastructure Project was a $15 million grant awarded to the Port of Columbia to purchase 200 acres, construct access and perimeter roads, and construct a railspur. The Port has approximately $5.5 million of dedicated State and Federal funds for the Railspur Project. available funds to leverage the requested $1.5 million in Fast Sites funds. The Port of Columbia in the past three years has been awarded nearly $50 million in state and federal grants associated with developing port infrastructure. The Port was awarded $500,000 as part of LED's LCRED program those funds are being used as part of our DHS Grant for the installation of 30,000 linear feet of security fencing, and EDA grant Emergency Staging Area, these funds will be exhausted prior to the end of 2025 and in accordance with Fast Site guidelines are not associated with the Rail Project.
Impact Statement: Describe the scope, purpose, and subsequent public benefit of the site development project(s). Explain how the requested funding will improve the site’s readiness for investment, accelerate development timelines, and enhance the state’s competitiveness in attracting new business, industry, or strategic infrastructure.
The $7 million Rail Spur Construction Project at the Port of Columbia will transform the site into a fully rail-served, development-ready industrial hub—directly aligned with the goals of LED’s FastSite Program. It will immediately enhance multimodal service to existing tenants, including Louisiana Green Fuels (LGF), Terral RiverService, timber processors, agricultural producers, and regional manufacturers. Rail access remains the Port’s most significant infrastructure gap; completing this spur will reduce tenant risk, accelerate delivery timelines, and unlock new industrial investment across the region. The Port of Columbia has already secured nearly $50 million in state and federal grants to advance infrastructure development—including the acquisition of over 200 acres, construction of access roads, and the planned development of a truck parking facility, emergency staging area, dock improvements, and a solar manufacturing facility with a 3 MW solar farm. The Port has also received multiple regional strategic planning grants to ensure its expansion serves as a catalyst for broader economic growth across the Ouachita-Black River region. Our Fast Site project includes construction of a modern rail spur, on-site staging and switching, and a Class I mainline connection to Union Pacific, creating seamless integration with truck and barge operations. These improvements will directly support LGF’s shipment of biomass feedstocks, carbon capture components, and renewable fuels while enabling Terral to move agricultural commodities (e.g., 100+ railcars of cottonseed) and industrial aggregates between river, rail, and highway with greater efficiency. Timber shippers, solar component manufacturers, and grain producers will gain access to competitive rail service for the first time—expanding regional freight capacity and reducing reliance on long-haul trucking. Importantly, this investment positions the Port of Columbia as one of the few certified multimodal FastSites in North Louisiana, offering direct access to rail, river, highway, and utility infrastructure in a fully developable industrial setting. With the spur in place, the Port can eliminate up to 12–18 months of development uncertainty for new projects—accelerating timelines, improving competitiveness, and reducing capital risk for potential investors. By filling this critical infrastructure gap, the FastSite-supported rail spur will strengthen the regional supply chain and the public benefits are substantial: enhanced freight capacity, increased private investment, lower transportation costs, expanding job opportunities, and long-term growth in clean energy, agribusiness, and advanced manufacturing. These impacts add resiliency within a rural economy poised for growth. With state support, the Port of Columbia will deliver a turnkey rail-served industrial site—ready for tenant expansion, job creation, and sustained economic impact across the Ouachita-Black River Region.
Financial Planning: Please list the total estimated eligible project costs, including the amount of funding requested. Attach at least 2 quotes that support this estimate.
The total estimated eligible project cost for the Rail Spur Construction Project is $7 million, and the Port of Columbia is requesting $1,500,000 in FastSite funding to close the final construction gap created by the delayed release of Priority 5 Capital Outlay funds. In accordance with LED FastSite Program requirements, FastSite loan funds will be used exclusively for construction activities and will not be applied to engineering, design, or pre construction services. All engineering and design work has already been funded through other secured sources. Because the project cannot be advertised for public bid until full funding is in place, the Port has submitted stamped engineering design plans and a comprehensive cost estimate in lieu of contractor quotes. These documents were prepared by licensed engineers with extensive rail infrastructure experience and include a complete, itemized breakdown of: Rail bed preparation; Track materials and installation; Drainage and stormwater improvements; Switching systems; On-site staging track development; and Class I mainline connection to Union Pacific The engineering estimate incorporates current unit prices, regional cost conditions, and Class I railroad construction standards, making it the most accurate and reliable cost basis available prior to bidding. Once funding is secured, the Port will fully comply with Louisiana Public Bid Law and solicit competitive construction bids to establish final pricing. Complete documentation of the project’s engineering cost estimates, rail design plans, and detailed construction budget is available online at www.portcolumbia.com, under “Documents” > “Fast Site.” These attached engineering documents demonstrate the Port’s due diligence, validate the total project cost, and confirm that the FastSite request is both appropriate and necessary to complete this critical multimodal infrastructure investment.
Return of Investment: Please describe the anticipated financial or economic benefit to the fund, including timing, amount, and mechanism of return (e.g., lease payments, revenue sharing, land sale, or other quantifiable impact). Include any assumptions used to calculate the return and how it aligns with the overall project timeline.
The Port of Columbia is advancing a $7 million rail spur construction project to support increased multimodal freight operations, unlock new industrial development, and enable full-scale operations for tenants such as Louisiana Green Fuels (LGF). The new rail infrastructure will transform the Port into a fully rail-served logistics hub along the Ouachita-Black River corridor. To date, the Port has secured $4.5 million from the Louisiana Department of Transportation and Development (LaDOTD) Port Priority Program and $1 million from the Delta Regional Authority (DRA). The Port is requesting $1.5 million from the LED FastSite Program to complete the project’s capital stack. FastSite funds will be used exclusively for eligible construction costs, consistent with LED program requirements. This public investment is essential to delivering a project with long-term economic, operational, and fiscal returns to the State of Louisiana. The Port has developed a conservative, multi-stream revenue strategy to fully repay the $1.5 million loan within the required five-year window. This plan leverages three primary revenue sources tied directly to the construction of the rail spur: The first source is land lease revenue. The Port will increase lease rates on 117 existing leased acres from $1,500 to $2,025 per acre, generating a consistent $61,425 annually. In Year 1, the Port will lease an additional 35 acres, with total leased acreage growing by 10 percent annually thereafter. All new acreage will lease at the updated $2,025 rate, producing a reliable and growing revenue stream. The Port currently has over 400 acres. The second source is rail usage revenue. The Port expects to handle 500 railcars in Year 1, with usage increasing to 1,000 cars by Year 5 as LGF operations scale. A fee of $125 per railcar will be charged for loading, unloading, and equipment use, consistent with regional market benchmarks. The third source is rail storage revenue. The project includes development of 10 railcar storage spaces designed to accommodate long-term tenant or transient usage. While initial demand is expected to be modest, the Port anticipates 25 percent utilization—approximately 900 cars per year—at $35 per day. This results in a conservative storage revenue estimate of $31,500 per year. Five-Year Revenue Summary Year Lease Revenue Rail Revenue Storage Revenue Total Annual Revenue 1 $132,300 $62,500 $31,500 $226,300 2 $163,080 $78,125 $31,500 $272,705 3 $196,938 $93,750 $31,500 $322,188 4 $234,182 $109,375 $31,500 $375,057 5 $275,150 $125,000 $31,500 $431,650 Total — — — $1,627,900 These projections indicate that rail usage fees, increased land-lease revenue, and railcar storage income will generate more than $1.6 million within five years, fully covering the LED FastSite loan obligation. This ROI figure reflects only the Port’s direct revenue from land leases, rail usage, and storage fees. It does not include wages from new jobs or broader economic multipliers. Including those would yield a significantly higher total economic impact, but this analysis conservatively focuses on measurable project-generated revenue to the Port. The return on investment was calculated based on $5.5 million in secured matching funds and $1.6 million in projected revenue, resulting in total benefits of $7.1 million over five years. This yields a conservative ROI of 3.75 to 1—not including payroll or induced impacts. The Port recognizes that infrastructure-driven growth can involve market fluctuations and timing uncertainties. While full repayment is confidently expected within five years, the Port views the LED FastSite loan as a construction-phase bridge loan that must be retired on schedule—either through operating revenue or, if needed, a guaranteed financial instrument. What makes FastSite uniquely valuable is its role in delivering upfront capital, unlike most state and federal infrastructure grants, which are reimbursable only after expenses are incurred. This feature allows the Port to advance construction without delay, begin generating revenue sooner, and mitigate risks related to cost inflation and market timing. In this way, the FastSite program fills a critical financing gap in Louisiana’s infrastructure toolkit. It empowers public entities like the Port of Columbia to align real-time capital needs with project schedules and development momentum. Should actual revenue fall short of full repayment by the end of the five-year term, the Port will issue a revenue-backed bond to cover the remaining balance. This bond will be secured by recurring lease payments, rail usage fees, and storage revenue, ensuring complete repayment without burdening local taxpayers. Importantly, this bond strategy not only guarantees LED’s return on investment, it also strengthens the Port’s capital structure and enables it to leverage future infrastructure projects using the same revenue streams. This approach reflects the Port’s broader commitment to innovative public financing, performance-driven project delivery, and long-term economic development aligned with the mission and intent of the LED FastSite Program.
Matching Funds Description: List the total amount of matching funds to be leveraged for this project. Describe the source(s), type (e.g., cash, in-kind), purpose, and status of the funds. Include any relevant documentation to support the commitment and availability of the match.
The Port of Columbia will leverage a total of $5,500,000 in secured matching funds for the Rail Spur Construction Project. These funds consist of: $4,500,000 in cash funding awarded through the Louisiana Department of Transportation and Development (LaDOTD) Port Priority Program (PPP), and $1,000,000 in cash funding awarded through the Delta Regional Authority (DRA). Both awards are dedicated specifically to the design and construction of the Port’s rail spur and associated infrastructure. Together, this $5.5 million match demonstrates a strong financial commitment and ensures that the LED FastSite investment will leverage significant state and federal resources to complete a critical multimodal infrastructure project. The Port has attached official award letters verifying the commitment and availability of these funds (available at www.portcolumbia.com/documents/FastSite). These matching resources are fully obligated to the rail spur project and serve as the primary financing for construction. The fund type is cash, and the funds are currently available for drawdown. The requested $1,500,000 FastSite loan will close a critical funding gap caused by the delayed release of Priority 5 Capital Outlay funding. The FastSite program’s ability to provide upfront, non-reimbursable capital makes it uniquely valuable for bridging this timing gap—ensuring uninterrupted construction progress on a shovel-ready, high-impact infrastructure project.

## Site Overview v1 (hidden)
Louisiana Economic Development 100 North Street, 7th Floor Baton Rouge, LA 70802-5264 800.450.8115 OpportunityLouisiana.com | Site Investment & Infrastructure Improvement Incentive Application
All shaded areas should be completed.
Site Information
Site Name
Physical Street Address
City, State, Zip
Coordinates (Lat/Long; in decimal format)
Total Acres
Total Contiguous Acres
Stand Alone Site or Industrial Park for Multiple Users?
Current Site Owner
Transaction Preference (sale/lease/etc.)
Price per acre; Lease price per acre
Inside the City Limits?
Zoning Classification
Rezoning required for Industrial?
Adjacent Zoning
Former Use?
Is the site within municipal/city limits?
Any height restrictions?
Any noise restrictions?
Any outdoor storage restrictions?
Any other major covenants or restrictions?
Link to Site Selection Center
Site Condition | YES/NO | If YES, please provide a description.
Does the site have a slope? What percent?
Are there any structures, crops or timber on the site?
Is the site currently being used (agriculture, etc.)? (see line 19)
Are floodplains present on the site?
** If YES to existing floodplain, on average, what is the difference in feet between natural grade and base flood elevation?
Are floodways present on the site?
** If YES to existing floodways, has a no-rise certification been completed and approved?
Are wetlands present on the site?
Current or former landfill on site?
Easements that impact development?
Transportation/Logistics | Distance (miles) | Name and Description
Nearest interstate
Nearest four-lane highway
Nearest two-lane highway
Nearest river port
Nearest intermodal facility
Nearest commercial airport
Nearest general aviation airport
Nearest rail line (if applicable, provide a description of rail line (main line, spur) and the class and name of the rail provider (Class I, Class III Shortline) )
Neighboring Uses | Distance (miles) | Name and Description
Nearest residential area
Nearest school
Nearest hospital
Nearest fire station
Nearest park
Utilities: Electricity | Response | Additional Details
Name of Electric Provider
Distance to nearest distribution line (feet)
Distribution voltage (kV)
Distance to nearest transmission line (miles)
Transmission voltage (kV)
Name or address or Lat/Long of nearest substation (miles)
Distance to nearest substation (feet)
Voltage and capacity of substation
Please provide a description what improvements are necessary to provide at least 3 MW of electric capacity Assume a 75% load factor and 24/7 operation
Please provide an estimated cost of these electric improvements
Please provide an estimated schedule of these electric improvements (months)
Please provide a description of any additional considerations involved with these necessary to facilitate electric improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.)
Utilities: Natural Gas | Response | Additional Details
Name of Natural Gas Provider
Distance of the nearest natural gas line to the edge of the site (feet)
Line Size (in)
Current Pressure (psi)
Please provide a description what improvements are necessary to provide at least 15 MCF per hour of natural gas capacity Assume 5-15 psi and consistent load across 24/7 operation
Please provide an estimated cost of these natural gas improvements
Please provide an estimated schedule of these natural gas improvements (months)
Please provide a description of any additional considerations involved with these necessary to facilitate natural gas improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.)
Utilities: Telecommunications | Response | Additional Details
Name of Telecom Provider
Distance to site (feet)
Estimated Timeline required to establish service (weeks)
Utilities: Wastewater | Response | Additional Details
Name of Wastewater Provider System
Distance of nearest wastewater line to edge of site (feet)
Line Size (inches)
Line Type (Gravity/Force Main)
Current Pressure (psi) if, applicable
Anticipated capacity requested from sewer system (GDP)
Does the sewer collection system have sufficient excess capacity for the site?
What is the current excess capacity of the wastewater line in gallons per day?
Name or address or Lat/Long of Wastewater Treatment Plant
Distance from Site (miles)
What is the current excess capacity of the wastewater treatment plant in gallons per day?
Does the wastewater treatment plant have sufficient excess capacity for the site?
If NO, Please provide a description of what improvements are necessary to provide at least 75,000 gallons per day of the required wastewater capacity
Please provide an estimated cost of these wastewater system improvements
Please provide an estimated schedule of these wastewater improvements (months)
Please provide a description of any additional considerations involved with these necessary to facilitate waste water improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.)
Utilities: Water | Response | Additional Details
Name of Water Provider System
Public Water System ID Number
Distance from nearest water line to the edge of the site (feet)
Line Size (inches)
Current Pressure (psi)
Anticipated demand from water system in gallons per day (GPD)
What is the current excess capacity of the potable water line in gallons per day?
Name of Water Treatment Plant
Distance from Site (miles)
What is the current excess capacity of the potable water system in gallons per day?
Does the water system have sufficient excess capacity for the site?
If NO, Please provide a description of what improvements are necessary to provide at least 100,000 gallons per day of the required water capacity
Please provide an estimated cost of these water system improvements
Please provide an estimated schedule of these water system improvements (months)
Please provide a description of any additional considerations involved with these necessary to facilitate industrial and/or potable water improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.)
ARCHIVED VERSION
DO NOT USE 10/8/2025

## Site
100 North Street, 7th Floor ¦ Baton Rouge, LA 70802-5264 800.450.8115 ¦ OpportunityLouisiana.com
All shaded areas should be completed.
Site Information
Site Name | Port of Columbia
Physical Street Address | 133 Riverton Campground Road
City, State, Zip | Columbia, La. 71418
Parish | Caldwell Parish
Coordinates (Lat/Long; in decimal format) | 32.186237; -92.103975
Total Acres | 400
Total Contiguous Acres | 400
Stand Alone Site or Industrial Park for Multiple Users? | Public Port
Current Site Owner | Columbia Port Commission
Transaction Preference (sale/lease/etc.)
Price per acre; Lease price per acre | Port owned, $10,000 per acres, currently leases for $1,500 per acre per year currently have 117 acres leased to LGF and Terral Riverservices.
Zoning Classification
Rezoning required for Industrial? | no
Former Use? | agriculture
Is the site within municipal/city limits? | no
Any other major covenants or restrictions? | none
If included on the Site Selection Center, please include link. | www.louisianasiteselection.com, www.portcolumbia.com document/fastsite/LED Site Certification Document
Site Condition | Yes/No | If yes, please provide a description.
Does the site have a slope? What percent? | no | relatively flat
Are there any structures, crops or timber on the site? | Yes | 20,000 sq.ft cottonseed warehouse, Aggregate yard and corn fields, with planned construction of 8,000 sq.ft warehouse and crew facilities Emergency Stagingn Area which will serve as a rail staging/loading facility during blue sky days.
Are floodplains present on the site? | Yes
** If YES to existing floodplain, on average, what is the difference in feet between natural grade and base flood elevation? |  | While the port is within the boundary of the 100 year flood plain Map, a significant portion of the property is above the 100 year flood elevation with the remaining property being less than 1 - 2 feet below the 100 year flood elevation. Flood map and site elevations can be found within our LED Site Certification Document on our webpage www.portcolumbia.com documents fastsite
Are floodways present on the site? | no
** If YES to existing floodways, has a no-rise certification been completed and approved?
Are wetlands present on the site? | yes | Our ESA has identifed wetland areas within the Port Boundary, however none of these identified areas are within the boundaries for the railspur construction. www.portcolumbia.com documents fast site LED Site Certification Document as well as updated wetland maps within our NEPA studies
Current or former landfill on site? | no
Easements that impact development? | no
Transportation/Logistics | Distance (miles) | Name and Description
Nearest interstate | 25 miles | I-20
Nearest four-lane highway | 0.5 miles | US165 runs adjacent to property
Nearest two-lane highway | 0.5 miles | Riverton Campground Road intersects property and is the access road to port.
Nearest river port | 0 | Port of Columbia is the nearest Port
Nearest intermodal facility | 0 | Upon completion of the rail spur at the port, Greater Ouachita Port 40 miles West Monroe
Nearest commercial airport | 30 | Monroe Regional Airport
Nearest general aviation airport | 5 | Columbia Airstrip
Nearest rail line (if applicable, provide a description of rail line (main line, spur) and the class and name of the rail provider (Class I, Class III Shortline) ) | 0 | Mail line, Class 1 - Union Pacific main north south line
Neighboring Uses | Distance (miles) | Name and Description
Nearest residential area | 0.5 | Riverton RV Park contains 20 residents with 6 perment homes
Nearest school | 8 | Caldwell Parish High School
Nearest hospital | 8 | Caldwell Memorial and Citizen Medical Center
Nearest fire station | 3 | Cory Volunteer Fire Department
Nearest park | 0.5 | USCOE Riverton Campground Boat launch and swim area
Utilities: Electricity | Response | Additional Details
Name of Electric Provider | 0.5 | Entergy
Distance to nearest distribution line (feet) | 500 | Distribution line run along US 165
Name or address or Lat/Long of nearest substation | 3 | Riverton Substation
Distance to nearest substation (feet) | 15000
Please provide a description of any considerations involved necessary to facilitate electric improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.) |  | The Port has electrical service, however the Peak load capcity available at the site is 1MW which will have to be expanded to accommodate the growth of the Port. The Port has received a DOTD PPP grant to construct a 3 MW solar farm to assist with electrical grid upgrade at the Port of Columbia.
Utilities: Natural Gas | Response | Additional Details
Name of Natural Gas Provider |  | Atmos Energy
Distance of the nearest natural gas line to the edge of the site (feet) | 5000 ft | runs along US 165
Line Size (in) |  | 3 inch line
Please provide a description of any considerations involved necessary to facilitate natural gas improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.) |  | the port is located within 2 miles of two transmission gas pipelines,
Utilities: Telecommunications | Response | Additional Details
Name of Telecom Provider |  | AT&T
Distance to site (feet) | onsite
Estimated Timeline required to establish service (weeks) | 1
Utilities: Wastewater | Response | Additional Details
Name of Wastewater System |  | no existing wastewater utilities at or near the site, The Port is working with the Columbia Eastside Sewage District which operates the Caldwell Parish Industrial Parks Sewage system to pursue funds to incorporate the Port. Our Tenant LGF will be developing its own waste water treament facility which will utilized by most of the Port's proposed operations. The planned construction of our Emergency Staging Area includes establishing bathroom facilities at the Port which will service the rail operations.
Distance of nearest wastewater line to edge of site (feet)
Line Size (inches)
Line Type (Gravity/Force Main)
Current Pressure (psi) if, applicable
What is the current excess capacity of the wastewater line in gallons per day?
Name or address or Lat/Long of Wastewater Treatment Plant
Distance from Site (miles)
What is the current excess capacity of the wastewater treatment plant in gallons per day?
Please provide a description of any considerations involved necessary to facilitate waste water improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.) |  | While the rail project will not address the sewage issue, the port has plans to pursue a $2 million dollar USDA Community Facility Grant to connect the Port of Columbia and Nearby residents with the Columbia Eastside Sewage System which is located within 3 miles, which does require a rail and 4 lane highway crossing to connect the systems.
Utilities: Water | Response | Additional Details
Name of Water System |  | Columbia East Side
Public Water System ID Number
Distance from nearest water line to the edge of the site (feet) | onsite
Line Size (inches) | 4 inch | as well as a 10 inch main line
Current Pressure (psi) | 60
What is the current excess capacity of the potable water line in gallons per day? | 0.6 MGD
What is the current excess capacity of the potable water system in gallons per day? | 0.6 MGD
Please provide a description of any considerations involved necessary to facilitate industrial and/or potable water improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.) |  | The Port is working with the Columbia East Side Water System to obtain a water sector grant to install an elevate water tank at the Port

## Site Overview v2 (hidden)
Louisiana Economic Development 100 North Street, 7th Floor Baton Rouge, LA 70802-5264 800.450.8115 OpportunityLouisiana.com | Site Investment & Infrastructure Improvement Incentive Application
All shaded areas should be completed.
Site Information
Site Name
Physical Street Address
City, State, Zip
Coordinates (Lat/Long; in decimal format)
Total Acres
Total Contiguous Acres
Stand Alone Site or Industrial Park for Multiple Users?
Current Site Owner
Transaction Preference (sale/lease/etc.)
Price per acre; Lease price per acre
Zoning Classification
Rezoning required for Industrial?
Former Use?
Is the site within municipal/city limits?
Any other major covenants or restrictions?
Link to Site Selection Center
Site Condition | YES/NO | If YES, please provide a description.
Does the site have a slope? What percent?
Are there any structures, crops or timber on the site?
Are floodplains present on the site?
** If YES to existing floodplain, on average, what is the difference in feet between natural grade and base flood elevation?
Are floodways present on the site?
** If YES to existing floodways, has a no-rise certification been completed and approved?
Are wetlands present on the site?
Current or former landfill on site?
Easements that impact development?
Transportation/Logistics | Distance (miles) | Name and Description
Nearest interstate
Nearest four-lane highway
Nearest two-lane highway
Nearest river port
Nearest intermodal facility
Nearest commercial airport
Nearest general aviation airport
Nearest rail line (if applicable, provide a description of rail line (main line, spur) and the class and name of the rail provider (Class I, Class III Shortline) )
Neighboring Uses | Distance (miles) | Name and Description
Nearest residential area
Nearest school
Nearest hospital
Nearest fire station
Nearest park
Utilities: Electricity | Response | Additional Details
Name of Electric Provider
Distance to nearest distribution line (feet)
Name or address or Lat/Long of nearest substation (miles)
Distance to nearest substation (feet)
Please provide a description of any additional considerations involved with these necessary to facilitate electric improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.)
Utilities: Natural Gas | Response | Additional Details
Name of Natural Gas Provider
Distance of the nearest natural gas line to the edge of the site (feet)
Line Size (in)
Please provide a description of any additional considerations involved with these necessary to facilitate natural gas improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.)
Utilities: Telecommunications | Response | Additional Details
Name of Telecom Provider
Distance to site (feet)
Estimated Timeline required to establish service (weeks)
Utilities: Wastewater | Response | Additional Details
Name of Wastewater Provider System
Distance of nearest wastewater line to edge of site (feet)
Line Size (inches)
Line Type (Gravity/Force Main)
Current Pressure (psi) if, applicable
What is the current excess capacity of the wastewater line in gallons per day?
Name or address or Lat/Long of Wastewater Treatment Plant
Distance from Site (miles)
What is the current excess capacity of the wastewater treatment plant in gallons per day?
Please provide a description of any additional considerations involved with these necessary to facilitate waste water improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.)
Utilities: Water | Response | Additional Details
Name of Water Provider System
Public Water System ID Number
Distance from nearest water line to the edge of the site (feet)
Line Size (inches)
Current Pressure (psi)
What is the current excess capacity of the potable water line in gallons per day?
What is the current excess capacity of the potable water system in gallons per day?
Please provide a description of any additional considerations involved with these necessary to facilitate industrial and/or potable water improvements to provide commercial level service (e.g., right-of-way, rail or stream crossings, permitting etc.)
ARCHIVED VERSION
DO NOT USE 10/8/2025

## Budget
100 North Street, 7th Floor ¦ Baton Rouge, LA 70802-5264 800.450.8115 ¦ OpportunityLouisiana.com
All relevant funding and dollar amounts should be submitted in column C
List of Total Project Costs | Include All Funding Sources | Amount | Instructions/Details
Total Acquisition | 0 |  | *Calculated field
Easements: |  | 0
Right of Way: |  | 0 | Engineer's Cost Estimate can be found at www.portcolumbia.com document/fast site/ rail project budget with project layout shown in Rail Design Plans
Total Site Improvements Construction | 1867000 |  | *Calculated field
Demolition/Removal: |  | 0
Drainage Improvements: |  | 175000
Easements: |  | 0
Dirt Work: |  | 180000
Grading: |  | 1512000 | 6,300 l.f. area impacted by planned rail activity
Site Mitigation: |  | 0
Site Rehabilitation: |  | 0
Other: |  | 0
Other: |  | 0
Other: |  | 0
Total Public Infrastructure | 2131000 |  | *Calculated field
Water Extension:
Sewer Extension: |  | 0
Road Extension: |  | 520000 | 2000 lf of access roads
Water Infrastructure Improvements: |  | 0
Sewer Infrastructure Improvements: |  | 0
Road Improvements: |  | 0
Other: |  | 1252500 | 4,175 linear feet of track
Other: |  | 95500 | gates, fencing, lighting
Other: |  | 263000 | Turn outs, Earthen Berms, Trackmobile Access/Grade Crossing, Track Items
Total Other/Miscellaneous | 3002000
Other: | Engineering, permit, etc. | 370000
Other: | Union Pacific Switch Eng & Const. | 1432000
Other: | equipment | 600000 | Train Tug, Fork lift
Other: | contingency | 600000
Other: |  | 0
Other: |  | 0
Other: |  | 0
Total Project Costs | 7000000 |  | *Calculated field
State Award Request | Amount |  | Instructions/Details
Requested Amount | 1500000 |  | Enter the amount of state award you are requesting.
Funding Match | Include All Funding Sources | Amount | Instructions/Details
Total Match Sources | 5500000 |  | Fund requests may not exceed 50% of the total project budget. Applicants are responsible for securing the remaining project funding through eligible matching sources. *Calculated field
Match Source 1: |  | 4500000 | LaDOTD for Railspur
Match Source 2: |  | 1000000 | DRA for Railspur
Match Source 3: |  | 0
Match Source 4: |  | 0
Match Source 5: |  | 0
Match Source 6: |  | 0
Match Source 7: |  | 0
Return on Investment (ROI) | Amount |  | Instructions/Details
Estimated State ROI | 7127900 |  | Submit supporting documentation of cumulative project benefit to the state.
Estimated ROI Ratio | 3.7519 |  | *Calculated field
Estimated Site Completion Year | 2027 |  | *Year Format YYYY
Estimated ROI Realization Year | 2029.1044 |  | *Calculated field. Submit supporting documentation with application.

## Timeline
100 North Street, 7th Floor ¦ Baton Rouge, LA 70802-5264 800.450.8115 ¦ OpportunityLouisiana.com
Complete project timeline to assess site readiness, alignment with goals, and potential economic impact.
Milestone | Responsible Party | Funding Source | Investment Amount | Duration (months) | Estimated Start Date | Estimated Completion Date | Additional Details
Pre-Construction Services | columbia Port Commission | Columbia Port Commission | 50000 | 3 | 2025-01-01 | 2026-04-01 | Preliminary work has been coompleted, bid package needs to be completed
Planning & Site Analysis | Columbia Port Commission, Project Engineer BHA, | Columbia Port Commission & DRA | 100000 | 3 | 2025-01-01 | 2026-04-01 | Preliminary work has been coompleted, bid package needs to be completed
Design & Engineering | Columbia Port Commission, Project Engineer BHA, Hatch | Columbia Port Commission & DRA | 400000 | 3 | 2025-01-01 | 2026-04-01 | Engineering design has been completed waiting on final approval from Union Pacfic
Permitting & Regulatory Approvals | Columbia Port Commission, Project Engineer BHA, Hatch | Columbia Port Commission & DRA | 400000 | 5 | 2025-01-01 | 2026-06-01 | Outstanding permit is associated with Union Pacific final approval of design and operational plan, We are in the final review of the revised rail design plan and anticipate approval first qtr of 2026
Construction & Infrastructure Delivery | Columbia Port Commission, Project Engineer BHA, Selected Contractor | LaDOTD Port Priority Program, DRA & Fast Sites | 5500000 | 13 | 2026-07-01 | 2027-08-01 | Once the bids have been awarded and the contracts have been finalized, they will be submitted to DOTD Port Priority for approval. Once approved, preconstruction meetings will be held and work will being
Commissioning & Inspection | Columbia Port Commissio, Project Engineer BHA | LaDOTD Port Priority Program & DRA | 500000 | 15 | 2026-07-01 | 2027-10-01 | Project Engineer BHA will have their inspectors onsite to ensure that the work meets design specifications. We anticipate the work beginning in June 26 and completed by Oct 27.
Operations, Maintenance & Closeout | Columbia Port Commission | Columbia Port Commission & Tenants | 50000 | 4 | 2027-06-01 | 2027-10-01 | The Port and its tenants will be responsible for operations and maintenance of the railspur area. Port, BHA and LaDOTD PPP will conduct final inspection.
Note on A4: FastSites Team: Objective: Identifies major phases of the site lifecycle.
Note on B4: FastSites Team: Objective: Clarify who is accountable for each phase. Instructions for Applicant: List the organization, agency, or contractor overseeing the milestone. Include role or title if known (e.g., “Project Engineer – ABC Consulting”).
Note on C4: FastSites Team: Objective: Show how each phase is financed. Instructions for Applicant: Specify the source(s) of funding (e.g., state grant, federal funds, private investment). If multiple sources apply, list each with approximate share.
Note on D4: FastSites Team: Objective: Quantify financial commitment. Instructions for Applicant: Provide the estimated dollar amount allocated to each milestone. Use whole numbers and round to the nearest thousand if needed.
Note on E4: FastSites Team: Objective: Indicate time required for each phase. Instructions for Applicant: Estimate the number of months needed to complete the milestone. Use realistic timeframes based on scope and complexity. Some phases may overlap.
Note on F4: FastSites Team: Objective: Establish project sequencing. Instructions for Applicant: Enter the anticipated start date for each milestone. Use MM/DD/YYYY format. Ensure dates align logically across milestones.
Note on G4: FastSites Team: Objective: Establish project sequencing. Instructions for Applicant: Enter the anticipated completion date for each milestone. Use MM/DD/YYYY format. Ensure dates align logically across milestones.
Note on H4: FastSites Team: Objective: Provide context or clarifications. Instructions for Applicant: Use this space to note dependencies, permitting status, contingencies, or other relevant information that may affect timing or execution.

## Due Diligence
100 North Street, 7th Floor ¦ Baton Rouge, LA 70802-5264 800.450.8115 ¦ OpportunityLouisiana.com
Ensure each email does not exceed 30MB to support successful delivery. Use your assigned FS Application ID to submit additional application documents.
Site Study Checklist | Submitted with Application | Completion Date | Additional Details or Attachment Description
Phase I Environmental Analysis | YES |  | The Port's website www.portcolumbia.com under documents has all the attachments associated with the Fast Site Application, LED Site Certification, Along with updates for Truck parking facility & Dock www.louisianasiteselection.com
Phase II Environmental Analysis, if applicable
Geotechnical survey/Soil Borings | YES |  | www.portcolumbia.com document LED Site Certification or www.louisianasiteselection.com
Endangered Species survey/US Fish and Wildlife Clearance | YES |  | www.portcolumbia.com document LED Site Certification or www.louisianasiteselection.com
Archeological survey/ State Historic Preservation Clearance | YES |  | www.portcolumbia.com document LED Site Certification or www.louisianasiteselection.com
Wetlands delineation/ USACE Jurisdictional Determination | YES |  | www.portcolumbia.com document LED Site Certification or www.louisianasiteselection.com
Boundary Survey | YES |  | www.portcolumbia.com document LED Site Certification or www.louisianasiteselection.com
Any master plans or feasibility studies? |  | 2026-10-25 | M-167 Freight Strategic Plan, DRA Strategic Planning Grant underway
Any other due diligence studies? | YES |  | www.portcolumbia.com documents - multiple NEPA studies associated with Dock, Truck Parking Facility, Solar Manufacturing Facility, LGF plant site, as well as LED's Certification Site document.

## Legends (hidden)
Application Checklist | Application Overview | Site | Budget | Timeline | Due Diligence
https://led.maps.arcgis.com/apps/webappviewer/index.html?id=89d1f2edcb734fa1902004affa2f70ba
YES
NO
N/A