## Annex B - Introduction
Annex B: LSIP Action Plan (2026–2029) – Introduction
This annex sets out the action plan that supports delivery of the Sussex and Brighton Local Skills Improvement Plan (LSIP) for the period 2026 to 2029. It provides further detail on the priorities and actions identified within the main LSIP report, outlining how these will be taken forward in practice.
As this is a live action plan, all elements will be reviewed and refined on a regular basis over the three-year period, ensuring they remain relevant, achievable and aligned to emerging evidence, delivery progress and changes in the labour market.
The action plan has been developed as a collaborative framework, bringing together employers, the Sussex Chamber of Commerce as the designated Employer Representative Body (ERB), further and higher education providers, statutory organisations, and wider partners. It is intended to support a coordinated, partnership-led approach to addressing the priority skills needs identified across Sussex and Brighton.
The action plan sets out indicative activities, delivery partners, and measures of success. Progress against these actions will be monitored on a regular basis by the ERB, working in collaboration with partners and aligned to wider governance arrangements. This will include tracking key performance indicators and outcomes to assess delivery and impact.
At the time of writing the action plan has focussed on activity in year 1 with indicative actions in subsequent years which will be confirmed/updated as necessary. Partners have agreed to lead on appropriate activities throughout the plan. Where activities currently reference provider groups or sectors (for example Further Education and Higher Education Sussex Strategic Alliance (FHESSA)), specific lead organisations for each activity will be agreed and assigned as the LSIP moves into delivery and implementation through ongoing partnership discussions and governance arrangements. Engagement with providers and delivery partners to support this process has already commenced. Year 1 is confirmed but as the plan evolves, devolution progresses, and funding streams change, we will review the lead organisation and supporting partners in line with the annual LSIP review process.
An annual LSIP progress report will be produced to review progress against the action plan, identify areas of impact, and highlight where further action or adjustment may be required. This reflects the iterative nature of LSIP delivery, ensuring that activity remains responsive to emerging evidence, changing labour market needs, and evolving local and national priorities.
KPI Methodology
The measures and key performance indicators (KPIs) set out in this action plan have been designed to support both effective delivery and proportionate monitoring of progress over the lifetime of the LSIP.
A balanced approach has been taken to ensure that KPIs are:
Measurable and evidence-based, drawing on available data sources such as the Individualised Learner Record (ILR), Higher Education Statistics Agency (HESA) data, LSIP employer and provider surveys, and partner reporting;
Realistic and deliverable, recognising the shared responsibility across partners and the limitations of data availability at local level;
Aligned to outcomes, linking activity-level delivery (short-term measures) to longer-term system change (medium-term measures).
Short-term measures focus on the tangible outputs and deliverables arising from LSIP activity. This includes the development of frameworks, mapping outputs, evidence reports, pathway models and partner-agreed approaches. These measures provide clear, early indicators of progress and are designed to be directly evidenced through documented outputs and shared products.
Medium-term measures focus on outcomes and impact, including changes in participation, progression, employer confidence and alignment between skills provision and labour market need. These are supported by both:
Headline KPIs, which reflect system-level change (e.g. progression into higher-level technical education, employer confidence), and
Supporting measures, which provide evidence of how activity is contributing to those outcomes (e.g. curriculum updates, use of LSIP evidence in planning).
Where specific targets are not yet defined, baselines will be established during 2026/27 using available data sources, with progress tracked over time through annual LSIP reporting.
This approach ensures that the action plan remains both practical for delivery partners and robust for monitoring and accountability, while allowing flexibility to respond to emerging evidence and changing labour market conditions.

## Priority 1
No. | Action | Activity | Process | Lead Organisation /Supporting Partner(s) | Timescales | Short term measure/KPI | RAG rating | Medium term measure/KPI | RAG rating | Funding/Resource status | Funding/Resource source & end date of funding
PRIORITY 1: Secure and grow technical capability across the Sussex and Brighton workforce and future pipeline to underpin innovation, productivity, business leadership, quality and environmental sustainability
Sectors of particular focus: advanced manufacturing and engineering; construction; land-based economy; digital technologies; creative industries
1 | Identify and map the technical capability and leadership requirements across key sectors | Establish a clear picture of the technical and leadership capability required across key sectors over the next three years, drawing on existing frameworks, labour market intelligence and sector analysis, including emerging specialist capability linked to clean energy, low-carbon technologies and environmental innovation (links to Priority 3 Action 1) | • Collate and analyse existing LSIP evidence including sector deep dives, employer surveys and labour market intelligence • Review national frameworks, occupational standards and Industrial Strategy priorities to benchmark capability needs • Undertake targeted employer engagement to validate current and future technical and leadership skills demand • Integrate intelligence from FE, HE and SCTP & other ITPs on current provision and emerging skills • Identify emerging technical capability linked to clean energy, low-carbon technologies and environmental innovation • Develop a structured capability framework covering Levels 1–8, including progression and leadership pathways • Validate capability framework with partners • Ensure alignment with cross-cutting themes including digital, sustainability and innovation | Lead: LSIP team Partners: Further Education (FE), Higher Education (HE), Sussex Council of Training Providers (SCTP) & other independent training providers (ITPs), Local Authorities, employer/sector bodies, employers | Year 1: Jul-Dec | Technical capability framework developed and validated through employer and partner engagement |  | 1. Increase the number of learners progressing into relevant higher-level education and training (Levels 4–6+) in LSIP key sectors by an agreed percentage by 2030. How it will be measured: Participation and completion data from: • Individualised Learner Record (ILR) data for FE and apprenticeships • Higher Education Statistics Agency (HESA) data for higher education provision Baseline: 2025/26 participation in Levels 4–6+ programmes aligned to LSIP priority sectors. 2. Increase the number of education and training programmes aligned to identified technical capability needs in LSIP priority sectors by 2030. How it will be measured: Progress will be monitored through annual reporting by the further education, higher education and independent training provider networks, reviewing how education and training provision across priority sectors evolves in response to identified capability needs. Baseline: Baseline to be established in 2026/27 following completion of the capability mapping undertaken through Priority 1 Action 1. |  | Funded | LSIP core budget - Year 1
2 | Align education and training pathways with technical capability needs | Map LSIP key sector provision pathways (links to Priority 2 & 3 Action 1 and Activity 1.6 Get Sussex Working Plan (GSWP)) | • Map all skills provision across the LSIP key sectors | Lead: Further Education and Higher Education Sussex Strategic Alliance (FHESSA) Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | Year 1: Jul-Dec | Provision mapping across key sectors completed |  |  |  | Resourced | FHESSA contribution - in-house resource
|  | Map the capability framework across education and training pathways and programmes (Levels 1–8), including apprenticeships, supported employment, higher technical routes and modular programmes such as Skills Bootcamps | • Map capability framework across the provision pathways • Use mapping output to inform next activity | Lead: FHESSA Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | STAGED PROCESS ACROSS TWO YEARS Year 1: Jan-Jun (selected sectors) Year 2 (remaining sectors) | Mapping activity completed across identified key sectors Outputs shared with partners to inform next stage activity |  |  |  | Resourced Partially funded | FHESSA contribution - in-house resource LSIP core budget - in-house resource for co-ordination (Year 1 only confirmed)
|  | Identify where curriculum content, assessment approaches or progression routes may need to be adapted or strengthened to reflect current and future workplace practice | • Identify gaps, duplication and misalignment between provision and employer demand across sectors and levels (consider geography and accessibility) • Assess impact of qualification requirements, funding rules and commercial viability on provision design • Gather employer evidence to demonstrate demand and support business case for new provision • Share insight widely with FE, HE and SCTP & other ITPs to inform curriculum planning and development • Identify opportunities for new provision including modular, flexible and specialist programmes • Align findings with local growth priorities and infrastructure developments • Support providers to respond to identified gaps through collaboration and funding opportunities | Lead: FHESSA Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | Year 2 | Gaps, duplication and misalignment between provision and employer demand identified Findings shared with providers and stakeholders |  |  |  | Resourced Partially funded | FHESSA contribution - in-house resource LSIP core budget - in-house resource for co-ordination (subject to Year 2 funding)
|  | Strengthen the understanding of technical capabilities within careers guidance, work experience and progression routes across key sectors (links to Activity 2.7 GSWP) | • Translate capability framework and pathways into accessible formats for careers guidance and CEIAG delivery • Share capability framework with partners so that it can be embedded into work experience, employer engagement activities, careers guidance and employment support services • Provide CPD for education staff | Lead: Sussex Learning Network (SLN) Partners: Careers Hubs, schools, FE, HE, SCTP and other ITPs, Local Authorities, DWP, employment support providers, careers leads, community organisations | Years 2 & 3 | Capability framework translated into accessible formats for CEIAG and careers delivery Engagement activity delivered with careers and employment support partners |  |  |  | Resourced Partially funded | SLN contribution - in-house resource Careers Hubs - current annual contract (CEC) to Aug 2026. Moves to 3-5 year contract via new provider from 2027
|  | Strengthen progression routes from Level 3 into higher technical and specialist roles (Levels 4–5 and above) (Links to Activity 6.1, 6.2 & 6.3 GSWP) | • Map and clarify progression routes from Level 3 to higher levels • Expand Level 4–5 provision aligned to employer demand • Integrate modular and flexible learning options • Align pathways with workforce demand and sector needs • Co-design curriculum, programmes and initiatives with employers • Promote progression opportunities to learners and employers | Lead: FE Sussex Partners: SCTP & other ITPs, HE, LAs, Awarding Bodies, sector/employer bodies, employers, SLN, LSIP Team | Year 2 & 3 | Progression routes from Level 3 to Levels 4–5+ defined and agreed with provider partners Progression opportunities promoted to learners and employers |  |  |  | Resourced Partially funded Funding for provision: - subject to availability | FE Sussex contribution - in-house resource LSIP core budget - in-house resource (subject to Year 2 & 3 funding) Core provider funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF) Lifelong Learning Entitlement (from Sept 26)
|  | Integrate digital, AI and sustainability capability within sector-specific training | • Embed cross-cutting skills into curriculum • Align with LSIP digital and sustainability priorities • Integrate modular, stackable and flexible learning that enables progression into technical, supervisory and management roles • Update curriculum content to reflect emerging technologies • Co-design curriculum, programmes and initiatives with employers • Promote opportunities to learners and employers | Lead: FE Sussex Partners: SCTP & other ITPs, HE, Local Authorities, Awarding Bodies, sector/employer bodies, employers, SLN, LSIP Team | Year 2 & 3 | Curriculum review activity undertaken to embed cross-cutting skills Programme updates identified and promoted to learners and employers. |  |  |  | Resourced Partially funded Funding for provision: - subject to availability | FE Sussex contribution - in-house resource LSIP core budget - in-house resource (subject to Year 2 funding) Core provider provision funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF) Lifelong Learning Entitlement (from Sept 26)
|  | Strengthen collaboration between employers and providers so training reflects real operational practice (links to Activity 3.1 GSWP) | • Deliver LSIP-led engagement events including annual Sussex Skills conference •Engage with Chamber-led sector forums • Share best practice and case studies | Lead: LSIP Team Partners: Employers, other employer bodies; FE, HE, SCTP & other ITPs, Local Authorities, Sussex Chamber of Commerce | Year 1–3 | Employer-provider engagement activity delivered Best practice and case studies shared across partners |  |  |  | Partially funded | LSIP core budget - events and marketing (Year 1)
3 | Strengthen entry, progression and retention in technical and specialist careers | Rebuild entry-level pathways (Levels 1–2) that help young people, career changers and returners, and those with special educational needs and disabilities to progress into technical training, apprenticeships and skilled work (links to Activity 2.2 & 6.5 GSWP) | • Map existing entry-level provision pathways into technical and specialist occupations • Identify the gaps in provision according to supply-side data • Develop Level 1–2 provision aligned to sector needs • Incorporate structured work experience, supported internships, placements and mentoring • Incorporate SEND and inclusive pathways • Align with progression routes into Level 3+ • Align with DWP and employment support provision • Engage employers to support progression • Promote opportunities to learners and employers | Lead: FE Sussex Partners: SCTP & other ITPs, Local Authorities, DWP, employment support providers, employers; SLN | Year 2 | Map of entry-level provision pathways completed Gaps in Level 1–2 provision identified Entry-level provision aligned to progression routes and sector needs |  |  |  | Resourced Partially funded Funding for provision: - subject to availability | FE Sussex contribution - in-house resource LSIP core budget - in-house resource (subject to Year 2 funding) Core provider provision funding (Levels 1 & 2)
|  | Strengthen progression opportunities for the existing workforce, enabling technicians and specialists to develop into advanced technical, supervisory and management roles (Links to Activities 3.1, 3.5 & 3.8 GSWP) | • Promote upskilling and CPD opportunities through existing employer engagement activities • Encourage employer investment through existing employer engagement activities | Lead: LSIP team & Local Authorities Partners: Growth Hub, SCTP, FE, HE, employer bodies | Year 1, 2 & 3 | Upskilling and CPD opportunities promotion materials shared with partners and promoted through employer engagement activity |  |  |  | Partially funded | Transform (East Sussex until March 2027 ) Growth Hub (DBT Year 1) LSIP core budget - in-house resource (Year 1 confirmed)
|  | Support employers, particularly SMEs, to offer inclusive and sustainable entry-level and progression opportunities (Links to Priority 4 Action 3 and Activity 3.8 GSWP) | • Explore a service that: - provides brokerage and support - promotes incentives and funding - connect SMEs with providers | Lead: Local Authorities Partners: LSIP team | Year 1 | Model such as Transform or similar funded pan Sussex beyond August 2026 |  |  |  | Partially funded | Transform' funded in East Sussex until March 2027 . Need to source funding beyond that for a Sussex-wide approach.

## Priority 2
No. | Action | Activity | Process | Lead Organisation /Supporting Partner(s) | Timescales | Short term measure/KPI | RAG rating | Medium term measure/KPI | RAG Rating | Funding/Resource status | Funding/Resource source & end date of funding
PRIORITY 2: Make digital and technological capability a baseline expectation across the Sussex and Brighton workforce and future pipeline, supporting safe and responsible use of emerging technologies.
Sectors of particular focus: All sectors
1 | Identify and agree the digital and technological capability needed across key sectors. | Draw on existing local and national frameworks, labour market intelligence and sector analysis to establish a clear picture of the digital and technological baseline capability needed across key sectors and education workforce | • Analyse LSIP employer evidence, workshops and sector insights to identify digital capability needs • Review national frameworks including AI, cyber and data standards • Integrate FE, HE and ITP intelligence on current provision and emerging needs • Undertake targeted employer engagement to validate current and future technical and leadership skills demand • Identify sector-specific digital capability requirements • Identify the core knowledge and skills needed to work safely and responsibly with digital, data and AI-enabled systems • Develop a structured capability framework covering Levels 1–8, including progression and leadership pathways • Validate capability framework with partners | Lead: LSIP team Partners: FE, HE, SCTP & other ITPs, Local Authorities, employer/sector bodies, employers | Year 1: Jul-Dec | Digital baseline capability framework developed and validated with employers and partners |  | 1. By 2029/30, agreed baseline expectations for digital and technological capability are embedded across education and training pathways in LSIP key sectors. How it will be measured: Progress will be monitored through annual reporting by the further education, higher education and independent training provider networks, reviewing how education and training provision across priority sectors evolves in response to identified capability needs. Baseline Baseline to be established in 2026/27 following agreement of the Sussex and Brighton digital capability baseline. 2. Reduce the proportion of employers reporting low confidence in leading the safe and responsible use of digital and emerging technologies by an agreed percentage by 2030. How it will be measured: Measured through the LSIP employer survey, establishing a baseline in 2026/27 and tracking changes in employer confidence over time. Baseline: Baseline established through the 2026/27 LSIP employer survey. |  | Funded | LSIP core budget (Year 1)
|  | Identify where digital and technological change is having the greatest impact on jobs, sectors and career pathways (links to Priority 4 Action 1) | • Analyse labour market data and job trends to identify impact of digital change • Review existing and gather new employer insight on digital transformation impacts • Identify priority occupations affected by AI and automation • Incorporate provider insight on emerging demand • Feed findings into curriculum and pathway design | Lead: LSIP team Partners: FE, HE, SCTP & other ITPs, Local Authorities, employer/sector bodies, employers | Year 1: Jul-Dec | Priority occupations and key sectors impacted by digital and technological change identified, documented and shared with partners. |  |  |  | Funded | LSIP core budget (Year 1)
2 | Align education and training pathways with digital and technological capability needs. | Map LSIP key sector provision pathways (links to Priority 1 & 3 Action 1 and Activity 1.6 GSWP) | • Map all skills provision across the LSIP key sectors | Lead: FHESSA Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | Year 1: Jul-Dec | Provision mapping across identified key sectors completed. |  |  |  | Resourced | FHESSA contribution - in-house resource
|  | Map the digital and technological capabilities identified in Action 1 across education and training pathways and programmes (Levels 1-8), including apprenticeships, adult learning and modular provision such as Skills Bootcamps | • Map capability framework across the provision pathways • Use mapping output to inform next activity | Lead: FHESSA Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | STAGED PROCESS ACROSS TWO YEARS Year 1: Jan-Jun (selected sectors) Year 2 (remaining sectors) | Mapping activity completed across identified key sectors Outputs shared with partners to inform next stage activity |  |  |  | Resourced Partially funded | FHESSA contribution - in-house resource LSIP core budget - in-house resource for co-ordination (Year 1 only confirmed)
|  | Identify where curriculum content, assessment approaches or progression routes may need to be adapted or strengthened to reflect current and future workplace practice | • Identify gaps, duplication and misalignment between provision and employer demand across sectors and levels (consider geography and accessibility) • Assess impact of qualification requirements, funding rules and commercial viability on provision design • Gather employer evidence to demonstrate demand and support business case for new provision • Share insight widely with FE, HE and SCTP & other ITPs to inform curriculum planning and development • Identify opportunities for new provision including modular, flexible and specialist programmes • Align findings with local growth priorities and infrastructure developments • Support providers to respond to identified gaps through collaboration and funding opportunities | Lead: FHESSA Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | Year 2 | Gaps, duplication and misalignment between provision and employer demand identified Findings shared with providers and stakeholders |  |  |  | Resourced Partially funded | FHESSA contribution - in-house resource LSIP core budget - in-house resource for co-ordination (subject to Year 2 funding)
|  | Strengthen the awareness of digital and technological capabilities within careers guidance, work experience and progression routes across sectors (links to Activity 2.7 GSWP) | • Translate capability framework and pathways into accessible formats for careers guidance and CEIAG delivery • Share capability framework with partners so that it can be embedded into work experience, employer engagement activities, careers guidance and employment support services • Provide CPD for education staff | Lead: SLN Partners: Careers Hubs, schools, FE, HE, SCTP and other ITPs, Local Authorities, DWP, employment support providers, careers leads, community organisations | Years 2 & 3 | Capability framework translated into accessible formats for CEIAG and careers delivery Engagement activity delivered with careers and employment support partners |  |  |  | Resourced Partially funded | SLN contribution - in-house resource Careers Hubs - current annual contract (CEC) to Aug 2026. Moves to 3-5 year contract via new provider from 2027
|  | Strengthen collaboration between employers and providers so training reflects real operational practice (links to Activity 3.1 GSWP) | • Deliver LSIP-led engagement events including annual Sussex Skills conference • Engage with Chamber-led sector forums • Share best practice and case studies | Lead: LSIP Team Partners: Employers, other employer bodies; FE, HE, SCTP & other ITPs, Local Authorities, Sussex Chamber of Commerce | Year 1–3 | Employer-provider engagement activity delivered Best practice and case studies shared across partners |  |  |  | Partially funded | LSIP core budget - events and marketing (Year 1 funding confirmed, years 2 & 3 subject to funding)
|  | Support educators and training providers to integrate responsible use of digital and emerging technologies into teaching and learning practices | • Provide guidance and frameworks for providers • Share best practice across providers • Support staff CPD in digital delivery | Lead: SLN Partners: SCTP & other ITPs, HE, FE | Years 2 & 3 | Guidance and frameworks for responsible digital delivery practices developed and shared with providers Staff CPD activities undertaken and best practice shared across providers |  |  |  | Resourced | SLN contribution - in-house resource
|  | Embed digital baseline capabilities within sector provision pathways | • Embed digital baseline capabilities within sector provision pathways • Integrate modular, stackable and flexible learning that enables progression • Update curriculum content to reflect emerging technologies • Co-design curriculum, programmes and initiatives with employers • Promote opportunities to learners and employers | Lead: FE Sussex Partners: SCTP & other ITPs, HE, Local Authorities, Awarding Bodies, sector/employer bodies, employers, SLN, LSIP Team | Year 2 & 3 | Baseline digital capabilities embedded across sector pathways Programme updates identified and promoted to learners and employers. |  |  |  | Resourced Partially funded Funding for provision: - subject to availability | FE Sussex contribution - in-house resource LSIP core budget - in-house resource (subject to Year 2 & 3 funding) Core provider funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF) Lifelong Learning Entitlement (from Sept 26)
|  | Strengthen foundational digital capability for learners and adults without Level 3 qualifications to support progression into work and further training | • Map essential digital skills provision across Sussex and Brighton in Level 2 and below delivery • Identify gaps in Level 2 and below delivery • Explore opportunities for new foundational digital provision | Lead: FE Sussex Partners: SCTP & other ITPs, Local Authorities, employment support providers, DWP | Year 2 & 3 | Gaps in foundational digital provision identified and priority areas for development defined and shared with providers. |  |  |  | Resourced Partially funded Funding for provision: - subject to availability | FE Sussex contribution - in-house resource LSIP core budget - in-house resource (subject to Year 2 funding) Core provider provision funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF) Lifelong Learning Entitlement (from Sept 26)
3 | Strengthen leadership capability and employer support for responsible technology adoption. | Strengthen leadership capability in areas such as digital governance, cyber security, risk management and responsible use of emerging technologies | • Identify the leadership and management capabilities needed to respond to digital and technological change across key sectors, including digital governance, cyber security, risk management and responsible use of emerging technologies • Review how digital and technological change-related leadership skills are currently reflected within FE, HE and ITP leadership and management provision • Engage employers to understand where leadership capability gaps are constraining progress on digital and technological change • Explore how digital and technological change-related leadership content can be incorporated into existing leadership, management and professional development programmes rather than relying only on stand-alone offers • Share insight and practical examples with providers to support programme adaptation and development | Lead: FHESSA Partners: SCTP and other ITPs, SLN, FE Sussex | Year 2 & 3 | Digital leadership capability requirements defined and shared with providers. |  |  |  | Resourced Funding for provision: - subject to availability | FHESSA contribution - in-house resource Core provider provision funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF) Lifelong Learning Entitlement (from Sept 26)
|  | Build on existing business support infrastructure, employer networks and sector initiatives to strengthen digital capability across the SME workforce (Links to Activities 3.1, 3.5 & 3.8 GSWP) | • Align with existing business support programmes e.g. Growth Hub • Promote training opportunities • Explore opportunities to: - provide brokerage support - reduce barriers to SME engagement - support workforce planning • Share progression pathways | Lead: LSIP team & Local Authorities Partners: Growth Hub, SCTP and other ITPs, FE, HE, employer bodies | Year 2 & 3 | Coordinated promotion of digital training opportunities across Sussex through partner networks Model such as Transform or similar funded pan Sussex beyond August 2026 |  |  |  | Partially funded | Transform' funded in East Sussex until March 2027 . Need to source funding beyond that for a Sussex-wide approach. Growth Hub (DBT) LSIP core budget - in-house resource for co-ordination (Year 1)

## Priority 3
No. | Action | Activity | Process | Lead Organisation /Supporting Partner(s) | Timescales | Short term measure/KPI | RAG Rating | Medium term measure/KPI | RAG Rating | Funding/Resource status | Funding/Resource source & end date of funding
PRIORITY 3: Embed skills for environmental sustainability and climate resilience across the Sussex and Brighton workforce and future pipeline, supported by leadership capability to enable consistent and effective implementation.
Sectors of particular focus: All sectors
1 | Identify sustainability and climate capability needs across key sectors | Draw on existing national frameworks, local climate strategies and sector intelligence to establish a clear picture of the sustainability and climate resilience capabilities required across key sectors | • Analyse LSIP green skills evidence including sector deep dives, 'Future of Green Skills Sussex' report, employer engagement and LMI • Review national policy and frameworks including Industrial Strategy and Clean Energy plans and integrate local authority climate strategies and priorities • Gather employer insight on 'embedded' sustainability practices and workforce needs • Identify where sustainability requirements are already influencing job roles, sector practices and supply chains and align with regulatory requirements and industry standards • Incorporate FE, HE and ITP intelligence on provision and emerging demand • Develop a structured capability framework covering Levels 1–8, including progression and leadership pathways that embeds capability within existing occupations/job roles • Validate capability framework with partners | Lead: LSIP team Partners: FE, HE, SCTP & other ITPs, Local Authorities, employer/sector bodies, employers; Clean Growth UK | Year 1: Jul-Dec | Sustainability capability framework developed and validated with employers and partners |  | 1. By 2029/30, sustainability and climate resilience capability is embedded across education and training pathways in LSIP key sectors. How it will be measured: Progress will be monitored through annual reporting by the further education, higher education and independent training provider networks, reviewing how education and training provision across priority sectors evolves in response to identified capability needs. Baseline: Baseline to be established in 2026/27 following completion of the sustainability capability mapping undertaken through Priority 4 Action 1. 2. Reduce the proportion of employers reporting low confidence in leading sustainability and climate-related workforce change by an agreed percentage by 2030. How it will be measured: Measured through the LSIP employer survey, establishing a baseline in 2026/27 and tracking changes in employer confidence over time. Baseline: Baseline to be established through the 2026/27 LSIP employer survey. |  | Funded | LSIP core budget (Year 1)
|  | Review evidence periodically over the lifetime of the LSIP to assess whether demand for specialist green occupations is emerging or increasing in certain sectors. Use these checkpoints to inform whether additional specialist training provision may be required | • Establish regular review cycle aligned to LSIP progress reporting • Monitor labour market and employer trends • Engage providers and employers to validate emerging demand • Feed into annual LSIP progress reports • Use evidence reviews to identify gaps in specialist provision • Assess viability of new provision based on employer demand • Share opportunities with FE, HE and SCTP & other ITPs | Lead: LSIP team Partners: FE, HE, SCTP & other ITPs, Local Authorities, employer/sector bodies, employers; Clean Growth UK | Year 2 & 3 | Review cycle established and aligned to LSIP reporting Findings shared with partners. |  |  |  | Unfunded | LSIP core budget (subject to year 2 & 3 funding
2 | Align education, training and workforce pathways with sustainability capability needs | Map LSIP key sector provision pathways (links to Priority 1 & 2 Action 1 and Activity 1.6 GSWP) | • Map all skills provision across the LSIP key sectors | Lead: FHESSA Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | Year 1: Jul-Dec | Provision mapping across LSIP key sectors completed. |  |  |  | Resourced | FHESSA contribution - in-house resource
|  | Map the sustainability capabilities identified in Action 1 across education and training pathways and programmes (Levels 1-8), including apprenticeships, adult learning and modular provision such as Skills Bootcamps | • Map capability framework across the provision pathways • Use mapping output to inform next activity | Lead: FHESSA Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | STAGED PROCESS ACROSS TWO YEARS Year 1: Jan-Jun (selected sectors) Year 2 (remaining sectors) | Mapping activity completed across identified key sectors Outputs shared with partners to inform next stage activity |  |  |  | Resourced Partially funded | FHESSA contribution - in-house resource LSIP core budget - in-house resource for co-ordination (Year 1 only confirmed)
|  | Identify where curriculum content, assessment approaches or progression routes may need to be adapted or strengthened to reflect current and future workplace practice | • Identify gaps, duplication and misalignment between provision and employer demand across sectors and levels (consider geography and accessibility) • Assess impact of qualification requirements, funding rules and commercial viability on provision design • Gather employer evidence to demonstrate demand and support business case for new provision • Share insight widely with FE, HE and SCTP & other ITPs to inform curriculum planning and development • Identify opportunities for new provision including modular, flexible and specialist programmes • Align findings with local growth priorities and infrastructure developments • Support providers to respond to identified gaps through collaboration and funding opportunities | Lead: FHESSA Partners: SCTP & other ITPs, Local Authorities, supported employment providers, DWP, LSIP Team | Year 2 | Gaps, duplication and misalignment between provision and employer demand identified Findings shared with providers and stakeholders |  |  |  | Resourced Partially funded | FHESSA contribution - in-house resource LSIP core budget - in-house resource for co-ordination (Year 1 only confirmed)
|  | Strengthen the awareness of sustainability capabilities within careers guidance, work experience and progression routes across sectors (links to Activity 2.7 GSWP) | • Translate capability framework and pathways into accessible formats for careers guidance and CEIAG delivery • Share capability framework with partners so that it can be embedded into work experience, employer engagement activities, careers guidance and employment support services • Provide CPD for education staff | Lead: SLN Partners: Careers Hubs, schools, FE, HE, SCTP and other ITPs, Local Authorities, DWP, employment support providers, careers leads, community organisations | Years 2 & 3 | Capability framework translated into accessible formats for CEIAG and careers delivery Engagement activity delivered with careers and employment support partners |  |  |  | Resourced Partially funded | SLN contribution - in-house resource Careers Hubs - current annual contract (CEC) to Aug 2026. Moves to 3-5 year contract via new provider from 2027
|  | Strengthen collaboration between employers and providers so training reflects real operational practice (links to Activity 3.1 GSWP) | • Deliver LSIP-led engagement events including annual Sussex Skills conference •Engage with Chamber-led sector forums • Share best practice and case studies | Lead: LSIP Team Partners: Employers, other employer bodies; FE, HE, SCTP & other ITPs, Local Authorities, Sussex Chamber of Commerce | Year 1–3 | Employer-provider engagement activity delivered Best practice and case studies shared across partners |  |  |  | Partially funded | LSIP core budget - events and marketing (Year 1 confirmed only, Year 2 & 3 subject to funding)
|  | Embed sustainability and climate resilience capabilities within key sector provision pathways | • Embed sustainability baseline capabilities within key sector provision pathways • Integrate modular, stackable and flexible learning that enables progression • Update curriculum content to reflect emerging technologies • Co-design curriculum, programmes and initiatives with employers • Promote opportunities to learners and employers | Lead: FE Sussex Partners: SCTP & other ITPs, HE, Local Authorities, Awarding Bodies, sector/employer bodies, employers, SLN, LSIP Team | Year 2 & 3 | Baseline capabilities embedded across key sector pathways Programme updates identified and promoted to learners and employers. |  |  |  | Resourced Partially funded Funding for provision: - subject to availability | FE Sussex contribution - in-house resource LSIP core budget - in-house resource (subject to Year 2 & 3 funding) Core provider funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF) Lifelong Learning Entitlement (from Sept 26)
3 | Strengthen leadership capability to enable sustainability and climate action | Strengthen leadership capability in areas such as sustainability strategy, regulatory compliance and climate risk management | • Identify the leadership and management capabilities needed to respond to sustainability requirements across priority sectors, including strategy, compliance, reporting and risk management • Review how sustainability and climate-related leadership skills are currently reflected within FE, HE and ITP leadership and management provision • Engage employers to understand where leadership capability gaps are constraining progress on sustainability and workforce change • Explore how sustainability-related leadership content can be incorporated into existing leadership, management and professional development programmes rather than relying only on stand-alone offers • Share insight and practical examples with providers to support programme adaptation and development | Lead: FHESSA Partners: SCTP and other ITPs, SLN, FE Sussex | Year 2 & 3 | Leadership capability requirements identified and shared with providers. |  |  |  | Resourced Funding for provision: - subject to availability | FHESSA contribution - in-house resource Core provider provision funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF) Lifelong Learning Entitlement (from Sept 26)
|  | Build on existing business support programmes, sector initiatives and employer networks to strengthen sustainability leadership (Links to Activities 3.1, 3.5 & 3.8 GSWP) | • Align with existing business support programmes • Promote training opportunities • Explore opportunities to: - provide brokerage support - reduce barriers to SME engagement - support workforce planning • Share progression pathways | Lead: LSIP team & Local Authorities Partners: Growth Hub, SCTP and other ITPs, FE, HE, employer bodies | Year 2 & 3 | Coordinated promotion of sustainabilty training opportunities across Sussex through partner networks Model such as Transform or similar funded pan Sussex beyond August 2026 |  |  |  | Unfunded | Transform' funded in East Sussex until March 2027 . Need to source funding beyond that for a Sussex-wide approach.

## Priority 4
No. | Action | Activity | Process | Lead Organisation /Supporting Partner(s) | Timescales | Short term measure/KPI | RAG Rating | Medium term measure/KPI | RAG Rating | Funding/Resource status | Funding/Resource source & end date of funding
PRIORITY 4: Strengthen access, entry and progression routes into employment to reflect technological change and Sussex and Brighton’s demographic realities, so that pathways remain inclusive, clear and aligned with employer expectations.
Sectors of particular focus: All sectors
1 | Identify where routes into employment need to evolve across key sectors | Map current entry points and progression routes across key sectors (links to Priority 1, 2 & 3 Action 1 and Activity 1.6 GSWP) | • Using the mapped LSIP key sector provision pathways, map the current entry points and progression routes | Lead: LSIP team Partners: FE, HE, SCTP and other ITPs, Local Authorities, employer/sector bodies, employers, employment support providers | Year 1: Jul-Dec | Pathway mapping across LSIP priority sectors completed |  | 1. Increase the proportion of individuals completing education, training or employability programmes who enter employment, progress within employment, or move into further training aligned to LSIP priority sectors within 6–12 months of completion, by an agreed percentage by 2030. How it will be measured: Progress can be monitored using: • provider destination data and Graduate Outcomes Survey data (FE, HE and training providers) • apprenticeship and employment outcomes •data from other employment and skills programmes Baseline: Baseline to be established using 2025/26 destination and progression data across education, training and employability programmes. |  | Funded | LSIP core budget (Year 1)
|  | Identify where technological change is altering job roles, entry routes or early career progression (links to Priority 2 Action 1) | • Analyse labour market data and job trends to identify impact of digital change • Review existing and gather new employer insight on digital transformation impacts • Identify priority occupations affected by AI and automation • Incorporate provider insight on emerging demand • Feed findings into curriculum and pathway design | Lead: LSIP team Partners: FE, HE, SCTP and other ITPs, Local Authorities, employer/sector bodies, employers, employment support providers | Year 1: Jul-Dec | Priority occupations and entry routes impacted by technological change identified, documented and shared with partners. |  |  |  | Funded | LSIP core budget (Year 1)
|  | Analyse workforce trends such as ageing workforces, economic inactivity and declining youth participation that may affect workforce supply and assess where these issues vary across different parts of Sussex and Brighton | • Analyse demographic and labour market data • Identify priority workforce challenges • Analyse sub-regional variation in labour market trends • Identify geographic disparities • Engage partners to validate findings • Integrate into LSIP evidence base | Lead: LSIP team Partners: FE, HE, SCTP and other ITPs, Local Authorities | Year 1/2/3: Dec-Mar (part of the annual update of the evidence base) | Review cycle established and aligned to LSIP reporting Findings validated and shared with partners. |  |  |  | Partially Funded | LSIP core budget - in-house resource / data analysis (Year 2 & 3 subject to funding)
2 | Align education, training and employment pathways with changing workforce needs | Strengthen routes into employment where traditional entry-level roles are reducing, changing or requiring different skills because of technology, business change or labour market pressures (links to Activity 2.2, 2.6 and 6.5 GSWP) | • Use evidence from Action 1 to identify sectors and occupations that are impacted •Review whether existing training offers and progression pathways remain fit for purpose in these sectors and occupations • Explore alternative or additional entry routes such as pre-employment provision, Skills Bootcamps, supported internships, apprenticeships and modular training • Include structured step-by-step entry routes that combine learning, work experience, placements, supported internships, project-based activity or other work-integrated elements where appropriate • Identify constraints including funding and qualification structures • Share intelligence with partners to support investment, planning and development | Lead: FE Sussex/Local Authorities/LSIP Team Partners: SCTP and other ITPs, DWP, employment support providers, employers | STAGED PROCESS ACROSS TWO YEARS Year 1: Jan-Jun (selected sectors) Year 2 (remaining sectors) | Key sectors and occupations impacted by changing workforce needs identified Alternative or additional provision requirements identified Findings shared with partners to inform investment, planning and development |  |  |  | Resourced Funding for provision: - subject to availability | FE Sussex contribution - in-house resource Core provider funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF)
|  | Support progression at different life stages and levels, including for young people, career changers, returners and economically inactive adults (links to Activity 3.2 GSWP) | • Review how current pathways serve different cohorts and identify where there are gaps or barriers for specific groups • Engage providers, DWP, careers services and pre-employment organisations to understand how support and pathway design can better reflect varied starting points and needs • Identify opportunities to strengthen or adapt progression for young people, returners, career changers and adults moving towards, back into work or within existing employment • Explore opportunities to align training offers more closely with engagement and support activity aimed at economically inactive adults and other target groups | Lead: FE Sussex/Local Authorities/LSIP Team Partners: SCTP and other ITPs, DWP, employment support providers, employers | Year 1: Jan-Jun (selected sectors) Year 2 (remaining sectors) | Pathway gaps and barriers for key cohorts identified Collaborative approaches to support progression agreed with partners |  |  |  | Partially funded | Core provider funding - in-house resource LSIP core budget - in-house resource (Year 1 funded only, year 2 & 3 subject to funding) Core provider funding (all levels) Skills Bootcamp programme Adult Skills Fund (ASF) Lifelong Learning Entitlement (from Sept 26)
|  | Improve the clarity of progression routes so learners, employers and advisers understand how individuals move into and through sectors (links to Priority 1 Action 1, Priority 2 & 3 Action 2) | • Ensure all pathway maps and guidance reflect entry-level routes, progression opportunities, modular and flexible learning options, and progression into higher-level training where relevant • Share maps with Careers Hubs, advisers, providers and employer-facing organisations to improve common understanding • Provide CPD for education staff | Lead: SLN Partners: Careers Hubs, schools, FE, HE, SCTP and other ITPs, Local Authorities, DWP, employment support providers, careers leads, community organisations | Year 2 & 3 | Capability framework translated into accessible formats for CEIAG and careers delivery Engagement activity delivered with careers and employment support partners |  |  |  | Resourced Partially funded | SLN contribution - in-house resource Careers Hubs - current annual contract (CEC) to Aug 2026. Moves to 3-5 year contract via new provider from 2027
3 | Enable employers to offer more entry and progression opportunities | Support employers, particularly SMEs, to offer inclusive and sustainable entry-level and progression opportunities (Links to Priority 4 Action 3 and Activity 3.8 GSWP) | • Explore a service that: - provides brokerage and support - promotes incentives and funding - connect SMEs with providers | Lead: Local Authorities Partners: LSIP team | Year 1 | Model such as Transform or similar funded pan Sussex beyond August 2026 |  |  |  | Partially funded | Transform' funded in East Sussex until March 2027 . Need to source funding beyond that for a Sussex-wide approach.
|  | Encourage shared approaches where employers collaborate to support supervision, employment skills, mentoring and workforce development | • Gather examples of collaborative approaches involving multiple employers, tripartite delivery and provider-supported progression models • Engage employers and providers to identify where shared models could be useful in sectors dominated by smaller employers • Explore how collaborative approaches can support mentoring, supervision, employment skills and early retention, particularly where employers cannot deliver these alone • Use sector forums, LSIP events and partner engagement to promote peer learning and practical models | Lead: LSIP team Partners: FE, HE, SCTP and other ITPs, Local Authorities, employer/sector bodies, employers | Year 2 & 3 | Collaborative employer models for entry, progression and workforce development identified and shared via employer engagement and wider partner communications |  |  |  | Unfunded
|  | Expand structured work experience, supported internships, placements and transitional roles that lead to sustained employment | • Work with employers and providers to identify where structured work experience, supported internships, placements and transitional opportunities can be expanded • Use employer engagement activity to connect employers able to offer opportunities with providers able to support recruitment, preparation and progression • Include FE, HE and ITP pathways within planning and signposting for these opportunities where relevant • Explore gaps in provision or candidate pipelines and how they might be addressed through collaboration between providers and employment support services • Promote these opportunities as part of wider progression pathways into sustained employment rather than stand-alone activity | Lead: LSIP team Partners: FE, HE, SCTP and other ITPs, Local Authorities, employer/sector bodies, employers, SLN, supported employment providers | Year 2 & 3 | Opportunities for expanding work experience, placements and transitional roles identified and shared via employer engagement and wider partner communications |  |  |  | Unfunded
|  | Strengthen mentoring and development opportunities within early career roles | • Promote the importance of in-work mentoring and early career support as part of retention and progression, especially for apprentices, new entrants and those returning to work • Gather and share examples of effective mentoring and progression support used by providers and employers • Encourage discussion with employers on how mentoring, supervision and structured development can be strengthened within early roles • Consider how provider support, tripartite working and progression planning can help sustain employment and support advancement • Use LSIP events and communications to reinforce mentoring and development as part of quality entry and progression routes | Lead: LSIP team Partners: FE, HE, SCTP and other ITPs, Local Authorities, employer/sector bodies, employers, SLN | Year 2 & 3 | Mentoring and early career development approaches identified and shared via employer engagement and wider partner communications |  |  |  | Unfunded
|  | Improve coordination between employers, employment support services and training providers so candidates are better prepared for entry into work | • Share recruitment pipeline information, role requirements and sector demand insight with providers and employment support partners to improve candidate preparation • Strengthen communication between employers, training providers, careers services and employment support services to improve coordination around candidate readiness • Encourage employer engagement in programme design, candidate preparation and progression planning where appropriate • Share intelligence on recruitment cycles, role requirements and changing workforce expectations with providers and support services • Use the LSIP to improve the consistency of evidence, messaging and coordination across the local system | Lead: LSIP team & Local Authorities Partners: FE, HE, SCTP and other ITPs, employer/sector bodies, employers, SLN | Year 2 & 3 | Coordinated approach to employer engagement and candidate preparation defined and shared with partners across the local system |  |  |  | Unfunded