## Tracker
mailto:info@buildingswell.com?subject=I Want to Learn More
Total Orders |  | Not Started |  | In Progress |  | On Hold |  | Complete |  | Overdue
10 |  | 4 |  | 4 |  | 0 |  | 2 |  | 0
orders |  | orders |  | orders |  | orders |  | orders |  | orders
Order / Job Name | Project | Department | Stage | Priority | Status | Assigned To | Start Date | Duration (Days) | Est. Completion | Days Until Due | Actual Completion | Notes
Panel Board PB-1 | Server Farm Telecom | Prefab | Fabrication | High | In Progress | mike.chen@example.com | 2026-02-17 | 5 | 2026-02-22 | 6 |  | 480V main panel
Panel Board PB-2 | Server Farm Telecom | Prefab | Procurement | High | In Progress | sarah.kim@example.com | 2026-02-14 | 12 | 2026-02-26 | 10 |  | Waiting on breakers from Eaton
Conduit Rack Assembly A | Main Street 123 | Prefab | Fabrication | Medium | Not Started | tom.park@example.com | 2026-02-24 | 3 | 2026-02-27 | 11
Wire Harness – MCC-01 | Main Street 123 | Engineering | Engineering / Design | High | Complete | james.liu@example.com | 2026-02-10 | 4 | 2026-02-14 |  | 2026-02-13 | Released to fab
Light Fixture Brackets | Cedar Heights | Prefab | Fabrication | Low | Not Started | ana.ruiz@example.com | 2026-03-03 | 2 | 2026-03-05 | 17
Transformer Connections | Oakridge Medical | Engineering | Engineering / Design | Critical | In Progress | david.okafor@example.com | 2026-02-12 | 6 | 2026-02-18 | 2 |  | Coordinating with mechanical
Fire Alarm Panel | Oakridge Medical | Prefab | Procurement | High | Not Started | maria.santos@example.com | 2026-02-20 | 15 | 2026-03-07 | 19 |  | Long lead — order ASAP
Generator Whip Assemblies | Server Farm Telecom | Prefab | Fabrication | Medium | Not Started | mike.chen@example.com | 2026-03-01 | 4 | 2026-03-05 | 17
Switchgear Bus Duct | Main Street 123 | QC | QC / Testing | High | In Progress | tom.park@example.com | 2026-02-18 | 2 | 2026-02-20 | 4 |  | Megger test scheduled
Receptacle Rough-In Kits | Cedar Heights | Prefab | Staging | Low | Complete | ana.ruiz@example.com | 2026-02-10 | 1 | 2026-02-11 |  | 2026-02-10 | Shipped to site
Formulas:
Overdue = IF(AND([Est. Completion]<>"",[Status]<>"Complete"),[Est. Completion]-TODAY(),"")
Est. Completion = IF(AND([Start Date]<>"",[Complete]<>""),[Start Date]+[Complete],"")

## Stages
Stage | Description
Engineering / Design | Drawings, load calcs, panel schedules, and coordination
Procurement | Material ordering, vendor coordination, lead time tracking
Fabrication | Conduit bending, panel assembly, wire harness prep
QC / Testing | Continuity checks, megger testing, label verification
Staging | Kitting, labeling, and staging for delivery
Shipping / Delivery | Loading, transport, and field delivery
Field Install | On-site installation and final connections
Punch / Closeout | Punch list items, as-builts, and project closeout