## Tracker
mailto:info@buildingswell.com?subject=I Want to Learn More
Total Orders |  | Not Started |  | In Progress |  | On Hold |  | Complete |  | Overdue
10 |  | 2 |  | 7 |  | 0 |  | 1 |  | 0
orders |  | orders |  | orders |  | orders |  | orders |  | orders
Order / Job Name | Project | Department | Stage | Priority | Status | Assigned To | Start Date | Duration (Days) | Est. Completion | Days Until Due | Actual Completion | Notes
Unit 4A – Kitchen Module | Cedar Heights Phase 2 | Production | Interior Finish | High | In Progress | tom.park@example.com | 2026-02-14 | 10 | 2026-02-24 | 8 |  | Cabinets arriving 2/16
Unit 4A – Bathroom Module | Cedar Heights Phase 2 | Production | Rough-In MEP | High | In Progress | mike.chen@example.com | 2026-02-17 | 5 | 2026-02-22 | 6 |  | Plumbing rough-in first
Unit 4B – Living Module | Cedar Heights Phase 2 | Production | Framing | Medium | In Progress | david.okafor@example.com | 2026-02-20 | 4 | 2026-02-24 | 8
Unit 4B – Bedroom Module | Cedar Heights Phase 2 | Engineering | Engineering / Design | Medium | Complete | james.liu@example.com | 2026-02-10 | 6 | 2026-02-16 |  | 2026-02-15 | Shop drawings approved
Lobby Module A | Oakridge Medical Wing | Procurement | Material Procurement | Critical | In Progress | sarah.kim@example.com | 2026-02-12 | 18 | 2026-03-02 | 14 |  | Steel lead time 3 weeks
Lobby Module B | Oakridge Medical Wing | Engineering | Engineering / Design | High | In Progress | maria.santos@example.com | 2026-02-14 | 10 | 2026-02-24 | 8 |  | BIM coordination ongoing
Corridor Module C1 | Oakridge Medical Wing | Production | Framing | Medium | Not Started | tom.park@example.com | 2026-03-05 | 5 | 2026-03-10 | 22
Classroom Pod 1 | Lincoln Elementary | QC | QC / Inspection | High | In Progress | ana.ruiz@example.com | 2026-02-18 | 2 | 2026-02-20 | 4 |  | Fire marshal inspection Wed
Classroom Pod 2 | Lincoln Elementary | Production | Insulation / Sheathing | Medium | In Progress | david.okafor@example.com | 2026-02-16 | 3 | 2026-02-19 | 3
Admin Office Module | Lincoln Elementary | Production | Wrap / Transport Prep | High | Not Started | mike.chen@example.com | 2026-02-25 | 2 | 2026-02-27 | 11 |  | Crane scheduled 2/28
Formulas:
Overdue = IF(AND([Est. Completion]<>"",[Status]<>"Complete"),[Est. Completion]-TODAY(),"")
Est. Completion = IF(AND([Start Date]<>"",[Complete]<>""),[Start Date]+[Complete],"")

## Stages
Stage | Description
Engineering / Design | Structural calcs, MEP coordination, shop drawings, BIM
Material Procurement | Lumber, steel, insulation, windows, fixtures ordering
Framing | Wall panel framing, floor deck, roof truss assembly
Rough-In MEP | Electrical, plumbing, and mechanical rough-in inside module
Insulation / Sheathing | Wall insulation, vapor barrier, exterior sheathing
Interior Finish | Drywall, paint, flooring, trim, cabinet install
QC / Inspection | In-plant inspection, code compliance, punch list
Wrap / Transport Prep | Weatherproofing, bracing, loading prep
Shipping / Set | Transport to site and crane set
Site Stitch | Module-to-module connections, final MEP tie-ins, exterior finish