Free Gap Analysis Template — City example

Built from 20,000+ strategic plans analyzed (2017–2024).

How to use this gap analysis template in 7 steps

Fill the header first, then one grid row per measure. Pull the current reading with its date and source, write the target with its deadline and assumption, and measure the gap. Name the gap type, run five whys once, then write one action with one named owner and a due date. Review the grid on a fixed day.

1. Pick one goal and one measure per row. Use a measure someone updates at least monthly, owned by a person who controls its inputs. If nobody can say what would move it by 10%, it's a placeholder, not a measure.

2. Write the current state with its date and source. For example: 7.5 minutes, September 2026, CAD export pulled October 3. A number without a date starts arguments, not decisions.

3. Write the target state with its deadline and assumption. “7.2 minutes by June 30, 2027, assuming all patrol positions are filled” tells you what to check first when the gap opens.

4. Measure the gap and name its type. Write the difference and its direction over the last three readings. Then pick one of the four gap types: performance, tracking, definition or strategy.

5. Run five whys once. Ask why the gap exists, then why again, until you reach something your organization can change this year. That answer goes in the root cause column.

6. Write one action, one owner and one due date. Name a person, with a title, who controls the inputs. In ClearPoint plan data, initiatives with a named owner are completed 2.5× as often (21.5% vs 8.7%).

7. Review the grid on a fixed day. Re-read every row on the monthly update day. Close a row when the reading meets its target line. Re-baseline a target when its assumption breaks, and write down why.

The four types of gap

| Gap type | What you see | What it usually means | First fix | In the examples |
| --- | --- | --- | --- | --- |
| Performance | A fresh reading, worse than the target line. | The work isn't producing the result. | Change or add one action. Check in within 90 days. | City 2.1 · Hospital 1.1 · University 1.1 |
| Tracking | No reading on the update day, or the same value for months. | Nobody owns the reading. | Name an owner for the data before you add any work. | City 4.2 · Hospital 4.1 · University 4.1 |
| Definition | The measure moved, but the target no longer makes sense. | An assumption behind the target broke. | Re-baseline the target and write down which assumption changed. | City 3.1 · Hospital 3.1 · University 2.2 |
| Strategy | Projects finish on time, and the measure still misses. | The plan is working on the wrong cause. | Pause the projects. Run a strategy review on that goal. | City 1.1 · Hospital 1.2 · University 1.2 |

Example 1: gap analysis for a city of 38,000 residents

This is the template filled in for the council-manager city of our 5-year strategic plan template, one quarter into its plan. Four measures show four different gaps: performance, tracking, definition and strategy. The analysis is dated October 10, 2026, covers the first quarter of FY2027, and goes to the November council work session.

Illustrative example. Owner names are ClearPoint demo personas.

| Field | City example |
| --- | --- |
| Organization and plan | City strategic plan FY2027–FY2031, council-manager city of about 38,000 residents. All four goals. |
| Analysis date | October 10, 2026 (the monthly update day) |
| Period covered | Q1 FY2027: July to September 2026 |
| Data sources | Police CAD export · work-order system · downtown storefront walk survey · 2026 pavement condition survey |
| Prepared by | Clarice W., City Manager |
| Reviewed at | Council work session, November 18, 2026 |
| Gap rule | A row is a gap when the latest reading misses the target line for the period, or when no reading arrives on the update day. |
| Next review | November 10, 2026 update day |

| Goal and measure | Current state (value, date, source) | Target state (value, deadline, assumption) | Gap | Gap type | Root cause | Action | Owner | Due date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 Answer priority-1 calls faster · Median priority-1 response time (minutes) | 7.5 (September 2026, CAD export pulled Oct. 3) | 7.2 by June 30, 2027, assuming all patrol positions are filled | 0.3 minutes slower; 7.4 at baseline, so moving the wrong way | Performance | Two patrol positions have been open since August, so night shifts run one car short on the east beat. | Launch the patrol shift redesign and post both positions. | Lance B., Police Chief | Nov. 1, 2026 · next reading Dec. 10 |
| 4.2 Close resident requests on time · Service requests closed within their target time | No reading on the Oct. 10 update day (last value 68%, August) | 71% by June 30, 2027 | Unknown: one update day missed | Tracking | The analyst who ran the monthly work-order export left in September. Nobody inherited the task. | Assign the export to a named analyst and add it to the update-day checklist. | Clarice W., City Manager | Nov. 10, 2026 update day |
| 3.1 Fill empty storefronts · Downtown ground-floor vacancy rate | 15% (September 2026 storefront walk survey) | 13% by June 30, 2027, set assuming both anchor tenants stayed | 2 points above target; up 1 point from the 14% baseline | Definition | Both anchor tenants closed in August. The target rests on an assumption that no longer holds. | Re-baseline the FY2027 target at the council retreat. Façade grant round 1 still opens Jan. 15. | Jimmy O., Economic Development Manager | January 2027 council retreat |
| 1.1 Bring local streets to good condition · Pavement Condition Index, network average (0–100) | 62 (2026 pavement condition survey) | 63 at the 2027 survey, on the way to 70 in FY2031 | 1 point below the FY2027 line; flat at 62 for three surveys while every resurfacing contract finished on time | Strategy | Resurfacing covers fewer lane-miles each year than the network loses to wear. The work delivers; the index stays flat. | Bring a pavement-preservation scenario (crack seal and slurry on streets in fair condition) to council before the FY2028 capital plan. | Maggie S., Public Works Director | March 2027 capital plan work session |

Why it's built this way

Every reading carries a date and a source. The council debates the fix, not the number.

The tracking row has no value, on purpose. A missing reading is a gap of its own, and it gets an owner before it gets an action.

The strategy row is the uncomfortable one. Every resurfacing contract finished on time, and the index didn't move. That's the signal to change the mix of work, not to add more of it.

Your gap analysis

Fill the header first, then one grid row per measure. The first grid row shows what to write.

| Field | What to write |
| --- | --- |
| Organization and plan | "[Organization] Strategic Plan FY2027–FY2031", and the goal area or department this analysis covers. |
| Analysis date | The day you pull the readings. Every value in the grid is as of this date. |
| Period covered | The month, quarter or term the readings describe, for example Q1 FY2027. |
| Data sources | Where each reading comes from: the system, the report, and who exports it. |
| Prepared by | One name: the person who fills the grid and checks the sources. |
| Reviewed at | The meeting that reviews the grid, with its date. |
| Gap rule | When a difference counts as a gap. For example: the latest reading misses the target line for the period, or no reading arrives on the update day. |
| Next review | The date of the next reading, usually the next monthly update day. |

| Goal and measure | Current state (value, date, source) | Target state (value, deadline, assumption) | Gap | Gap type | Root cause | Action | Owner | Due date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| [Goal number and name] · [the one measure that shows progress] | [Value] ([date of the reading], [source]) | [Value] by [deadline], assuming [the assumption behind the target] | [Difference and direction], [trend over the last three readings] | [Performance / Tracking / Definition / Strategy] | [What the fifth 'why' points to] | [One action that removes the root cause] | [Name, title] | [Date the action is done] · next reading [date] |

See how ClearPoint keeps every gap, owner and due date current: www.clearpointstrategy.com/get-a-demo