# Office Move Checklist

Company: [Company Name]

Move Date: [Date]

Project Manager: [Name]

All 80+ tasks across 7 phases. Assign an owner to each task before sharing.

|  | Task | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| ## 6-12 months out |  |  |  |  |
| ☐ | Review current lease: notice period, exit penalties, and restoration requirements | Legal / Move Lead |  | Not started |
| ☐ | Notify current building management of move date; confirm notice period required (typically 60-90 days) | Facilities |  | Not started |
| ☐ | Get a rough decommissioning estimate from a commercial fit-out contractor | Facilities |  | Not started |
| ☐ | Photograph the existing space before any decommissioning begins (for dispute protection) | Facilities |  | Not started |
| ☐ | Pull attendance data from the current office: peak occupancy, average daily headcount, meeting room utilization | Facilities / Workplace |  | Not started |
| ☐ | Set the move budget with a contingency plan to cover unexpected expenses (15–20% buffer) | Finance |  | Not started |
| ☐ | Appoint a project manager to own key milestones and coordinate all vendors | Leadership |  | Not started |
| ☐ | Define what the new space needs to fix or improve | Move Lead |  | Not started |
| ## 3-6 months out |  |  |  |  |
| ☐ | Sign new lease | Move Lead / Legal |  | Not started |
| ☐ | Order internet the same day you sign. It takes 60–90 days to get set up, longer if the building isn't already wired for it | IT |  | Not started |
| ☐ | Confirm decommissioning scope and get a final cost estimate | Facilities |  | Not started |
| ☐ | Get certificate of insurance from the moving company before signing | Facilities / Finance |  | Not started |
| ☐ | Lock in floor plan decisions: desk ratio, neighborhoods, reception layout | Facilities / Workplace |  | Not started |
| ☐ | Select workspace management software (desk booking, room scheduling, visitor management) | IT / Facilities |  | Not started |
| ☐ | Select and contract professional movers | Facilities |  | Not started |
| ☐ | Select IT relocation vendor | IT |  | Not started |
| ☐ | Contract fit-out contractor if the space needs work | Facilities |  | Not started |
| ☐ | Audit existing furniture (desks, chairs, storage, conference furniture): catalogue what moves and what gets replaced | Facilities |  | Not started |
| ☐ | Schedule liquidation or donation pickup for furniture not moving, and order any new furniture needed | Facilities |  | Not started |
| ☐ | Schedule e-waste disposal for old equipment: monitors, hard drives, peripherals | IT / Facilities |  | Not started |
| ☐ | Arrange temporary storage for furniture or equipment that won't move immediately | Facilities |  | Not started |
| ☐ | Set up shared project tracker with a detailed timeline and dedicated move channel in Slack or Teams | Move Lead |  | Not started |
| ## 1-3 months out |  |  |  |  |
| ☐ | Run a Wi-Fi and network check across the new space (glass walls and open floors create dead zones) | IT |  | Not started |
| ☐ | Build a detailed inventory of all IT equipment and existing office equipment: user, device type, current desk, destination desk | IT |  | Not started |
| ☐ | Build and roll out a labeling system for all equipment | IT |  | Not started |
| ☐ | Back up all data | IT |  | Not started |
| ☐ | Load the detailed floor plan into the booking platform | Workplace |  | Not started |
| ☐ | Set up desk booking: zones, neighborhoods, check-in method (QR or app) | Workplace |  | Not started |
| ☐ | Set up room scheduling with calendar sync (Outlook or Google) | Workplace / IT |  | Not started |
| ☐ | Set up visitor check-in at reception | Workplace |  | Not started |
| ☐ | Brief department heads on the booking system before briefing their teams | HR / Facilities |  | Not started |
| ☐ | Update the company address across: website, Google Business Profile, clients, vendors, bank, insurance | Operations / Marketing |  | Not started |
| ☐ | Submit USPS Change of Address (mail forwarding) | Operations |  | Not started |
| ☐ | Update business registration and state filings with new address | Legal / Finance |  | Not started |
| ☐ | Update payroll and HR systems with new address for tax purposes | HR / Finance |  | Not started |
| ☐ | Notify business insurance and commercial property insurance of address change | Finance |  | Not started |
| ☐ | Update employee email signatures with new address | HR / Operations |  | Not started |
| ☐ | Reorder business cards and marketing materials with new address | Marketing |  | Not started |
| ☐ | Update vendor contracts and supply agreements with new shipping address | Operations |  | Not started |
| ☐ | Email clients, customers, and partners about the move date and new address | Operations / Account teams |  | Not started |
| ☐ | Reprogram building access cards, security badges, and access codes for new location | IT / Facilities |  | Not started |
| ☐ | Send employees a specific FAQ: new address, how to book desks, team zones, move day logistics | HR |  | Not started |
| ☐ | Reschedule recurring client visits and customer meetings around move week | Operations / Account teams |  | Not started |
| ☐ | Remind employees to clear desks of personal belongings and non-essential items before move day | HR |  | Not started |
| ☐ | Confirm parking at new building and arrange permits if needed | Facilities |  | Not started |
| ☐ | Order moving supplies: boxes, labels, packing tape, packing materials, and office supplies for day one | Facilities |  | Not started |
| ## Final 2 weeks |  |  |  |  |
| ☐ | Tech dry run: book a desk, schedule a room, run a test visitor check-in | IT / Workplace |  | Not started |
| ☐ | Final walkthrough of every meeting room and break rooms: network ports, AV, and room display | IT |  | Not started |
| ☐ | Confirm occupancy sensors are live | Workplace / IT |  | Not started |
| ☐ | Make sure kiosks are easy to find for visitors | Workplace |  | Not started |
| ☐ | Check that signage matches room names in the booking system | Facilities |  | Not started |
| ☐ | Confirm fire safety, evacuation plan, and security systems are operational at new space | Facilities |  | Not started |
| ☐ | Confirm moving truck and movers: arrival time, freight elevator booking, building access | Facilities |  | Not started |
| ☐ | Confirm IT vendor schedule for move day | IT |  | Not started |
| ☐ | Arrange parking passes for move day | Facilities |  | Not started |
| ☐ | Send the detailed moving day plan to all employees: timing, what to do on arrival, who to contact | HR / Move Lead |  | Not started |
| ☐ | Confirm all filing cabinets and storage are labeled and ready | All departments |  | Not started |
| ## Move day |  |  |  |  |
| ☐ | IT vendor on site before employees arrive for IT setup and sensitive equipment | IT |  | Not started |
| ☐ | Move lead on site, with contact list for all employees and key vendors | Move Lead |  | Not started |
| ☐ | Confirm internet is live before employees arrive | IT |  | Not started |
| ☐ | Distribute key cards and building passes | Facilities |  | Not started |
| ☐ | Verify all devices arrive at correct destination desks | IT |  | Not started |
| ☐ | Test conferencing and VoIP setup | IT |  | Not started |
| ☐ | Put up emergency contacts and the floor plan somewhere visible on each floor | Facilities |  | Not started |
| ☐ | Keep the move channel open for real-time questions | Move Lead |  | Not started |
| ☐ | Coffee, water, and snacks on site for the team and movers | Move Lead / HR |  | Not started |
| ☐ | Photograph any damage to furniture and both spaces during the move | Move Lead / Facilities |  | Not started |
| ☐ | Walk the old space with movers before they leave. Confirm nothing is left behind | Move Lead / Facilities |  | Not started |
| ☐ | Read utility meters at the old space before leaving | Facilities |  | Not started |
| ☐ | Return keys to old building OR document the timeline for return | Facilities |  | Not started |
| ## Week 1 |  |  |  |  |
| ☐ | Keep a help channel active for move-related questions | Move Lead |  | Not started |
| ☐ | Send employees a reminder on how to use the booking system | HR |  | Not started |
| ☐ | Collect issues from department heads | Move Lead |  | Not started |
| ☐ | Return keys and access cards to previous building | Facilities |  | Not started |
| ☐ | File any remaining change-of-address notifications | Operations |  | Not started |
| ☐ | Schedule decommissioning work on old space | Facilities |  | Not started |
| ## First 60-90 days |  |  |  |  |
| ☐ | Review desk utilization by zone: identify over- and underused neighborhoods | Workplace |  | Not started |
| ☐ | Compare occupancy sensor data to booking data. Ghost bookings skew utilization numbers. Adjust check-in settings if needed | Workplace |  | Not started |
| ☐ | Check if rooms are staying blocked after meetings end early. Turn on auto-release if they are | Workplace |  | Not started |
| ☐ | Adjust zone boundaries in the booking platform based on observed behavior | Workplace |  | Not started |
| ☐ | Check room booking patterns and adjust room-to-desk ratio if needed | Workplace |  | Not started |
| ☐ | Gather feedback on employee experience in the new space | HR |  | Not started |
| ☐ | Complete decommissioning of old space | Facilities |  | Not started |
| ☐ | Post move evaluation: review total move costs versus budget | Finance |  | Not started |
| ☐ | Update the floor plan in the booking software if the layout changed | Workplace |  | Not started |
| ☐ | Plan an office warming party to welcome the team properly | HR / Move Lead |  | Not started |