| April 2026 Monthly Progress Summary LSIDB Pumping Stations |  |
| --- | --- |
| Key Monthly Progress |  |
| Lapperditch - MCC kiosk constructed including base slab cast - Outfall embankment steps installed and landing slab cast - Ducting and drawpits installed - Drainage and manhole chambers constructed - Gusset plates welded to PFU channels - Excavation complete for rootlock wall & cable diversion - Rootlock wall - Retaining kerbs installed for rootlock wall - Steelwork/GRP fabrication drawings/procurement underway - Stop log board installation commenced - Pump install complete Marshfield - Retaining wall weep holes cored and drainage installed - MCC kiosk retaining wall foundations built (including rebar) - MCC retaining wall units installed and grouted - Ducting and drawpits to MCC kiosk installed - MCC kiosk backfilled with Type 1 and compacted - Concrete blinding poured for Kiosk base slab - Steelwork/GRP fabrication drawings/procurement underway - Gusset plates welded to PFU channels - Stop log board installation commenced - Pump/Pipe/Flapvalve install underway |  |
| Key Planned Work for Next Month |  |
| Lapperditch - Divert NG Cable - Install Geogrow Rootlock wall - Install Stop logs (Inlet) - Break out swale, start culvert extension - Install Eel pass Marshfield - Install MCC kiosk base - Complete pipe/pump install - Install stop logs - Install Eel pass rhine base slab & steps Install Eel pass retaining wall |  |

Key Project Dates

Lapperditch Date; Activity. December 2025; Design Completion. January 2026; Site Construction Commence. Late Spring 2026; Commissioning. Summer 2026; Site Works Complete. Summer 2026; Project Completion.

Marshfield

| Date | Activity |
| --- | --- |
| January 2026 | Design Completion |
| January 2026 | Site Construction Commence |
| Summer 2026 | Commissioning |
| Summer 2026 | Site Works Complete |
| Summer 2026 | Project Completion |

Oldbury Naite

| Date | Activity |
| --- | --- |
| September 2026 | Construction Start |

Elmore Back

| Date | Activity |
| --- | --- |
| Winter 2026 | Design Completion |
| Summer 2026 | Site Construction Commence |
| Summer 2026 | Commissioning |
| Summer 2026 | Site Works Complete |
| Summer 2026 | Project Completion |