# Soft Launch Checklist

# Why This Matters

Like any marketplace, the Talent Marketplace needs to be stocked with products (opportunities) before opening for business. You only get one chance to make a good first impression. Make this one count by ensuring the marketplace has plenty of opportunities for new users to choose from!

🧠 BEHAVIORAL SCIENCE TIP: Social Proof

Empty marketplaces fail because nobody wants to be first. People look to others to validate their behavior. A populated marketplace signals legitimacy, safety, and value—triggering the bandwagon effect that drives rapid adoption.

# The Three Phases of a Successful Soft Launch

- Pre-Soft Launch: Set the stage with careful planning and selection

- During Soft Launch: Create momentum through urgency, competition, and visibility

- After Soft Launch: Capture learnings and leverage early advocates

Pre-Soft Launch

Step 1: Select Your Early Adopters Strategically

- 5-7% of total launch population (the critical mass needed to establish social proof)

- Diverse representation from all business units (not clustered in one area)

- Mix of managers and individual contributors (different perspectives and needs)

- Influential connectors in the business—people others naturally look to and trust

🧠 BEHAVIORAL SCIENCE TIP: Trusted Messengers

Research shows that adoption spreads through networks via trusted peers, not top-down mandates. Selecting influential 'connectors' creates multiple adoption pathways. Their participation signals safety and value to their networks, accelerating spread.

How to select them (two options):

- Stakeholder nomination: Ask key stakeholders to identify individuals who are natural advocates, respected voices, and early technology adopters

- Self-selection with framing: Send an email to the entire launch population offering 'exclusive early access' and 'the opportunity to shape the platform' for volunteers

Total time commitment: 2.5 hours over the soft launch period

- Attend 1 training session (60-75 minutes): Vision for Talent Marketplace & how to get started

- Create a detailed profile (5/5 completion rate)

- Publish at least one piece of 'Work' to the marketplace

- Act as the 'go-to' person in their business area for questions

- Provide feedback via end-of-launch survey

🧠 BEHAVIORAL SCIENCE TIP: Implementation Intentions

Make commitments specific and concrete. Instead of 'participate in the soft launch,' specify exactly what, when, and how much. Research shows specific implementation intentions increase completion rates by 2-3x compared to vague goals.

Step 2: Determine Optimal Timing

Recommended duration: 2-3 weeks. This creates the optimal balance between giving people time to complete tasks and maintaining urgency. Longer soft launches risk content becoming stale before full launch. Shorter periods don't provide enough time for adoption behaviors to form.

Sample 2-Week Timeline:

| Day | Activity |
| --- | --- |
| Day 0 | Send invitation to Early Adopters with exclusive framing |
| Day 2-3 | Host training sessions (make them interactive and fun) |
| Day 5 | Scheduled 'posting time' block (from training) + first progress update |
| Day 8 | Midpoint celebration: Share early wins, department leaderboard |
| Day 11 | Final push: 'Only 3 days left!' reminder with gap-to-goal visualization |
| Day 13 | Send feedback survey |
| Day 14 | Celebration & recognition: Share final results, thank early adopters publicly |

Step 3: Set Clear, Public KPIs

Track these three adoption metrics and share them visibly with Early Adopters so they understand what success looks like and how they contribute.

| KPI | Definition | Goal |
| --- | --- | --- |
| Registration Rate | % of users who have accepted T&Cs out of all employees with access | 90% |
| Profile Completeness | % of users with profile completeness of at least 4 out of 5 | 80% |
| Published Activities | Total number of opportunities published on the platform | <3,000 users = 25 3-5k users = 50 5k+ users = 100 |

🧠 BEHAVIORAL SCIENCE PRINCIPLE: Goal-Setting Theory

Specific, measurable goals with visible progress tracking increase achievement rates dramatically. Public goals create accountability through social pressure. Frequent progress updates maintain motivation and create micro-celebrations that reinforce behavior.

Step 4: Review & Tailor Communications Plan

Review your soft launch communications materials and ensure they incorporate these behavioral nudges:

- Scarcity framing: 'Exclusive early access,' 'limited group,' 'be among the first'

- Social proof: 'Join your colleagues from [department X],' 'Other leaders are already participating'

- Loss aversion: 'Don't miss your chance to shape the platform,' 'This opportunity closes on [date]'

- Identity priming: 'As innovators and early adopters in our company...'

During Soft Launch

Step 1: Run High-Energy, Interactive Training Sessions

Recommended training: Vision for Marketplace & Getting Started (60-75 minutes)

- What is our vision for the Talent Marketplace? (10 min)

- How does it work? What's in it for me? (15 min)

- Live demo: Creating your profile together (20 min)

- Live demo: Publishing 'Work' (15 min)

- Q&A and next steps (10 min)

| Technique | How to Apply |
| --- | --- |
| Do-it-together | Drop the platform link in chat. Have everyone create their profile DURING the session. Ask them to post a 😎 emoji once they hit 5/5 completion. |
| Implementation Intentions | At the end of training, schedule a 15-30 minute 'Posting Time' block in attendees' calendars 2-3 days later. This transforms vague intention into concrete action. |
| Gamification | Create friendly competition: 'Let's guess which department will post the most projects!' Display guesses and track throughout launch. |
| Social Recognition | Celebrate the first person to hit 5/5 by name in the session. Public recognition motivates others and normalizes the behavior. |

Step 2: Create Urgency

Throughout the soft launch, maintain momentum with regular progress updates that leverage social dynamics:

- Daily/bi-daily scoreboard updates: 'We're at 67% profile completion—only 13% to go!' or '42 projects published, 8 away from our goal!'

- Department leaderboards: 'Marketing is leading with 15 projects posted. Can Engineering catch up?'

- Visual progress indicators: Use speedometers, thermometers, or progress bars showing gap-to-goal

- Countdown messaging: 'Only 5 days left!' '72 hours until soft launch ends!'

🧠 BEHAVIORAL SCIENCE TIP: Loss Aversion & Social Accountability

Showing the gap-to-goal triggers loss aversion—people hate to see goals unmet. Public progress creates social accountability. Leaderboards tap into competitive dynamics and desire for status. Together, these create 'productive urgency' without feeling coercive.

Step 3: Lead by Example

The project team should publish their own program objectives to the marketplace. This demonstrates commitment and normalizes the behavior.

Sample Team Goals to Post:

- Achieve 50% registered users within 6 months

- Achieve ROI within first year (marketplace-driven value exceeds platform cost)

- Increase internal mobility rates by X%

- Improve utilization of critical skills by X%

Step 4: Collect Structured Feedback

Send a feedback survey toward the end of the soft launch (Day 13 of a 14-day launch). Focus on four areas:

| Category | Sample Questions |
| --- | --- |
| Vision | - What excites you most about the marketplace? - Do you understand how it fits into organizational strategy? - Is it clear what's in it for you as a [manager/employee]? |
| Blockers | - Do you have any concerns about the marketplace? - Can you anticipate pushback from your part of the business? Why? - How would you recommend addressing these concerns? |
| Training & Comms | - What did you like about the training and communications? - What could be improved? - What do you want to know more about? |
| Platform Usage | - How long did it take to complete your profile/post Work? - Did you understand the difference between applied and discovered candidates? - Was anything unclear or confusing? |

After Soft Launch

Step 1: Review feedback and implement quick wins before full launch

- Amplify the positive: Include what excited people in launch communications

- Sharpen the benefits: If value proposition wasn't clear to specific personas (e.g., managers), refine messaging

- Address blockers head-on: Build FAQ responses or messaging that preemptively addresses anticipated concerns

- Improve materials: Update training decks or comms based on confusion points

🧠 BEHAVIORAL SCIENCE TIP: Proactively addressing concerns

Addressing concerns before people raise them is far more effective than reactive responses. It builds trust, demonstrates you're listening, and neutralizes objections before they spread.

Step 2: Collect Powerful Testimonials

Real user stories are among your most persuasive assets for full launch. Gather three types of testimonials:

| Testimonial Type | Purpose & Sample Questions |
| --- | --- |
| Senior Leader | Purpose: Provides top-down legitimacy and strategic vision - How do you envision the marketplace benefiting the organization? - What convinced you to post your own work? What was the experience like? |
| Early Adopter Employee | Purpose: Peer voice that others identify with; addresses ease of use - What excites you about the marketplace? - How easy was it to create your profile and find opportunities? - What would you tell a colleague who's on the fence? |
| Manager | Purpose: Addresses manager-specific concerns, especially 'talent poaching' fears - How will you use the marketplace to support your team's development? - What were your initial concerns? How has your thinking evolved? - What would you say to other managers worried about losing talent? |

🧠 BEHAVIORAL SCIENCE TIP: Similarity Bias & Social Proof

People are more persuaded by those similar to themselves. A senior leader testimonial won't convince an individual contributor, but a peer's will. Having multiple testimonial types covers the spectrum of identities in your audience. Real stories with specific details are far more credible than generic endorsements.