## Priority 1
SLVBHG Strategic Priorities 2023-2026
Priority 1: | Action Steps | Person Responsible | Timeline | Measurements of Success | Progress/Notes
SLVBHG will attain certification as a comprehensive provider by the State of Colorado by July 1, 2024. | Assess if SLVBHG offers the required services to become a comprehensive provider and add services that are missing (*list is included below) | Leova/Jennifer | 2023-11-01 | Assessment completed | OP SUD- need more Will need IOP for both Mental Health and SUD
| Submit a cost report to Colorado Department of Healthcare and Financing (HCPF) | Kyle Turnwall | November 30, 2023 | Cost report completed | Develop PPP Model- analysis- completed
| Assess the properties SLVBHG owns and determine ideal state of ownership | Kyle Turnwall/Victoria | 2024-03-31 | Property plan established | Will begin listing
| Develop a plan to strengthen external partnerships (This is included as an action step for both priority 1 & 2) | Kate/C-suite *these relationships should not be held exclusively by the CEO | 2024-03-31 | Written plan developed | Should include strengthening partnerships with primary care providers
| Implement plan to strengthen external partnerships | C-suite/Directors | 2024-12-31 | Partnership survey demonstrates increased support
| Develop programming that is not already in place (IOP/TBD) | Leova/Jennifer | Need to align timeline based on certification requirements | Programming developed as needed | In Progress
| Apply for status as a comprehensive provider | Leova/Jennifer | Need to align timeline based on application requirements (July 1, 2024 start date for PPS) | Status obtained | Attestestation complete for BHA and HCPF
| Obtain Prospective Payment System rate | Kyle Turnwall | Need to align timeline based on application requirements | Rate obtained and assessed as sufficient
| Determine if SLVBHG should also apply for essential provider status for specific service line | Victoria | July 1, 2024 start date for enhanced fee schedule. THS could not find deadline to apply | Essential provider status obtained | N/A
*Required services: | • Emergency and crisis behavioral health services |  | Leova: | Jennifer
| • Mental health and substance use outpatient services |  | OP MH | Psych
| • Behavioral health high-intensity outpatient services |  | OP SUD | Case Mang./New Begginings
| • Care management |  | SUD Forensic | SOTP
| • Outreach, education, and engagement services |  | Schools | Housing
| • Mental health and substance use recovery supports |  | Care Coordination | Peer Services
| • Outpatient competency restoration |  | Bridges | Transportation
| • Screening, assessment, and diagnosis, including risk assessment, crisis planning, and monitoring to key health indicator |  | Restoration | Crisis/Mi Esperanza
|  |  | Adol. CM | DVR
Off. Services
SafeCare
PSSF/Child First

## Priority 2
SLVBHG Strategic Priorities 2023-2026
Priority 2: | Action Steps | Person Responsible | Timeline | Measurements of Success | Progress/Notes
SLVBHG will become a Certified Community Behavioral Health Clinic (CCBHC) by 2026. | Develop a plan to strengthen external partnerships (This is included as an action step for both priority 1 & 2) | Victoria & Kate/C-suite *these relationships should not be held exclusively by the CEO | 2024-03-31 | Written plan developed | Should include strengthening partnerships with primary care providers
| Assess what services/programs should be added or eliminated to be in alignment with what is required by the model or if community needs have changed | Leova/Jennifer | By May 2024 grant submission | Assessment completed
| Determine what is needed to enhance "Business intelligence" and continuous quality improvement capacity | C-suite | By May 2024 grant submission | BI and CQI needs identified
| Evaluate if the current board composition and member advisory committee meets the requirements of CCBHC or make changes as needed | Victoria | By May 2024 grant submission | Requirements met | Done for BHA
| Complete an application to Substance Abuse and Mental Health Services Administration (SAMHSA) for CCBHC | Kate | Notice of Funding Opportunity (NOFO) will likely come out in March 2024 and proposals will be due in May 2024 | Proposal submitted
| Advocate for state-level action on CCBHC | Victoria | Next state planning grant application deadline is anticipated December 2024 | State pursues planning grant or goes directly to application to be part of the Demonstration
| Obtain scoring sheet and resubmit to SAMHSA in next round if not funded | Kate | Notice of Funding Opportunity (NOFO) will likely come out in March 2025 and proposals will be due in May 2025 | Proposal submitted
CCBHC Required Scope of Services
Crisis Services
Treatment Planning
Screening, Assessment, Diagnosis & Risk Assessment
Outpatient Mental Health & Substance Use Services
Targeted Case Management
Outpatient Primary Care Screening and Monitoring
Community-Based Mental Health Care for Veterans
Peer, Family Support & Counselor Services
Psychiatric Rehabilitation Services

## Priority 3
SLVBHG Strategic Priorities 2023-2026
Priority 3: | Action Steps | Person Responsible | Timeline | Measurements of Success | Progress/Notes
SLVBHG Board of Directors will become a diversified, data-informed board with defined Key Performance Indicators by September 2024. | Survey current board members to gauge individual timeframes for remaining on the board, and institute term limits for existing and incoming board members. | Victoria | November 2023 | Staggered terms defined | Completed- Still ned to update/fix bylaws
| Identify key performance indicators (KPI's) and other metrics that will be regularly reported on to the board by the CEO | Victoria | January 2024 | KPIs identified | Completed
| Recruit new board members that were identified as potential candidates in the board retreat, or others | Executive Committee of Board | January 2024 | 9 to 11 board members are serving terms | Added Mark Manzanares to the board
| Provide appropriate data and updates on monthly/quarterly basis | Victoria and/or delegate | February 2024 - June 2026 | Monthly/quarterly reports provided
| Complete by-laws changes as needed | Board of Directors | June 2024 | New bylaws enacted | Requires working with an attorney

## Priority 4
SLVBHG Strategic Priorities 2023-2026
Priority 4: | Action Steps | Person Responsible | Timeline | Measurements of Success | Progress/Notes
SLVBHG will develop a comprehensive plan to attract and sustain workforce talent and be recognized as an employer of choice by July 1, 2025. | Evaluate current structure of HR department as it responds to HR laws | Victoria and Toni | October 2023 - June 2026 | Evaluation completed and necessary changes identified. | Patient Accounts and HR staffing
| Identify where SLVBHG may need to make new investments in getting updated technology to respond to changes in the industry | Victoria and Jana | October 2023 - June 2026 | Technology needs identified and budget allocated as needed. | Client electronic signature has been identified as a priority
| Identify professional development opportunities that can be offered to staff | C-suite | October 2023 - June 2026 | Staff retention rates | Training to support priorities 1 and 2
| Review current workforce recruitment strategies and determine if new strategies are needed | Toni | October 2023 - June 2026 | Length of vacancy/recruitment success rate | Grants awarded (2)
| Conduct staff survey - round 2 | Energage Toni and Victoria | November 2023 - December 2023 | Survey is completed | Need to evaluate results of survey
| Promote workplace wellness | Wellness Committee Chair (Bonnie Ortega) | October 2023 - June 2026 | Implementation of recommendations determined with Energage | SLVBHG has an exisiting workplace wellness committee Have engaged with Energage and will soon enter into a second round survey with them for workplace wellness

## Priority 5
SLVBHG Strategic Priorities 2023-2026
Priority 5: | Action Steps | Person Responsible | Timeline | Measurements of Success | Progress/Notes
SLVBHG will evaluate the pros and cons of participating in a bid as provider/owner of a Regional Accountable Entity (RAE) in the Medicaid Accountable Care Collaborative 3.0. SLVBHG will also evaluate the pros and cons of participating in a bid as a provider/owner of a Behavioral Health Administrative Services Organization (BHASO) and make the strategic decision whether to be part of a bid. | Review BHASO RFI, consider submitting comments | Victoria | 2023-11-03 | RFI reviewed, comments submittted if applicable | SLVBHG will be submitting an RFI response-Completed
| Review ACC 3.0 concept paper | Victoria, Jennifer, Leova & Kyle | October - November 2023 | Concept paper read | Next step will be for the C-suite to review as a group
| SLVBHG will determine if it will participate in a bid as part of Health Colorado Inc. (HCI) – by November 30, 2023 i. RAE ii. BHASO | Victoria | 2023-11-30 | Response provided to HCI
| Review draft RAE RFP | Victoria, Jennifer, Leova & Kyle | November- December 2023 | draft RFP reviewed
| SLVBHG will evaluate other partnership opportunities for a bid – by April 1, 2024 i. RAE ii. BHASO | Victoria | 2024-04-01 | Partnership opportunities vetted | May not be relevant if SLVBHG stays in bid with HCI. Potential partners may include but not be limited to: Signal, Diversus, Rocky Mountain Health Plans/United, Southern Colorado Health Network (SCHN), new configuration coming out of dissolution of HCI, or other
| Review BHASO final RFP | Victoria, Jennifer, Leova & Kyle | 2024-04-01 | RFP reviewed | will want to do an individual review and then a team review of the RFPs
| Review final RAE RFP | Victoria, Jennifer, Leova & Kyle | 2024-04-01 | RFP reviewed | will want to do an individual review and then a team review of the RFPs
| Other action steps to be determined | C-suite | TBD | TBD