Microplanning data to be collected

Microplanning is divided into two main areas:

- The province and district level teams gather details and information from all peripheral locations based upon a list of data to collect. This information gathering occurs prior to the microplanning workshop hosted in each province, as it is critical that the correct information is brought to the microplanning workshops to achieve its objectives. At least four weeks prior to the province workshop, the information required should be communicated to the district level.

- The second step is a microplanning workshop at the provincial level, bringing together the district teams that have collected the necessary data to ensure that the outcomes of the workshop – a detailed plan and budget for each district – can be achieved.

The final step in the microplanning process is the return of the central level teams to compile all district information results into one detailed campaign microplanning document with associated budget.

Information to be collected from districts for campaign planning prior to the provincial level microplanning includes:

District level:

- List of all members of the district coordination structure, including contact information

- List of potential additional members of the coordination structure that are not yet engaged

- Maps – district and provincial level maps, lower level maps if available, EPI maps if available – any maps!

Note: Maps are EXTREMELY important to help in the process of selecting DPs and their “catchment area”. And of course, very useful in planning micro-transport to DPs. As a minimum requirement, district teams must (if they don’t already have one) draw by hand on a “giant paper” a map of the district showing the road network, including rivers, bridges, location of Sede and localidades, health facilities, distances between sede, localidades and health facilities, villages, hard-to-reach areas, and any other relevant features.

- Warehousing – availability, location and contact information; condition (see warehouse assessment in annexes 13 and 14 of the LPoA); size; security measures; estimated costs (note: for all proposed warehouses, a warehouse assessment must be completed and will be verified by the SR logistics focal point). District teams should encourage people to use tape measures to calculate correct square footage of storage / warehouse space for LLIN. For warehousing, additional things to be collected are:

  - Warehouse manager and assistant name and contact number – include description of relevant experience based on criteria for selection

- Transport – availability of necessary (based on needed transportation – trucks, motorcycles, boats, donkeys, porters, etc.) transport modes and costs. Additional information to be collected includes:

  - Vehicles available (size, condition, etc.), as well as contact information for owners

  - Cost for fuel per litre (gas and diesel)

  - Main transport corridors, routes, conditions, obstacles, etc.

  - Any seasonal limitations to road movement in the area

- Microplanning and coverage results from the last EPI campaign in the district

- Information from EPI MOH staff on what could have been improved to extend coverage and reach targets (if not reached)

- List of all health facilities in the district and, for each health facility, the list of villages and their estimated population that are served by the health facility (normally within 5km)

  - If a health facility is serving a population beyond 5km from the facility (due to lack of peripheral facilities or health posts), these villages (with their population) should be listed separately for later mapping

  - If there are villages that are not covered by any health facility (too remote), these should also be listed (with their population) and including the distance from the health facility

  - In addition to the listing of all of the villages, any of them that are hard-to-reach (for any reason – access, geography, distance, etc. – should be identified with a reason as to why they are difficult to access and proposed solutions for planning purposes

- Number of community volunteers available for household assessment and LLIN distribution

- Location of potential distribution points based on “normal” points of congregation, EPI vaccination points, etc.

- Organizations (FBO / CBO) working in the district who could contribute to the campaign via their normal activities with some additional training or materials plus contact information

- List of churches and mosques or other religious gathering locations plus contact information

- List of schools (all levels) plus contact information

- List of people who have community influence and could be net advocates plus contact information

- List of traditional leaders plus contact information

- Reach of district and local radio stations and, in particular, a mapping of areas that may not be reached and therefore require additional interpersonal communication