Terms of reference for the central microplanning team for mass ITN distribution campaign 2018

Objective

To undertake the microplanning for the mass ITN distribution campaign and plan for all activities in line with the timeline and in collaboration with implementation level staff.

Specific objectives

1.	To participate actively in the training of trainers for microplanning, ensuring good knowledge of the campaign strategy, the objectives of microplanning, the use of the microplanning templates and the results of the microplanning workshops.

2.	Facilitate the microplanning workshops with representatives from provinces/regions, and districts, so as to:

a.	Prepare a detailed mapping by district in order to plan implementation activities

b.	Fill in the microplanning templates for each district with the information collected

from district representatives

c.	Identify distribution points and the number of staff needed for household registration and distribution

3.	Discuss the timeline of activities and the roles and responsibilities of all the actors in the campaign.

4.	Develop a plan to evaluate local warehouses.

5.	Identify the next steps required before implementation of the distribution campaign.

6.	Clean the microplans and prepare for validation.

7.	Develop a narrative report about the microplanning workshops and make recommendations to the national level.

Expected results

- Participants from provinces/regions and districts participating in the workshops will be well informed about the campaign and its timeline.

- Roles and responsibilities of all involved are well understood.

- District microplans are available and contain detailed mapping.

- Information about the logistics of the operation, including road transport situation, availability of means of transport, etc. is available and was used to develop the micro transport plans.

- Next steps to take in the campaign are identified.

Methodology

- Before microplanning begins, an official communication will be sent to every province/region, and district to invite participants to the microplanning workshop. The communication will include a list of information to be collected before the workshop.

- Central teams of facilitators will be trained for 3 days. Each team will comprise three people (one logistics, one communication and one technical/M&E).

- The central teams will run workshops (either at regional or at district level) where participants are from districts and communities, and where the information requested is provided.

- Each microplanning workshop will be of four days duration.

- At the end of the workshops, the central teams will work at national level to clean and finalize the microplans before they are sent for validation to the national level coordinating committee.

Participants

The central level facilitation team will come from national and provincial/regional level Ministry of Health and partner organizations. Staff with expertise in logistics, programme/monitoring and evaluation and communication will be selected.

At the field level, participants will be five District Health Management Team (DHMT) members per district, one health facility representative per health facility and five representatives of local government and community organizations.

Budget

Attach to these TORs the budget for the whole microplanning exercise (including the validation session) for review by the fiscal agent (if required).