MICROPLANNING WORKSHOP FOR ITN UNIVERSAL COVERAGE CAMPAIGN

General objective

To develop microplans for the ITN universal coverage campaign and ensure a comprehensive understanding of the campaign strategy, the microplanning objectives, the use of the maps and microplanning template to develop the microplans, the expected results from the microplanning workshops and the next steps for the implementation of the campaign.

Specific objectives

- To explain the ITN universal coverage campaign strategy, including the roles and responsibilities of involved actors

- To ensure that the final microplans include:

  - Detailed mapping of municipalities/administrative localities in each district for planning for the implementation of activities

  - A completely filled in microplanning template with the information collected in advance of the workshops and the information on the maps

  - The distribution points that have been selected (and/or pre-positioning sites) and the number of personnel required for a successful household registration and ITN distribution

  - A micro transport plan

- To discuss the timeline of activities and key milestones

- To identify the next steps for the implementation of the campaign

Day 1

| Time | Activity | Notes for facilitator |
| --- | --- | --- |
| 8:45 – 9:00 | Arrival of participants |  |
| 9:00 – 9:30 | Opening of the training - Welcome - Introduction of participants and facilitators - Identification of timekeeper and reporter) - Review of the objectives of the workshop and agenda - Ground rules - Administrative information |  |
| 9:30 – 10:00 | Presentation: Overview of the ITN universal coverage campaign - Objectives - Strategies - Roll out of the campaign - Planning for communication - Planning for logistics | Use the same presentation developed for the training of facilitators. Print out the presentation if there are expected problems with electricity for projection where the workshops will be taking place. |
| 10:00 – 10:15 | Question, answer and discussion |  |
| 10:15 – 10:45 | Coffee |  |
| 10:45 – 11:15 | Presentation: Roles et responsibilities of campaign actors - Explain the roles of the campaign actors for the planning and implementation of the universal coverage campaign - Explain the coordination structures and their terms of reference | Distribute photocopies of the description of roles and responsibilities and the terms of reference for the coordination structures (copy from the campaign plan of action) |
| 11:15 – 11:30 | Question, answer and discussion |  |
| 11:30 – 12:00 | Presentation: Introduction to microplanning - What is microplanning? - What are the objectives of microplanning? - How is microplanning organized? - What are the expected results from microplanning in each district? | Ask participants what the objective of microplanning is and note on flipchart paper. Use the same presentation developed for the training of facilitators. Print out the presentation if there are expected problems with electricity for projection where the workshops will be taking place. |
| 12:00 – 12:15 | Question, answer and discussion |  |
| 12:15 – 12:45 | Introduction to the mapping group work and establishing the map legend Examples of aspects for the map: - Roads, bridges, rivers, forests, mountains, other important topographical features - Health facilities, health posts, hospitals, etc. - Churches, mosques, markets, community or religious organizations, women’s groups, etc. - Communities, villages - Possible warehousing locations (used in the past, used by other programs) - Areas with specific barriers or risk for participation in the campaign (e.g. hard to reach areas) Establish the legend for the map for the group work | Ask participants what aspects to include on the map before completing the list. Establish the map legend that will be used by all of the groups for the mapping to ensure harmonization across maps (for example, a cross to represent a health facility). Participants should bring the maps found at the district and municipality/locality level to use as a base. It will be important to decide for the mapping whether the maps will be developed for each municipality/locality or for the entire district. The same question is relevant for the breakdown of the urban areas. For the group work, participants should add the details using the information collected in advance of the microplanning workshops. |
| 12:45 – 13:00 | Question, answer and discussion |  |
| 13:00 – 14:00 | Lunch |  |
| 14:00 – 16:00 | Group work – Mapping - The result will be a detailed map for the planning of the campaign (location of markets, schools, health facilities, rivers, poor roads, warehouses, churches, missing bridges, hard-to-reach populations, etc. | Supports required include: - Flipchart paper - Markers (many colours) - Scotch tape - Post-it notes |
| 16:00 – 16:30 | Coffee break |  |
| 16:30 – 17:30 | Group work – Mapping (continued) |  |
| 17:30 | End of day 1 |  |

Day 2

| Time | Activity | Notes for facilitator |
| --- | --- | --- |
| 8:45 – 9:00 | Arrival of participants |  |
| 9:00 – 10:30 | Group work – Mapping (continued) |  |
| 10:30 – 11:00 | Coffee break |  |
| 11:00 – 12:30 | Presentation – Review of microplanning template - Review of microplanning template for logistics/M&E and for communication, worksheet by worksheet and explain how the information collected prior to the workshops and the mapping should be used to complete the electronic template - Describe how the template will calculate the number of people / teams required for the household registration and the distribution of ITNs - Describe how the template will gather together the information needed for the micro storage and transport planning - Explain how the worksheets are linked with the budget | Introduction to the microplanning template and review of all the worksheets and how they are linked with the budget. Review the links between cells and explain how each element affects the others. |
| 12:30 – 13:00 | Question, answer and discussion |  |
| 13:00 – 14:00 | Lunch |  |
| 14:00 – 14:45 | Introduction to group work – Filling in the microplanning template - Using the maps, identify the distribution points (DP) and the villages that are linked to each DP (on the basis of distance between the villages and the DP and ensuring planning for outreach and mobile sites for hard-to-reach areas) - After identification of the DPs, use the population data to fill in the microplanning template | The participants should come to the workshops with a list of all of the villages or neighbourhoods, as well as the population for each one. The facilitator should demonstrate how to fill in the microplanning template through simulating the exercise for one distribution point to ensure that participants understand the process. The participants will fill in the microplanning template on the basis of the mapping and the population data. Reinforce that the mapping should be one of the reference points for making decisions about the location of distribution points, not just the population. |
| 14:45 – 15:00 | Question, answer and discussion |  |
| 15:00 – 16:00 | Group work – Filling in the microplanning template - The output will be a completely filled in microplanning template with the villages and their population grouped together by distribution point |  |
| 16:00 – 16:30 | Coffee break |  |
| 16:30 – 17:00 | Group work – Filling in the microplanning template (continued) |  |
| 17:00 – 17:15 | Discussion / Update on progress of groups |  |
| 17:15 | End of day 2 |  |

Day 3

| Time | Activity | Notes for facilitator |
| --- | --- | --- |
| 8:45 – 9:00 | Arrival of participants |  |
| 9:00 – 10:30 | Group work – Filling in the microplanning template (continued) |  |
| 10:30 – 11:00 | Coffee break |  |
| 11:00 – 13:00 | Group work – Filling in the microplanning template (continued) |  |
| 13:00 – 14:00 | Lunch |  |
| 14:00 – 16:00 | Group work – Filling in the microplanning template (continued) |  |
| 16:00 – 16:30 | Coffee break |  |
| 16:30 – 17:00 | Discussion / Update on progress of groups |  |
| 17:00 | End of day 3 |  |

Day 4

NOTE: For day 4, groups will work in parallel to maximize the time for the planning. A proposal is put forward in the agenda below but should be modified based on priorities.

| Time | Activity | Notes for facilitator |
| --- | --- | --- |
| 8:45 – 9:00 | Arrival of participants |  |
| 9:00 – 10:00 | Logistics – Presentation and introduction to group work: Development of micro storage and transport plans | Use the presentation developed for the training of facilitators to explain how to develop the micro storage and transport plans on the basis of the microplanning template and the mapping. |
| 9:00 – 10:00 | Communication – Plenary and discussion - In-depth planning for activities in support of advocacy, social mobilization and behaviour change communication | Key populations, effective channels, leaders to involve, etc. Establish the key milestones for the communication activities. |
| 9:00 – 10:00 | Monitoring and evaluation – Plenary and discussion - Data collection tools and data transmission circuit to identify potential bottlenecks in each district | Review of data collection tools and comments, review of the data circuit and potential problems for sending data / solutions proposed. |
| 10:00 – 10:30 | Question, answer and discussion by group |  |
| 10:30 – 11:00 | Coffee break |  |
| 11:00 – 13:00 | Group work: Development of micro storage and transport plans |  |
| 11:00 – 13:00 | Group work: Update of the risk assessment and mitigation plan for each district | Representatives for communication and M&E can begin work on the risk assessment and mitigation planning during the workshops for finalization at district level with the district coordination committee. The facilitators should share the template from the central level as an example. |
| 13:00 – 14:00 | Lunch |  |
| 14:00 – 15:00 | Group work: Development of micro storage and transport plans (continued) |  |
| 14:00 – 15:00 | Group work: Update of the risk assessment and mitigation plan for each district (continued) |  |
| 15:00 – 16:00 | Plenary: - Explain the next steps for (1) the cleaning of the microplans and (2) the validation of the microplans |  |
| 16:00 – 16:30 | Coffee break |  |
| 16:30 – 17:15 | Review of timeline and next steps |  |
| 17:15 – 17:30 | End of workshop |  |