## Instructions
100-day plan for an interim CFO (template)
Provided by nugrow GmbH (www.nugrow.de)
How it works
1. Sheet 'Plan': enter the engagement start date in the blue/yellow cell.
2. The due date per task is calculated from the day count (calendar days from start).
3. Set the status per task via the dropdown: Open, In progress, Done. Overdue tasks turn red.
4. The top shows progress per phase and overall.
Notes
The tasks are an example and must be adapted to situation, company and assignment. Days, owners and status are example values.
The template does not replace tax, legal or financial advice.
Questions? www.nugrow.de/en/kontakt

## Plan
100-day plan
Engagement start date | 2026-10-05
Today (leave empty = automatic)
Overall progress | 15.79% |  | Progress per phase
Overdue tasks | 0 |  | Days 1–30: Understand and secure | 37.5%
Total tasks | 19 |  | Days 31–60: Stabilise | 0%
|  |  | Days 61–100: Shape and hand over | 0%
# | Phase / Task | Day from start | Due date | Owner | Status | Overdue?
Days 1–30: Understand and secure
1 | Conversations with management, shareholders and team leads held | 5 | 2026-10-10 | Interim CFO | Done
2 | Access to bank, accounting, payroll and tax advisor set up | 3 | 2026-10-08 | Interim CFO | Done
3 | Balances, open items and payment obligations for the next 13 weeks captured | 10 | 2026-10-15 | Interim CFO | Done
4 | 13-week cash flow forecast set up | 14 | 2026-10-19 | Interim CFO | In progress
5 | Loan agreements, covenants and bank deadlines collected | 14 | 2026-10-19 | Interim CFO | In progress
6 | Status of the month-end close and open review points recorded | 21 | 2026-10-26 | Controlling | Open
7 | Contracts listed with deadlines and notice dates | 21 | 2026-10-26 | Finance lead | Open
8 | First assessment with priorities handed to management | 30 | 2026-11-04 | Interim CFO | Open
Days 31–60: Stabilise
9 | Weekly plan-versus-actual of cash introduced | 35 | 2026-11-09 | Controlling | Open
10 | Month-end close set up with a fixed calendar and owners | 40 | 2026-11-14 | Accounting | Open
11 | Receivables management and payment terms reviewed, measures defined | 45 | 2026-11-19 | Finance lead | Open
12 | Budget and forecast agreed with department heads | 50 | 2026-11-24 | Controlling | Open
13 | Approval rules for payments and contracts defined in writing | 50 | 2026-11-24 | Interim CFO | Open
14 | Reporting for shareholders and board agreed | 60 | 2026-12-04 | Interim CFO | Open
Days 61–100: Shape and hand over
15 | Metrics set with definitions agreed and reported for the first time | 70 | 2026-12-14 | Controlling | Open
16 | Finance team structure and staffing assessed, recommendation prepared | 80 | 2026-12-24 | Interim CFO | Open
17 | Systems and processes: gaps and priorities documented | 85 | 2026-12-29 | Finance lead | Open
18 | Handover documentation for successor or next step created | 95 | 2027-01-08 | Interim CFO | Open
19 | Closing conversation with management and shareholders held | 100 | 2027-01-13 | Interim CFO | Open
Note: example data (invented). Please adapt start date, tasks, days and owners.
Formulas:
Due date = B3+[Day from start]
Overdue? = IF(AND([Status]<>"Done",[Due date]<IF(B4="",TODAY(),B4)),"Yes","")