## Risk Barometer
|  | R A G Status | Comments / Detail | Actions required
NHS
High Impact | Contract Status for Investment from VCSE Alliance | a | agreed to renew to 31.03.2027 awaiting contract
| Structural Change to ICB | a | Initial cluster to 31.03.2027, then merger | Identify key contacts in new set up and build relationships
| Personnel Change at ICB | r | Directors appointed, other appointments awaited | currently seeking director level meetings
| Status of Local Improvement Finance Implementation | g | 5 of 7 areas currently approved, 2 outstanding
Medium Impact | Contract/Delivery Status for other NHS work | a | mixed contract lengths/prospects | commissioner agreements current
| LIO health staff - morale and turnover | a | very low morale with uncertainty of future contracts of ICB parnerships | monitoring closely and providing additional support where needed
| Personnel Change at Providers | g | staffing almost settled | LIO staff working to rebuild relationships
| Financial Status of Providers | g | current restructuring - outcomes unclear
LGR
High Impact | Status of core infrastructure contract from County Council | g | have made proposal to extended funding 31/07/2028 | Plan for alternative approach if rejected
| Political Status | r | May elections likely to bring changes to district county leadership | Plan to meet new Cabinet members ASAP, provide council staff with relevant information they need
| Structural Change in councils | a | consultation on competing proposals due in July 2026
Medium Impact | District Councils Contract Status | a | have made proposal to extended funding 31/03/2028 | Plan for alternative approach if rejected
| VCSE Grants Status | a | too early to judge
| Personnel Change |  | unknown currently
| Service Continuity/Disruption |  | unknown currently
Devolution
| Shadown Combined Authority live from 01.04.2026 | g
| Continue meeting with senior directors / CEO to build relationship and make case for working with VCFSE | a | Aim to get VCFSE representation of forming boards / decision making bodies | Prioritise meetings with combined authority
| Monitor local political progress | a
Partners
| Relationship with neighbouring LIO 1 | g | currently working well | meet regularly to plan and act together
| Relationship with neighbouring charity | a | some challenges as risk of competing for same funding | keep conversations going and seek collaborative opportunities
| Joint working in local authority area with another charity | g | reviewed joint project delivery Jan 2026, funding to 31.03.2027 | review June 2026, plan for next delivery phase