## Phase Timeline
Video Production Timeline — Editable Phase Table
Sparkhouse · thesparkhouse.com/blog/video-production-timeline · durations from Sparkhouse project actuals
Phase | What happens | 6-week | 8-week | 12-week | What the client owes us | What closes the phase
Kickoff & discovery | Align on audience, goal, deliverables, distribution, constraints, stakeholders, and approval process | 2-3 days | 3-5 days | 1 week | Clear brief, stakeholders, available brand/product information, known deadlines | Agreement on project direction and what the video needs to accomplish
Creative/concept | Develop and refine the core creative direction before detailed scripting or production planning | 3-4 days | 5-7 days | 1.5-2 weeks | Consolidated feedback and approval from decision-makers | Approved concept
Scripting | Turn the approved concept into the spoken and visual structure that will actually be produced | 4-5 days | 1 week | 2 weeks | Accurate messaging, factual/product input, feedback, approvals | Approved script
Pre-pro (casting, location, scheduling) | Build the shoot around the approved creative: talent, locations, crew, equipment, schedules, logistics, shot planning | 5-7 days | 1.5 weeks | 2 weeks | Talent/location approvals, availability, product/assets, logistical decisions | Locked production plan and confirmed shoot
Shoot day(s) | Capture the footage required by the approved script and production plan | 1 day | 1-2 days | 1-2 days | Required people/products/location access and timely on-set decisions where needed | Required footage captured
Assembly/first cut | Build the first complete version from the footage and approved structure | 4-5 days | 1 week | 1.5 weeks | Nothing until review unless missing assets or clarification is required | First cut delivered for review
Revisions | Address consolidated client feedback and refine structure, selects, pacing, messaging, and other approved changes | 3-5 days | 1 week | 2 weeks | Consolidated, actionable feedback submitted on time | Picture/content approval
Graphics/music/color | Finish visual polish after the structure is stable: graphics, animation as applicable, music, sound, color | 3-4 days | 1 week | 1.5 weeks | Final brand/legal checks and approval where applicable | Finishing approved
Final delivery + versions | Export approved master and required cutdowns, aspect ratios, platform versions, or other agreed deliverables | 1-2 days | 2-3 days | 3-5 days | Confirmation of final specs if not previously established | Final files delivered