## Slide 1: SUSTAINABLEIT.ORG
IT Sustainability Business Case Template

## Slide 2
Contents
Introduction
1
Sustainable IT value types, metrics, & examples
2
IT Sustainability Business Case Presentation Template
4
Business case content and sourcing guide
3

## Slide 3: Introduction: IT Sustainability Business Case Template
This presentation includes basic guidance for building business cases for investment in sustainable IT. The primary resource is a template for developing IT sustainability business cases. It consists of generic template pages, each followed by an example of that page populated with hypothetical information based on a fictional sustainability business case.
There are four different initiatives presented in the example: green IT infrastructure modernization; sustainable AI operations; a unified ESG data platform; and responsible IT procurement and lifecycle management. Although each project is assessed separately and compared, the recommendation is to green-light all four. Therefore, the implementation plan, governance framework, costs and ROI, and program at-a-glance pertain to all four as a single portfolio program.
Members of SustainableIT.org reviewed and vetted the business case template. Examples cited are hypothetical but representative and realistic. The PowerPoint business case template design was downloaded from SmartSheet.

## Slide 4: Sustainable IT value types, metrics, & examples – Part 1
Meta Type of Value | Specific Type of Value | Description | Expression of Value (Units) | Documented Value
Enterprise – Tangible (Financial) | Operating cost efficiency | Energy-efficient data centers, energy-efficient hardware, and hardware lifecycle extensions. | • % reduction in IT energy use • kWh/year avoided • metric tonne tCO₂e/year avoided • % reduction in infra OPEX/TCO | 20–40% reductions in data-center energy, plus ~20–25% reductions in the annualized carbon and cost tied to endpoint and server refresh.
 | Revenue growth & innovation | IT-enabled sustainable products and analytics create new markets or services. | Revenue growth (%), new product count | Products with sustainability attributes deliver 6–25% higher revenue. NYU Stern’s Sustainable Market Share Index finds that products marketed as sustainable grew 2.3× faster than conventionally marketed products and accounted for about 30% of CPG market growth.
 | Investor attraction & capital access | Transparent ESG reporting platforms build investor trust and credit rating advantages. | Cost of capital basis points, ESG fund inflows ($) | Strong ESG = lower risk, lower cost of capital. High-ESG firms’ borrowing costs can be 15% lower than low-ESG peers (e.g., ~7.0% vs 8.2% average cost of debt).
 | Compliance & reporting cost reduction | Automated ESG data systems reduce manual reporting time and audit expense. | Reporting cost ($), labor hours saved | A 2022 Forrester study showed 20–40% reductions in time spent on ESG reporting and about $75k in avoided manual reporting costs, plus $116k saved on audit support over three years. A 2025 report ESG teams saved 5,400 hours over three years by automating data collection and reporting.
 | Supply-chain resiliency | Digital-twin and traceability solutions prevent disruptions and shortages. | Avoided loss ($), disruption days avoided | A 2025 empirical study of Chinese listed firms finds that stronger ESG performance significantly improves supply-chain resilience, with ESG scores positively correlated with resilience indices even after controlling for firm characteristics. Thomson Reuters’ 2024 study on supply-chain resilience notes that companies integrating ESG into supplier selection are better able to mitigate trade and disruption risks, contributing to lower cost impacts when shocks occur.
Enterprise – Intangible | Brand equity & stakeholder trust | Demonstrated sustainability improves reputation and loyalty. | Brand equity %, NPS lift | PwC’s 2024 Voice of Consumer survey found that consumers are willing to pay on average 9.7% more for sustainably produced or sourced goods. A 2024 Simon-Kucher global study reports 54% of consumers willing to pay a premium for sustainable products (up from 35% in 2020).
 | Talent attraction & retention | Purpose-driven digital strategy strengthens employee engagement. | Turnover rate (%), engagement score | Deloitte and SHRM show that organizations with strong sustainability and purpose-driven cultures can see up to 50–55% lower employee turnover and higher engagement scores than peers.
 | Resiliency & adaptability | Diversified suppliers, climate-risk analytics, and remote-work enable continuity. | Uptime %, incident frequency | Multiple studies (Zhou 2021; Wu 2024; Li 2022) find that firms with stronger ESG performance experience significantly lower stock price volatility and smaller drawdowns during crises such as COVID-19 compared to low-ESG peers. Reliability-centered maintenance and modern monitoring have delivered O&M cost reductions of around 26% while improving uptime.

## Slide 5: Sustainable IT value types, metrics, & examples – Part 2
Meta Type of Value | Specific Type of Value | Description | Expression of Value (Units) | Documented Value
Enterprise – Negative Value Avoided | Regulatory non-compliance | Avoid fines, litigation, or delisting from poor ESG performance. | Avoided penalties ($), fines (#) | Recent enforcement actions for environmental and greenwashing-related cases frequently reach tens to hundreds of millions of dollars per case in fines and settlements.
 | Reputational & greenwashing risk | Transparent IT data systems prevent misinformation. | Crises avoided (#), media sentiment index | In 2025 ruling, TotalEnergies was told by a Paris court to pay €10,000 per day of delay for removing misleading ESG statements and a potential penalty of €20,000 per day for failing to publish the ruling. The company also had to pay €24,000 to three NGOs plus an additional €15,000 to cover their legal costs. In 2025 a German court imposed a €25 million fine on DWS (Deutsche Bank’s asset mgmt. arm), for misleading ESG marketing statements and exaggerated environmental credentials. DWS also had to pay a $19 million settlement to the U.S. SEC over similar ESG misrepresentation.
IT Function – Tangible (Financial) | IT asset lifecycle optimization | Extended device/server life, resale, and reuse lower capital outlay. | IT CapEx/OpEx savings ($), e-waste reduction (t) | TCO Certified reports that extending laptop life by 2 years can reduce lifecycle emissions by about 30%. French ADEME-cited that extending computer life from 2 to 4 years can cut its environmental footprint by 50%.
 | Cloud compute optimization | Migrating workloads to hyperscalers improves energy efficiency, reduces comparable costs and reduces carbon footprint. | Energy use (kWh), cost savings ($) | Accenture finds moving from on-prem to public cloud yields up to 65% reduction in energy consumption and 84% reduction in carbon emissions. Cloud TCO studies show cloud cost reductions of 20–30% from rightsizing, reserved instances, and workload scheduling
 | Responsible AI | Sustainable AI lifecycle management includes structured AI governance (clear roles, training, lifecycle gates, sustainability and ethics criteria, reusable platforms); carbon-aware computing, data proliferation management, model compression, and preference for small language models. | Compute hours, kWh saved | Organizations with responsible AI governance (clear roles, lifecycle gates, sustainability and ethics criteria, reusable platforms) show up-to-37% emission reductions, 60% reporting-cycle reductions, and 30–76% cost savings (as seen in SustainableIT RAI Award winners). Energy & carbon: Responsible AI governance that enforces efficiency practices (model compression, right-sizing, low-carbon regions) can cut per-inference or per-training-run energy use by 30–90% and halve emissions when combined with hyperscale / low-carbon infrastructure (Nature) Cooling & water: Governance that requires modern AI-optimized cooling designs and water-smart siting can deliver around 20% reductions in cooling energy and 50–70% water savings (Business Insider).
IT Function – Intangible | Digital literacy and AI ethics maturity | Training teams on sustainable AI and ESG governance raises risk awareness. | Training hours, maturity level | Responsible AI training increases trust and reduces bias incidents.

## Slide 6: Sustainable IT value types, metrics, & examples – Part 3
Meta Type of Value | Specific Type of Value | Description | Expression of Value (Units) | Documented Value
IT Function – Intangible | Digital literacy and AI ethics maturity | Training teams on sustainable AI and ESG governance raises risk awareness. | Training hours, maturity level | Responsible AI training increases trust and reduces bias incidents.
IT Function – Negative Value Avoided | Limiting unplanned outages and security breaches | Implementing modern, energy-efficient and resilient infrastructure (backup, DR, security monitoring) that reduces outage frequency and impact in trading, payments, and digital channels — including climate-driven and AI-driven load spikes. | Downtime hours, incidents avoided (#) | ESG-oriented risk studies show that firms with better ESG risk management experience fewer “catastrophic drawdowns” (50%+ equity losses (Sustainalytics). RAI governance lowers exposure to AI-related breaches, where the incremental cost per breach is measured in hundreds of thousands to millions of dollars on top of an already $4.4–6M average (IBM).
 | Mitigating resource scarcity and hardware dependency | Circular procurement reduces exposure to rare-earth supply risk. | Procurement risk index | Reduced supply-chain disruption risk from critical minerals shortages through reuse and remanufacture.

## Slide 7: Business case content and sourcing guide - Parts 1-3
Section | Purpose | Content to Provide | Information Sourcing
1. Executive Summary | Concisely state the rationale and value proposition for investment. Include vision, strategic objective, purpose of the business case (generally, questions the case will answer), and business case sponsor. | • One-paragraph overview of the business challenge and proposed IT sustainability initiatives • Summary of expected financial ROI (e.g., cost savings, payback, IRR) • Headline ESG benefits (carbon reduction, social impact, governance improvement) • Key recommendation to leadership for investment approval | • Use prior-year financial reports and IT cost-of-ownership models • Reference enterprise ESG scorecards and annual reports for macro targets • Align figures with the finance team’s ROI templates
2. Problem Statement/ Opportunity Statement | Define the business, operational, or regulatory issue being solved and the opportunity to be realized. | • Describe current IT sustainability gaps (e.g., inefficient infrastructure, fragmented ESG data, lack of AI governance) • Quantify baseline issues: energy cost, emissions, or compliance risks • Summarize market/regulatory pressures (CSRD, SEC Climate Rule, etc.) • Clarify the opportunity for IT to drive enterprise ESG performance | • Pull Scope 1-3 emission data from CSO or Envizi/Net Zero cloud dashboards • Review IT energy bills, cloud usage metrics, and SEC/CSRD disclosure gaps • Benchmark against CDP or EcoVadis ratings
3. Proposed Initiatives | Outline the sustainability initiatives to be funded. | • Initiative title (e.g., Green Data Infrastructure, Sustainable AI, ESG Analytics Platform) • Stakeholders • Reference vendor LCAs and AI use-case assessments. • Objective: What this initiative achieves • Actions: Key implementation steps • Expected impacts: Tangible sustainability results (energy reduction %, data visibility, compliance readiness), and financial results • Costs • Requirements of stakeholders • ESG Link: Which pillar(s) it advances and how • Financial Link: Where it saves or generates money | • Gather from cross-functional workshops (CIO, CSO, CFO) • Use enterprise architecture and FinOps tools (ServiceNow, Flexera) to model energy and cost savings • Reference vendor LCAs and AI use-case assessments

## Slide 8: Business case content and sourcing guide – Parts 4-5
Section | Purpose | Content to Provide | Information Sourcing
4. Sustainability Impact Analysis (details of impact presented in Step 3) | Demonstrate measurable sustainability outcomes across all ESG pillars. | • Environmental: CO₂ reduction, energy savings, waste reduction, circularity, water impact • Social: Employee engagement, DEI improvements, community programs, supplier ethics, digital inclusion • Governance: ESG data accuracy, compliance, AI ethics, supplier transparency, board oversight, greater business resiliency • Provide expected KPIs and targets (quantified where possible) • Explain how IT enables enterprise-level ESG commitments | • Environmental data from cloud dashboards + LCA tools (Rejoose, Greenpixie, Sphera) • Social metrics from HR and supplier audits (RBA, EcoVadis) • Governance KPIs from ESG reporting software (Datamaran, SpheraCloud) • Resiliency metrics • Supply chain resiliency data from procurement systems with vendor risk modules • Business continuity and disaster recovery logs, IT incident reports, cloud provider resilience SLAs • CDP or WRI Aqueduct data for regional physical climate risk to facilities or data centers • Finance/operations logs for downtime cost per hour; ITSM data for mean time to recover
5. Financial Impact Analysis (details of impact presented in Step 3) | Present quantified economic value of the investment. | • Investment cost: total and by category (e.g., infrastructure upgrades, software licenses, staffing) • Hard-dollar benefits: cost reductions (energy, procurement, reporting), revenue gains, risk avoidance, lower cost of capital • Metrics: NPV, IRR, payback period, cumulative 3–5-year savings • Notes on assumptions and sensitivity (e.g., energy price, adoption rate) | • Source energy and cloud billing data from AWS Cost Explorer/Azure Monitor • Estimate carbon price using regional ETS rates • Use Excel or Power BI financial model linked to utility data and IT asset costs

## Slide 9: Business case content and sourcing guide – Parts 6-8
Section | Purpose | Content to Provide | Information Sourcing
6. Risk Analysis | Identify and mitigate potential delivery or business risks. | • List top 5–7 risks by category (financial, change management, technology, security, regulatory, reputational) • Rate by likelihood/impact • Mitigation measures and ownership • Include “risk of inaction” (e.g., regulatory fines, lost investor confidence) | • Extract from the enterprise risk register and internal audit findings • Leverage compliance dashboards (GRC tools, ISO audit logs)
7. Summary and Recommendation | Summarize the case for approval and recommend the best initiative alternatives, if any. | • Present on one page an initiative at a glance • Reinforce that sustainability and profitability are aligned • Restate financial and ESG returns in one paragraph • Emphasize leadership’s role (CIO + CSO + CFO partnership) • Explicit call to action: Approve investment and initiate implementation | •Validate numbers with finance and CSO teams • Reference enterprise ESG dashboard or sustainability scorecard
8. Implementation Roadmap | Define the 2-3-year plan to deliver and scale results. | • Year 1: Foundations, governance setup, baselines, quick wins • Year 2: Major system build-outs and deployments • Year 3: Optimization, integration into BAU (business-as-usual) • Milestones, KPIs, responsible teams, decision gates • Dependencies (e.g., cloud vendor agreements, sustainability team partnership) | • Use PMO systems (Jira, Smartsheet, ServiceNow Portfolio Management) • Integrate with IT strategy roadmaps and budget planning cycles

## Slide 10: Business case content and sourcing guide – Parts 9-10
Section | Purpose | Content to Provide | Information Sourcing
9. Governance | List the responsible parties and their contact information. | • The project manager is responsible for managing project implementation. • The project sponsor is accountable for ensuring the project is completed. • You may also describe the project team, review teams, and quality consultants. | 
10. Appendices (Optional) | Add supporting material. | • ESG KPI glossary • Emissions baseline methodology • Financial model summary table • Vendor selection criteria or scoring sheets • References and citations | • Pull from SustainableIT.org standards taxonomy and vendor LCAs • Include Excel baselines and carbon calculation outputs

## Slide 11
Title
Business Case
00/00/0000
v. 0.0.0
YOUR
LOGO
IT Sustainability Business Case Presentation Template

## Slide 12
Executive summary
Executive summary - Example
Problem/opportunity
Problem/opportunity - Example
Proposed IT sustainability Initiatives
Proposed IT sustainability Initiatives – Examples
Sustainability Impact Analysis – Example
Financial Impact Analysis
Risk analysis of initiatives
Risk analysis of initiatives - Examples
Risk comparison
Risk comparison - Examples
Comparison of initiatives
Comparison of initiatives - Example
Recommendation
Recommendation - Example
Implementation Plan
Implementation Plan - Example
Governance
Governance - Example
Summary
Summary – Example
Potential Appendices
Initiative at a glance
Contents

## Slide 13
VISION | Describe in one line the intended benefits of the proposed IT sustainability project.
STRATEGIC OBJECTIVE | Describe how your project contributes to the strategic sustainability and value objectives of the organization.
PURPOSE OF THE BUSINESS CASE | Describe what questions about the sustainability initiatives the business case will resolve.
BUSINESS CASE SPONSOR | Name the individuals, departments, or groups sponsoring the business case. Include stakeholders consulted for the business case – particularly sustainability, finance, compliance, other business functions.
EXECUTIVE SUMMARY

## Slide 14
VISION | Transform GFS’s IT function into a powerful engine for sustainable growth—cutting emissions, strengthening governance, and driving financial performance through modern, efficient, and responsible technology.
STRATEGIC OBJECTIVE | Implement an integrated Sustainable IT program that modernizes infrastructure, embeds responsible AI, unifies ESG data, and drives sustainable procurement to deliver a 50% emissions reduction, measurable cost savings, and full CSRD-ready transparency by Year 3.
PURPOSE OF THE BUSINESS CASE | For the proposed initiatives, this case will resolve: How to reduce the energy intensity and operating cost of our data centers while improving performance and resiliency. How to govern AI at scale in ways that minimize ESG risk and leverage its benefits. How to eliminate fragmented ESG data and move to a single, auditable source of truth. How to ensure suppliers meet environmental, ethical, and circularity standards that reduce our Scope 3 emissions
BUSINESS CASE SPONSOR | Chief sponsors are the CIO, CSO, and CFO. Secondary sponsors are the chief of procurement, chief risk officer, COO, chief data officer, and CTO (head of infrastructure.
EXECUTIVE SUMMARY - EXAMPLE

## Slide 15
PROBLEM STATEMENT (Define the business, operational, or regulatory issue being solved.) | Describe current IT sustainability gaps (e.g., inefficient infrastructure, fragmented ESG data, lack of AI governance). Quantify baseline issues: energy cost, emissions, or compliance risks. Summarize market/regulatory pressures (CSRD, SEC Climate Rule, etc.), including timing urgency. .
OPPORTUNITY STATEMENT (Define the business opportunity to be reaiized.) | Detail the opportunity (upside) for sustainability transformation in IT in terms of how it will help business achievement of sustainability goals, how it would drive hard and soft business value. Include competitive and market positioning. Include timing aspect of the opportunity.
PROBLEM | OPPORTUNITY

## Slide 16
PROBLEM STATEMENT (Define the business, operational, or regulatory issue being solved.) | Inefficient and carbon-intensive IT operations — legacy data centers (PUE 1.7) and low renewable energy use (19%) drive 3,500 tons of avoidable CO₂ and high energy costs. Fragmented and unreliable ESG data — sustainability metrics are scattered across systems, slowing reporting, increasing manual effort, and creating CSRD/CSDDD compliance and audit risks. Rapid growth of AI and compute demand — increasing workloads lack governance for energy use, ethical oversight, and carbon impact management. Unsustainable procurement and lifecycle practices — supplier ESG visibility is limited, refresh cycles are too short, and e-waste processes miss circularity, reuse, and value-recovery opportunities. Misalignment between IT and enterprise ESG goals — IT is not yet fully leveraged to reduce emissions, strengthen governance, support social commitments, or meet investor and regulatory expectations. .
OPPORTUNITY STATEMENT (Define the business opportunity to be reaiized.) | Cut IT emissions by 50% and reduce operating costs through AI-driven data center optimization, workload consolidation, and migration to renewable-powered cloud regions. Create a single, auditable ESG source of truth by unifying carbon, energy, procurement, and AI data into an automated platform that enables CSRD-ready reporting and real-time insights. Use AI to drive efficiency and sustainability gains, optimizing compute usage, predicting maintenance, reducing energy demand, and automating ESG data collection. Advance circular and responsible IT procurement by embedding ESG criteria into vendor selection, extending device lifecycles, reducing e-waste by 30%, and recovering asset value. Position IT as a strategic enabler of enterprise ESG goals by strengthening governance, boosting talent engagement, reducing regulatory and reputational risk, and enhancing investor confidence.
PROBLEM | OPPORTUNITY - EXAMPLE

## Slide 17
INITIATIVE X
INITIATIVE DESCRIPTION | OBJECTIVE | STAKEHOLDERS | ACTIONS | SUSTAINABILITY/VALUE LINK
Describe the essential aspects of the initiative or program | Primary goals | Who is most affected by the initiative, who is essential to its development, and who would own and maintain the initiative during development and after completion | Key implementation steps | Describe which corporate sustainability pillar or goal this initiative affects Describe which business financial or competitive goals the initiative affects
KEY FACTORS | 
Sustainability impact | Tangible results (energy/emissions/water reduction %, social impacts, data accuracy & visibility, compliance readiness)
Financial impact | Financial results (top- and bottom-line impacts, ROU, NPP, IRR, costs avoided)
Costs | Investment required -- Total and by category (e.g., infrastructure upgrades, software licenses, staffing)
Stakeholder requirements | What will be needed from stakeholders, including time and other resources, and expertise
Title – IT Sustainability Initiative X (copy page for multiple initiatives)

## Slide 18
INITIATIVE 1: Example - Green Data Infrastructure Optimization
INITIATIVE DESCRIPTION | OBJECTIVE | STAKEHOLDERS | ACTIONS | SUSTAINABILITY/VALUE LINK
Optimize on-premise data centers and accelerate migration to renewable-powered cloud platforms to significantly reduce energy use, carbon emissions, and IT operating costs. | Reduce data center energy use, emissions, and operating cost. | CIO/CTO/Head of Infrastructure Head of Cloud/FinOps Lead | Deploy AI-driven DCIM and cooling optimization (e.g., EkkoSense-style IoT sensors + ML). Decommission underutilized servers and consolidate facilities. Migrate high-compute and non-sensitive workloads to renewable-powered cloud regions. Modernize remaining on-prem facilities with efficient cooling/power systems. | Major impact on environmental footprint (energy/CO₂), improves governance through improved performance analytics. Hard-dollar OPEX savings; reduced capital refresh needs; lower risk costs.
Initiative 1: Green Data Infrastructure Optimization
KEY FACTORS | 
Sustainability impact | 20–30% facility energy reduction, totaling 3,000 tons CO₂ avoided annually
Financial impact | $0.4–0.6M annual electricity/cooling OPEX savings. Higher resiliency and reduced hardware failure rates.
Costs | 4–5M over three years for data center upgrades, sensors, DCIM software, cloud migration efforts, and infrastructure modernization.
Stakeholder requirements | Oversight of modernization plan, governance reviews, architectural approvals. Cloud planning, workload analysis, and cost-carbon optimization cycles.

## Slide 19
INITIATIVE 2: Example - Sustainable AI & Intelligent Operations
INITIATIVE DESCRIPTION | OBJECTIVE | STAKEHOLDERS | ACTIONS | SUSTAINABILITY/VALUE LINK
Embed responsible, energy-aware AI practices and deploy AI-driven optimization tools to reduce compute demand, automate ESG workflows, and ensure ethical, compliant AI operations. | Ensure AI drives ESG outcomes and is operated responsibly and efficiently. | Head of AI/AI Governance Lead CIO/CTO | Use AI/ML to optimize compute scheduling, workload placement, data center load balancing. Apply ML for predictive maintenance to reduce waste and avoid unnecessary replacements. Track AI workload carbon footprint and select renewable-powered GPU cloud regions. Enforce AI ethics, transparency, ISO 42001 alignment. | Supports E (energy efficiency), S (ethical use of AI), G (governance controls). Financial Link: Efficiency savings; reduced risk exposure; stronger compliance posture.
Initiative 2: Sustainable AI & Intelligent Operations
KEY FACTORS | 
Sustainability impact | 5–10% additional energy reduction; reduced risk of unethical AI outcomes and improved compliance
Financial impact | S100K+ annual savings
Costs | $2–3M total (platform licensing, engineering, integration, audit readiness)
Stakeholder requirements | Define sustainable AI standards, review models & optimize, oversee AI energy tracking, obtain AI ops tools, create governance committee; apply AI frameworks (ISO 42001), approve architecture model

## Slide 20
INITIATIVE 3: Example - Unified ESG Analytics & Data Platform
INITIATIVE DESCRIPTION | OBJECTIVE | STAKEHOLDERS | ACTIONS | SUSTAINABILITY/VALUE LINK
Implement an integrated ESG data platform that consolidates all sustainability metrics into a single, auditable source of truth enabling automated reporting, real-time insights, and CSRD-ready compliance. | Build unified ESG data system for high-accuracy, auditable reporting | Chief Sustainability Officer/ ESG Reporting Lead CIO/Chief Data Officer | Consolidate IT, supply chain, HR, and facility sustainability data into one platform. Automate GHG calculations, cloud carbon imports, sensor-fed facility metrics. Deliver dashboards, scenario modeling, and CSRD-aligned reports. | Strengthens governance, improves environmental reporting accuracy, supports social metrics tracking; improves company sustainability rating. Lower reporting cost; avoided regulatory penalties; stronger ESG ratings.
Initiative 3: Unified ESG Analytics & Data Platform
KEY FACTORS | 
Sustainability impact | 70% reduction in manual reporting time. Accelerates decision cycles and reduces rework, providing more accurate baselines for carbon, energy, and asset utilization—leading to better budgeting and improved ROI on sustainability initiatives.
Financial impact | $200K/year in avoided labor or contractor costs. Avoided noncompliance fines of $250K – $1M+ per violation, equaling $100-$200K in monetized risk avoidance (10% probability of event × cost of event). Identifies new efficiency opportunities across IT & operations, in $250K/year infrastructure cost savings. Total: $550-$650K.
Costs | $2–3M for ESG software licensing, data integration, dashboards, consulting, and audit readiness features.
Stakeholder requirements | Define reporting requirements, oversee CSRD readiness, validation cycles. Approve platform design, ensure data integration and governance standards.

## Slide 21
INITIATIVE 4: Example - Sustainable IT Procurement & Lifecycle Management
INITIATIVE DESCRIPTION | OBJECTIVE | STAKEHOLDERS | ACTIONS | SUSTAINABILITY/VALUE LINK
Transform IT procurement and asset lifecycle processes by enforcing supplier ESG standards, extending device lifespans, enabling circularity, and reducing Scope 3 emissions and hardware costs. | Reduce Scope 3 emissions and operational cost through ESG-embedded procurement. | Chief Procurement Officer/Procurement Sustainability Lead Head of IT Asset Management | Require suppliers to disclose carbon footprints, science-based targets, labor/waste practices. Integrate ESG scoring (EcoVadis/CDP) in all RFPs. Extend device refresh cycles by 1–2 years (20–33% lower lifecycle carbon). Formalize ITAD program for resale, donation, or certified recycling. | Circularity, supply-chain ethics, digital inclusion Reduced procurement cost, recovered residual value, lower risk
Initiative 4: Sustainable IT Procurement & Lifecycle Mgmt.
KEY FACTORS | 
Sustainability impact | 30% e-waste reduction; 15% reduction in Scope 3 IT supply chain emissions.
Financial impact | $300K annual cost savings from reduced hardware purchases; $200K+ in periodic resale value recovered.
Costs | $1–1.5M for supplier ESG scoring tools, ITAD partnerships, lifecycle optimization tooling, training, and program management
Stakeholder requirements | Update RFP criteria, score vendors, manage renewals with ESG factors. Oversee lifecycle extensions, refresh optimization, asset recovery programs.

## Slide 22
Sustainability Impact Analysis| EXAMPLE
IMPACT CATEGORIES | IMPACT EXPECTATIONS | PRIMARY KPIs
Environmental |  | 
Data center energy reduction: | 5 GWh annual energy reduction from optimized cooling, server utilization & clean-energy cloud. | Annual data center & cloud energy consumption (kWh/GWh)
Carbon reduction (Scope 1–3): | 3,000–3,500 tons CO₂ reduced per year via data center optimization & cloud migration 30% lower embodied carbon in hardware through circular ITAD | Year-over-year IT Scope 1–3 CO₂e emissions (tons)
Hardware lifecycle/circularity improvements: | 30% reduction in e-waste volumes through extended device lifecycles & certified recycling. | Average embodied carbon per device purchased (kg CO₂e/device)’ E-waste volume processed (kg or tons/year).
Social |  | 
Community device reuse/donation: | Community digital inclusion via 500+ donated/refurbished devices over 3 years. | Number devices deployed to communities (per year)
Supplier labor transparency improvements: | Stronger social standards alignment through ethical, fair-labor supplier requirements and diverse supplier preference. | % of suppliers meeting ethical labor and diversity compliance standards
Governance |  | 
CSRD assurance readiness improvements: | 70% reduction in manual ESG reporting effort through automated data collection & dashboards. | Time required per ESG reporting cycle (hours or days)
Strengthened ESG controls & audit trails: | Lower compliance & regulatory risk through reliable emission tracking, supplier due diligence, and AI ethics controls. Reduced likelihood of ESG misreporting or greenwashing risk through assured, high-quality data. | # of ESG reporting or audit exceptions identified per cycle; % of ESG data sources with automated validation & audit trails
Vendor ESG scoring, compliance, and risk monitoring: | Embedded ESG policy controls in procurement, AI governance, IT risk management & project gating. | % of IT & procurement projects complying with ESG controls.
Sustainability Impact Analysis – Example

## Slide 23
Financial Impact Analysis| INITIATIVE X
Investment Overview | Totals | Financial benefits (recurring) | Totals | Overall Financial Impact | Totals | ROI Metrics
Total program investment: |  | Operational savings: |  | Annual recurring financial benefit: |  | Payback period:
Initiative cost allocation: |  | Cloud & energy optimization savings: |  | 3–5 year total net benefit: |  | IRR:
Infrastructure modernization: |  | Lifecycle extension & ITAD value recovery: |  | Cost avoidance/risk reduction: |  | 5-year ROI:
Sustainable AI operations: |  | Reporting automation efficiencies: |  | Effect on cost of capital/ESG rating: |  | 
ESG analytics platform: |  |  |  |  |  | 
Responsible procurement & lifecycle: |  |  |  |  |  | 
Financial Impact Analysis

## Slide 24
RISK ANALYSIS | INITIATIVE X
 | RISK RATING & MITIGATION Rating= (Likelihood × Impact), adjusted for mitigation effectiveness |  |  |  | 
MAJOR RISKS | LIKELIHOOD (1-5) | IMPACT (1-5) | MITIGATION STRATECY | COST | RATING SCORE
List top 5–7 risks by category (financial, change management, technology, security, regulatory, reputational). Include “risk of inaction” (e.g., regulatory fines, lost investor confidence). |  |  | Measures to be taken, and ownership | Estimate of cost of mitigation strategies | X/25
Risk Analysis – Initiative X

## Slide 25
RISK ANALYSIS | EXAMPLE - Green Data Infrastructure Optimization
 | RISK RATING & MITIGATION Rating = (Likelihood × Impact), adjusted for mitigation effectiveness |  |  |  | 
MAJOR RISKS | LIKELIHOOD (1-5) | IMPACT (1-5) | MITIGATION STRATEGY | COST | RATING SCORE
Financial: Cost overruns or lower-than-expected savings | 3 | 4 | Conduct phased pilots before full rollout. Use conservative estimates for energy savings. Maintain monthly FinOps tracking and adjust workloads dynamically. | $75K–$150K consultants, monitoring tools, pilot work | 8/25
Change management: Resistance From Infrastructure Teams | 4 | 3 | Provide hands-on training for DC optimization tools. Highlight staff productivity gains from automation. Identify sustainability “champions” within teams. | $50K–$100K training, workshops, change mgmt. resources | 7/25
Technology risk: DCIM/AI tools fail to deliver expected gains | 3 | 5 | Run PoCs using limited zones or racks before full deployment. Select proven vendors with finance case studies. Include performance-based SLAs for energy/cooling optimization. | $120K–$250K pilot deployment, SLA structuring, architectural reviews | 9/25
Security risk: Increased attack surface from IoT sensors and new integrations | 3 | 4 | Enforce zero-trust segmentation for IoT devices. Ensure vendor solutions meet security standards. Continuous monitoring using SOC tools. | $150K–$300K security hardening, network segmenting, | 8/25
Regulatory & compliance risk: Poor data quality leading to misstated emissions | 2 | 5 | Implement automated data collection across energy, cloud, and IoT systems. Validate baselines through Sustainability/CSO teams. Enable audit trails and retain raw sensor data for verification. | $40K–$80K data validation tools, CSRD audit preparation | 6/25
Risk of inaction: Persisting inefficiencies, higher costs, and regulatory exposure | 4 | 5 | Approve and fund project; integrate DC optimization into IT strategy. Establish mandatory targets for reduction. Regular reporting to CIO/CSO steering committee. | $0 beyond funding the initiative | 12/25
Risk Analysis – Initiative 1

## Slide 26
RISK ANALYSIS | EXAMPLE - Sustainable AI & Intelligent Operations
 | RISK RATING & MITIGATION Rating = (Likelihood × Impact), adjusted for mitigation effectiveness |  |  |  | 
MAJOR RISKS | LIKELIHOOD (1-5) | IMPACT (1-5) | MITIGATION STRATEGY | COST | RATING SCORE
Financial: High compute costs from inefficient AI workloads | 4 | 4 | Implement model-optimization (quantization, pruning), workload scheduling, & cloud GPU rightsizing. Use FinOps dashboards to monitor AI compute cost drivers. | $75K–$150K tooling, ML engineering effort | 10/25
Change management: Resistance to new AI governance and efficiency controls | 4 | 3 | Provide training on responsible AI, model efficiency practices, and carbon-aware development. Establish AI “champions” in data science and engineering teams. | $40K–$80K training, workshops, governance sessions | 8/25
Technology risk: AI tools and automation pipelines underperform or fail to integrate | 3 | 5 | Pilot AI Ops tools (MLOps, AIOps, carbon telemetry) before full deployment. Select proven vendors with enterprise-scale references. Require performance-based SLAs. | $120K–$220K pilots & PoCs, integration, architecture validation, testing | 9/25
Security risk: Model, data, or pipeline vulnerabilities increase attack surface | 3 | 5 | Apply secure MLOps practices, model access controls, encrypted pipelines, and supply-chain checks on AI libraries. Conduct adversarial testing & integrate w/ SOC monitoring. | 150K–$300K (security assessments, tooling, testing) | 10/25
Regulatory & ethical risk: AI bias, non-transparency, or non-compliance with AI governance standards | 3 | 5 | Adopt ISO 42001-aligned responsible AI controls (bias audits, explainability testing, model documentation). Track AI energy usage for CSRD reporting. | $60K–$150K governance tooling, testing, policy dev. | 8/25
Risk of inaction: Continued reliance on spreadsheets causes compliance exposure and lost insights | 5 | 5 | Approve and deploy the platform; mandate it as the enterprise system of record. Integrate sustainability metrics with financial data early to avoid misaligned reporting. | $0 beyond funding the initiative | 15/25
Risk Analysis – Initiative 2

## Slide 27
RISK ANALYSIS | EXAMPLE - Unified ESG Analytics & Data Platform
 | RISK RATING & MITIGATION Rating = (Likelihood × Impact), adjusted for mitigation effectiveness |  |  |  | 
MAJOR RISKS | LIKELIHOOD (1-5) | IMPACT (1-5) | MITIGATION STRATEGY | COST | RATING SCORE
Financial: higher-than-expected cost of data integration and platform deployment | 3 | 4 | Use phased implementation, starting with GHG data and expanding to supply chain, HR, and cloud. Require fixed-fee proposals for integration and data engineering. Limit customization; use out-of-box modules. | $75K–$125K integration consultants, data engineering | 8/25
Change management: Low adoption of data entry, validation, or workflow changes | 4 | 3 | Conduct training for IT, Facilities, Procurement, and HR data owners. Create data stewardship roles & SLAs for data quality. Establish governance councils led jointly by IT + CSO. | $40K–$80K training, change management, documentation | 8/25
Technology & data quality risk: Platform integrations fail or data quality is insufficient for CSRD assurance | 3 | 5 | Start with automated data feeds for cloud carbon, energy meters, and procurement data. Apply strict data validation rules, audit trails, and automated error detection. Choose platforms with strong financial services references and proven CSRD readiness. | 120K–$200K integration layers, QA tools, engineering time | 9/25
Security risk: Centralizing ESG data increases exposure to unauthorized access | 3 | 4 | Enforce role-based access control (RBAC) and MFA. Encrypt data in transit & at rest; follow existing policies. Conduct regular penetration testing and third-party security assessments. | $100K–$200K security controls, assessments, monitoring tools | 7/25
Regulatory risk: CSRD/CSDDD reporting fails audit due to incomplete or inaccurate data | 2 | 5 | Map the platform to CSRD ESRS standards; include audit-ready traceability and version control. Involve Internal Audit and Sustainability in early design. Ensure full documentation of all calculations, emission factors, and data sources. | $60K–$120K audit readiness tools, external advisory support | 6/25
Risk of inaction: AI energy use grows unchecked, leading to higher emissions, higher costs, and regulatory exposure | 5 | 5 | Implement Sustainable AI standards as mandatory practice across all AI teams. Prioritize renewable-powered compute regions and energy-aware scheduling. | $0 beyond funding the initiative | 15/25
Risk Analysis – Initiative 3

## Slide 28
RISK ANALYSIS | EXAMPLE - Sustainable IT Procurement & Lifecycle Management
 | RISK RATING & MITIGATION Rating = (Likelihood × Impact), adjusted for mitigation effectiveness |  |  |  | 
MAJOR RISKS | LIKELIHOOD (1-5) | IMPACT (1-5) | MITIGATION STRATEGY | COST | RATING SCORE
Financial: Higher hardware costs or supplier price increases due to ESG requirements | 3 | 4 | Use TCO models to demonstrate lifecycle savings (energy efficiency, longer refresh). Negotiate multi-year pricing or bundled circularity commitments with vendors. Use competitive bidding to pressure pricing for ESG-compliant vendors. | $$30K–$75K procurement analysis, vendor negotiations, TCO modeling tools | 7/25
Change management: Resistance from procurement and ITAM teams to new ESG criteria | 4 | 3 | Provide staff training on ESG procurement scoring and circularity guidelines. Embed ESG scorecards directly into procurement workflows and RFP templates. Align performance KPIs w/ sustainability & lifecycle goals. | $40K–$80K training, new templates, workflow updates | 8/25
Technology risk: Poor integration of supplier ESG data into procurement systems | 3 | 4 | Integrate ESG scoring modules (EcoVadis/CDP) into the procurement system. Run pilots using a limited supplier subset before scaling. Use vendor-provided APIs and pre-built connectors to reduce failure points. | $80K–$150K integration, API configuration, data governance | 8/25
Security risk: Insufficient data wiping or chain-of-custody issues in ITAD program | 2 | 5 | Require certified ITAD vendors (R2v3, e-Stewards). Enforce strict chain-of-custody tracking, including serialized device auditing. Conduct quarterly audits of ITAD vendor processes. | $50K–$120K vendor audits, secure logistics, verification tools | 6/25
Regulatory & supply chain risk: Suppliers fail ESG requirements or provide incomplete data | 3 | 5 | Require suppliers to disclose Scope 1–3 data, certifications, and human-rights compliance. Integrate automated supplier risk monitoring into procurement. Include ESG clauses and termination rights in contracts. | $60K–$120K legal updates, risk modules, supplier assessments | 9/25
Risk of inaction: Rising Scope 3 emissions, higher costs, missing CSRD requirements for supply-chain transparency | 5 | 5 | Approve Initiative 4; embed ESG clauses in all IT vendor RFPs; mandate lifecycle KPIs. Consolidate vendors to those with strong ESG maturity and verified reporting. | $0 beyond funding the initiative | 15/25
Risk Analysis – Initiative 4

## Slide 29
COMPARISON OF INITIATIVES
CRITERIA | INITIATIVE 1 | INITIATIVE 2 | INITIATIVE 3 | INITIATIVE 4
BENEFITS |  |  |  | 
RELATIVE DISADVANTAGES |  |  |  | 
COSTS |  |  |  | 
RISKS |  |  |  | 
NOTES |  |  |  | 

## Slide 30
COMPARISON OF INITIATIVES - EXAMPLE
CRITERIA | INITIATIVE 1: Green Data Infrastructure | INITIATIVE 2: Sustainable AI | INITIATIVE 3: Unified ESG Platform | INITIATIVE 4: Sustainable Procurement & Lifecycle
BENEFITS | Reduces emissions by 50% & energy use by 20–30%. Cuts operational cost ($0.5M/year) through optimization & consolidation. Improves resilience, PUE, & workload efficiency. | Reduces AI-driven energy & compute cost by 5–10%. Improves model governance, transparency, & ethical compliance. Automates operational insights & reduces manual tuning effort. | Creates single source of truth for all ESG data (carbon, supply chain, HR, cloud). Reduces ESG reporting effort by 70%, saving $200K/year. Enables CSRD-ready audit trails & decision-making insights. | Reduces Scope 3 emissions by 15–30% through circular practices. Cuts hardware costs via extended refresh cycles & value recovery. Improves supply-chain due diligence & ESG compliance.
RELATIVE DISADVANTAGES | Physically complex; dependent on facilities & cloud migration timing. Requires substantial coordination between DC, cloud, & architecture teams. Benefits may take vs. software-only initiatives. | AI teams/users may resist constraints. Benefits depend on workload maturity & alignment with FinOps. Requires specialized AI/ML expertise to implement sustainably. | Integration complexity across multiple enterprise systems. Requires new data governance roles & processes. High dependency on cross-functional data owners for accuracy. | Supplier ESG maturity varies widely; data quality uneven. Requires sustained procurement behavior change. Benefits depend on vendor participation & contract integration.
COSTS | $4–5M across modernization, sensors, cloud transition, & optimization tooling. Moderate OPEX for monitoring & perf. tuning. Mitigation costs (pilots, engineering) included in initiative budget. | $1–1.5M for AI optimization tools, governance framework, & MLOps. Moderate ongoing OPEX for compute monitoring & governance operations. Mitigation expenses include pilots, QA, & SLA development. | $2–3M for licenses, integration, dashboards, & audit alignment. Ongoing annual license/support fees for ESG data systems. Mitigation includes validation tooling, audit prep, & data engineering. | $1–1.5M for ESG procurement modules, ITAD partnerships, lifecycle tools. Minor ongoing compliance monitoring & supplier scoring costs. Mitigation includes supplier assessments, audits, & workflows.
RISKS | Integration failure of DCIM or sensor systems. Cooling/thermal optimization underperformance. Inaction results in long-term cost and emissions lock-in. | GPU usage costs escalate rapidly without controls. Model lifecycle vulnerabilities increase security exposure. Highest risk of inaction due to unchecked AI workload growth. | CSRD/CSDDD audit failure from incomplete or inaccurate data. Integration or data quality issues reduce platform credibility. Risk of inaction creates severe compliance failures. | Supplier non-compliance or false ESG claims. ITAD chain-of-custody failures with high data exposure. Inaction drives rising Scope 3 exposure & CSRD penalties.
NOTES | Delivers largest carbon reduction of all initiatives. High visibility to leadership due to cost & impact. Foundations for Initiatives 2 and 3 (AI ops + ESG analytics data). | Strong synergy with ESG platform (Initiative 3). Requires modern cloud regions with reliable carbon telemetry. Governance maturity becomes competitive differentiator. | Central nervous system for all ESG initiatives. Supports investor, regulatory, and board transparency. Often yields savings beyond IT (procurement, facilities, operations). | Critical for supply-chain transparency under CSRD/CSDDD. Generates fast wins through refresh cycle adjustments. Strong alignment with community donation/reuse programs.

## Slide 31
RECOMMENDATION
RECOMMENDATION | Summarize the case for approval and recommend the best initiative option(s), if any. Reinforce that sustainability and profitability are aligned Emphasize leadership’s role (CIO + CSO + CFO partnership) Restate financial and ESG returns in one paragraph Explicit call to action: approve investment and initiate implementation

## Slide 32
RECOMMENDATION - EXAMPLE
RECOMMENDATION | We recommend approving and funding the full four-initiative Sustainable IT investment program as an integrated portfolio—beginning immediately with Green Infrastructure and the Unified ESG Platform, while simultaneously launching Sustainable AI and Responsible Procurement as parallel, lower-cost governance and process tracks—so the company can reduce emissions by 50%, lower operating costs, meet CSRD-level compliance expectations, and future-proof its AI and supply-chain capabilities. The initiatives are interdependent and deliver maximum value when executed together. The combined program mitigates the highest-severity enterprise risks. The integrated program offers strong, near-term financial ROI.

## Slide 33
PROJECT TITLE | Give the project a clear and descriptive name. Consider any naming conventions that your organization has, such as numbering formats.
OUTCOMES, DEPENDENCIES, AND KPIs | Using the information from the analysis section, describe the expected outcomes and deliverables, delivery dates, and criteria for measuring success. Also, identify who is accountable for achieving outcomes. Describe outcomes as new or modified sustainability benefits and tangible business value. Identify which customers will use the deliverable and gain the benefits. List dependencies (e.g., cloud vendor agreements, sustainability team partnership).
WORK PLAN | Describe how the project will be executed. Include the following: ● The high-level project phases ● The deliverables and target completion dates ● Cost to carry out the plan ● The personnel and expertise required
BUDGET | Provide a high-level project budget.
ADDITIONAL RESOURCES | Describe other resources required, such as equipment, human resources, or additional office or lab space.
IMPLEMENTATION PLAN

## Slide 34
PROJECT TITLE | Sustainable IT Modernization Portfolio (Initiatives 1–4)
OUTCOMES, DEPENDENCIES, AND KPIs | 50% reduction in IT emissions through infrastructure optimization, renewable cloud migration, and responsible AI usage. CSRD-ready, audit-grade ESG data via a unified analytics platform covering carbon, energy, procurement, cloud, HR, and AI. Lower IT operating costs ($1M+/yr) from cloud optimization, energy savings, extended hardware lifecycle, automated ESG reporting. Improved Scope 3 transparency with supplier ESG scoring, lifecycle KPIs, and certified ITAD workflow. Cloud vendor renewable-region support; facilities coordination; ESG taxonomy alignment; procurement supplier data; FinOps and ML engineering collaboration; Internal Audit partnership. PUE improvement; annual energy cost reduction; verified CO₂ reduction (tons/year). % of automated ESG data sources integrated; reporting cycle time reduction; CSRD assurance readiness. % AI workloads with energy/impact tracking; GPU cost reduction from optimization. % suppliers with ESG scorecards; % devices extended/reused/recovered.
WORK PLAN | Phase 1 (0–3 mo): Baselines, ESG taxonomy, requirements, platform selection, DC & AI readiness assessment. Phase 2 (3–9 mo): Deploy DCIM sensors, initial cloud migrations, pilot AI optimization, build ESG data integrations (carbon, cloud, energy). Phase 3 (9–18 mo): Infrastructure modernization, workload consolidation, AI governance rollout, supplier ESG scoring, Scope 3 integrations. Phase 4 (18–24 mo): Full CSRD dashboarding, audit-trail enablement, expanded AI automation, lifecycle optimization, steady-state monitoring. Deliverables: Energy/CO₂ baseline (Month 3); ESG data model & platform live (Month 6) DC cooling optimization + AI workload pilots (Month 9) Cloud migration waves + procurement ESG integration (Month 12–18) CSRD-ready reporting & steady-state dashboards (Month 18–24)
BUDGET | $8–11M over 24 months. Infrastructure modernization & cloud migration: $4–5M. ESG platform & data integration: $2–3M. Sustainable AI tooling & governance: $1–1.5M. Responsible procurement & lifecycle programs: $1–1.5M. Offsetting annual benefits: $1–1.3M/year savings, risk avoidance, & improved ESG ratings.
ADDITIONAL RESOURCES | IoT/DCIM sensors, cloud migration staging environments, ESG data warehouse capacity. ITAD-certified logistics support; supplier ESG data feeds (EcoVadis/CDP). Short-term contractors for data engineering, integration, and carbon accounting. Training for AI governance, procurement ESG scoring, and ESG reporting workflows. Facilities and energy-management coordination for modernization and renewable sourcing.
IMPLEMENTATION PLAN - EXAMPLE

## Slide 35
PROJECT MANAGEMENT FRAMEWORK | GOVERNANCE
Governance
List the responsible parties and their contact information.
The project manager is responsible for managing project implementation.
The project sponsor is accountable for ensuring the project is completed.
You may also describe your project team, review teams, and quality consultants.
PARTY RESPONSIBLE | ROLE | CONTACT INFORMATION

## Slide 36
GOVERNANCE - EXAMPLE
Governance - EXAMPLE
PARTY RESPONSIBLE | ROLE | CONTACT INFORMATION
CIO | Executive Program Sponsor | 
CSO, CFO | Co-sponsors | 
Project manager | Day-to-day execution: Directs all initiative workstreams (Infrastructure, ESG Platform, AI Ops, Procurement). Maintains schedule, budget, risks, and reporting cadence. Facilitates Steering Committee meetings and stakeholder alignment. | 
Project team (core delivery group) | Infrastructure Engineering & Cloud Architecture Team ESG Data & Integration Engineering Team AI Governance & ML Engineering Team Procurement ESG & Lifecycle Management Team Sustainability Reporting & Carbon Accounting Team FinOps & Finance Analysts | 
Review Team (oversight and assurance | Steering Committee (Monthly): CIO (chair), CSO, CFO, CTO, CDO, CPO Internal Audit Review (Quarterly): CSRD readiness, data assurance, controls validation Finance Review (Quarterly): ROI tracking, realized savings, cost-to-date Sustainability Review (Bi-monthly): ESG metrics, CO₂ progress, Scope 3 visibility | 
Quality and compliance consultants | External ESG reporting advisor (CSRD / assurance alignment) Cloud optimization & DCIM performance consultant Responsible AI governance advisor (ISO 42001 readiness) Supplier ESG rating provider (EcoVadis/CDP) | 
Subject matter experts | Data center engineering; cloud architecture; facilities energy; sustainable ai & intelligent operations ML engineering; ai governance; FinOps, ESG data architecture; carbon accounting; data quality & controls Supplier ESG; IT asset management; circularity | 

## Slide 37
SUMMARY
Summary
  Summary of Business Case
  Closing Statements

## Slide 38
SUMMARY
Summary
  This portfolio program delivers a unified strategy that modernizes infrastructure, embeds responsible AI, integrates audit-grade ESG reporting, and transforms procurement to extend device lifecycles and reduce Scope 3 emissions—cutting IT’s carbon footprint by 50%, lowering operating costs by $1M+ annually, ensuring CSRD-ready compliance, and positioning IT as a strategic enabler of enterprise sustainability, resilience, and financial performance.
  By approving this integrated four-initiative portfolio, the organization enables IT to accelerate decarbonization, strengthen regulatory compliance, reduce long-term operating costs, improve supplier transparency, and establish a modern, responsible foundation for cloud, AI, and ESG reporting—delivering immediate value, mitigating rising risks, and future-proofing the enterprise for the next decade.

## Slide 39
SUMMARY
Potential Appendices
  Initiative at a glance (see next page)
  ESG terms and KPI glossary
  Emissions baseline methodology
  Financial model summary table
  Vendor selection criteria or scoring sheets
  References and citations

## Slide 40
Initiative at a Glance
Overview
Text, bullets
Total Cost
Text
Financial Benefits
Text
Sustainability Benefits
Text. bullets
Time Frame
START DATE:
END DATE:
ROI
Payback period:
IRR:
Cumulative 5-year net benefit:

## Slide 41
Initiative at a Glance
Overview
The Sustainable IT Modernization & ESG Compliance Enablement Program Phase 1 consists of optimization of on-premise data centers and accelerated migration to renewable-powered cloud platforms to significantly reduce energy use, carbon emissions, and IT operating costs.
Total Cost
$4M green infrastructure optimization.
Financial Benefits
$600–800K energy and cloud optimization savings.
Sustainability Benefits
20–30% facility energy reduction, totaling 3,000 tons CO₂ avoided annually.​
20–30% reduction in IT-related CO₂ emissions through data center optimization, thermal improvements, workload consolidation, and renewable-powered cloud migration.​
15–30% reduction in Scope 3 IT emissions through extended device lifecycles, reuse/refurbishment, and responsible procurement.
Time Frame
START DATE: 01/01/2026
END DATE: 12/31/2028
ROI
Payback period: 5-6 years
IRR: 8%–15%
Cumulative 5-year net benefit: Positive, driven by recurring savings, substantial risk avoidance, and compliance assurance.​

## Slide 42
Contact
Steve Rovniak | Vice President
& WhatsApp +1 617.970.7720
Steve.Rovniak@sustainableIT.org
Advancing Global Sustainability through Technology Leadership
Notes: clean up