## Lessons Learned Register
| Lessons Learned Register: [Insert Organisation Name] - [Insert Project Name] |  |  |  | Prepared By: [insert] Date Prepared: [insert]
No | Category | Event | Impact (Positive / Negative) | Impact (Description) | Lessons Learned | Action Items
01
02
03
04
05
06
07
08
09
10

## Lessons Learned - Example
| Lessons Learned Register: Project Management Planet - Launch of a New App |  |  |  | Prepared By: J Smith Date Prepared: S Jones
No | Category | Event | Impact (Positive / Negative) | Impact (Description) | Lessons Learned | Action Items
01 | Communication | Project team experienced delays due to unclear communication between departments. | Negative | Moderate project delay (1 week) | Clear, consistent communication is critical between stakeholders and delivery teams. | Implement a weekly cross-department stand-up and a shared project status board.
02 | Planning | Early involvement of the finance team during the budgeting phase resulted in accurate cost forecasting. | Positive | Avoided budget overruns and improved stakeholder confidence | Involving key departments early leads to better forecasting and planning accuracy. | Make finance and procurement engagement a standard part of the project initiation phase.
03 | Risk Management | A key supplier went out of business, and there was no contingency plan. | Negative | Major delivery delay and increased cost | High-risk suppliers must have contingency plans. | Update risk register to include supplier continuity; establish alternative vendors.
04 | Scheduling | Tasks were underestimated during the planning phase, leading to timeline slippage. | Negative | Project extended by 2 weeks | Include buffer time and use historical data to improve time estimation. | Conduct planning workshops and use past project data to refine time estimates.
05 | Quality Control | Initial product version failed QA due to incomplete testing criteria. | Negative | Increased rework and costs | QA testing must be based on comprehensive acceptance criteria. | Enhance QA checklist and involve QA team earlier in requirements gathering.
06 | Stakeholder Engagement | Key stakeholder was not consulted early, leading to late-stage changes. | Negative | Scope creep and rework | Stakeholders must be identified and engaged from the beginning. | Update stakeholder analysis matrix; involve all relevant parties during planning.
07 | Process Improvement | Implementing agile sprints and regular retrospectives improved workflow transparency and adaptability. | Positive | Improved team morale and delivery consistency | Agile methodologies enhance adaptability and team engagement. | Adopt agile practices as standard for future projects; provide agile training to new team members.
08
09
10