SHIM

Sprint Checklist

A 4–5 week process for identifying the right Tracks, prioritizing them, and defining a practical path to production.

# What a SHIM Sprint Is

A SHIM Sprint helps an organization identify the workflows that matter most, determine where SHIM is the right fit, and define the best first path into production.

The goal is not to generate ideas in the abstract. The goal is to leave with:

- a clear view of the highest-impact opportunities,

- a prioritized set of candidate Tracks,

- and a practical set of options for what to do next.

# Before the Sprint Starts

## Establish the Core Team

- Identify the executive sponsor

- Identify the SHIM lead

- Identify 6–10 AI champions across key departments

- Confirm the working team for the sprint

## Gather the Starting Context

- Collect the org chart

- Identify major departments and business functions

- Confirm the overall business goals for the effort

- Share the AI Champion Survey

## Prepare the Sprint

- Set the sprint calendar

- Schedule the stakeholder workshops

- Confirm the midpoint checkpoint

- Confirm the final readout date

Output: Sprint plan, AI champions list, and survey responses in progress

# Weeks 1–2: Discover the Work

## Understand the Current State

- Review recurring workflows across the business

- Understand who does the work, where it happens, and what systems are involved

- Identify major handoffs, bottlenecks, and exception patterns

- Surface workflows that are high effort, high volume, or operationally important

## Separate the Opportunity Types

As discovery progresses, bucket opportunities into:

- TransformWork opportunities — Workflows that could benefit from a custom workflow interface and iterative AI modernization

- Off-the-shelf quick wins — Existing tools that may solve part of the problem immediately

- Standalone AI opportunities — Opportunities that may not require workflow transformation but still create value

Output: First-pass Track Inventory

# Midpoint Checkpoint

## Align on Where the Opportunity Is

- Review what was learned in the first workshops

- Share the early opportunity buckets

- Confirm which workflows matter most to the business

- Pressure-test where SHIM is the best fit

- Narrow toward the strongest first Tracks

The midpoint is not the final recommendation. It is a checkpoint to confirm direction before deeper scoping begins.

Output: Prioritized shortlist of Tracks and opportunity areas

# Weeks 3–4: Scope the Path Forward

## Turn Priorities into Options

- Validate technical feasibility

- Understand system access and integration realities

- Explore what a pilot could look like

- Develop rough business cases

- Compare candidate Tracks

- Build multiple paths forward

A strong SHIM Sprint should present options, not a single yes/no proposal.

Output: Recommended pilot path and investable options

# Final Readout

## What a Successful SHIM Sprint Delivers

At the end of the sprint, the client should have:

- a clear understanding of the company’s most important workflows,

- a view of which workflows are best suited for SHIM,

- a prioritized set of initial Tracks,

- and a recommended path to production with multiple options.

## What Happens Next

The most common next step is a production pilot focused on one or more Tracks:

- build the custom workflow interface,

- connect it to the existing systems of record,

- and begin the SHIM Loop in production.

Rule of thumb

A SHIM Sprint is successful when it creates the clarity and confidence needed to move into production work.