## Checklist
Job Closeout Checklist
Job name |  | Job no. |  | PM
Substantial completion |  | Days to close |  | Target close
Progress | 0 of 28 complete, 28 open, 0 past due | Days left
Section | Item | Responsible | Due date | Status | Date done | Evidence / link | Notes
1. Work done and accepted | Punch list is complete and signed off by the owner or architect. | PM
1. Work done and accepted | Certificate of substantial completion is signed and the date recorded. This date starts the warranty and lien clocks. | PM
1. Work done and accepted | Final inspections are passed and the certificate of occupancy is issued. | PM
1. Work done and accepted | Required testing, startup, commissioning, and owner training are complete and documented (TAB, fire alarm, sprinkler, HVAC startup, controls, electrical testing). Mark N/A if the job had none. | PM
1. Work done and accepted | Required O&M manuals, as-builts, warranties, spare parts, attic stock, keys, training records, and other contract closeout deliverables have been accepted by the owner or architect. Accepted, not just sent. | PM
1. Work done and accepted | Final completion is formally accepted by the owner, and the architect's or engineer's final certificate is issued where the contract requires one. A certificate of occupancy is not contract acceptance. | PM
1. Work done and accepted | Job is fully demobilized: rentals called off rent, trailer gone, dumpsters pulled, temp utilities shut off or transferred. This is where small shops lose the most money after a job ends. | PM
2. Revenue is final | Every change order and claim has a final disposition: signed, withdrawn, rejected, or carried as a documented claim with a dollar amount and an owner-approved plan. Nothing is left sitting in pending. An open claim does not keep the job open, but it does get written down. | PM
2. Revenue is final | Contract value in the accounting system matches the signed contract plus executed change orders. | Controller
2. Revenue is final | Final pay application is billed, including retainage. | PM
2. Revenue is final | Billing reconciliation: final contract value minus total billings equals zero, except for specifically documented unbilled amounts. | Controller
2. Revenue is final | AR reconciliation: total billings minus cash received equals remaining AR and retainage. The balance has a responsible person and an expected collection date. | Controller
2. Revenue is final | Final lien waiver is delivered to the project owner, plus consent of surety if the job is bonded. | Controller
3. Costs are all in | PM certifies in writing/via email that no additional job cost is expected, other than identified warranty cost or specifically listed accruals. | PM
3. Costs are all in | Commitment report is reviewed. Every subcontract and PO is reconciled to final invoices and closed, or the remaining balance is supported by a documented accrual. Committed cost minus invoiced cost equals zero except for explained accruals. | Controller
3. Costs are all in | Backcharges are issued and agreed before the final sub payment goes out. | PM
3. Costs are all in | Final sub payment and retainage are not released until the final unconditional waiver, closeout documents, warranties, and any other contract closeout requirements are received. | Controller
3. Costs are all in | Final payroll, credit card charges, and equipment charges are posted. | Controller
3. Costs are all in | Known but uninvoiced items are accrued. The bond premium true-up is the usual one. | Controller
4. Books are closed | Estimated cost to complete is zero, revenue recognition is final, and any over- or underbilling balance is resolved. | Controller
4. Books are closed | Warranty work from here on goes to a warranty job or GL account. The job does not get reopened. | Controller
4. Books are closed | Warranty expiration date is on the calendar, and sub warranty contacts are saved. | PM
4. Books are closed | Contract, change orders, subcontracts, lien waivers, COIs, and closeout documents are in one archive folder. | Controller
5. Owner sign-off and close | Open exposures are listed and each one has a decision: unresolved claims, backcharges, disputes, injuries, insurance matters, liquidated damages, warranty disputes, threatened litigation. These do not have to stop the close, but each needs an amount, a person, and a next step. | Owner
5. Owner sign-off and close | Final margin is compared to the original estimate, and any large variances are explained (owner and PM, 15 minutes). | Owner
5. Owner sign-off and close | Two or three lessons are written down: what the estimate missed, and which subs to use again or avoid. | Owner
5. Owner sign-off and close | Owner approves closing the job. | Owner
5. Owner sign-off and close | Job status is set to closed in the accounting system so nothing else can be coded to it. Not before the owner has approved. | Controller
Note on D4: Target from the ground rules: close within 90 days of substantial completion. Change it here if you want a different target.

## How to use
How to use this checklist
Ground rules
- Start this checklist at substantial completion, not when the job feels done. Target: closed within 90 days.
- Any job over 95% complete with no cost activity for 60 days goes on the closeout list automatically.
- Review all open closeout checklists once a month, in the same sitting as the WIP review.
- If the remaining costs are known and small (under $2,500), accrue them and close. Don't hold a job open over a $400 invoice.
- An open claim or dispute does not have to keep the job open. It has to be written down with an amount, a person, and a next step.
- The bookkeeper does not mark a job closed in the system until the owner has approved it (last two items on the list).
Filling it in
- The yellow cells at the top of the Checklist tab are the job details. Fill those in first.
- When the checklist is started, give every item a Due date. A due date that passes while the item is still open turns red, and the Progress line counts it as past due.
- When an item is finished, set Status to Done (or N/A), enter Date done, and fill in Evidence / link. Blank status counts as open.
- Evidence / link is the proof, not a description of the work. Paste a link to the file or folder, or name the document: signed change order log, final pay app, waiver PDF, owner acceptance letter, PM's no-more-cost email, commitment report, final WIP.
- If there is no evidence to point to, the item is not done.
- Target close, Days left, and Progress are formulas. Don't type over them.
- Finished items turn gray. Use the filter arrows on the header row to show only open items or only one person's items.
Example of a completed row
Responsible: PM Due date: 9/18/2026 Status: Done Date done: 9/14/2026 Evidence / link: Punch list signed by architect, PDF in job folder > Closeout Notes: Two items accepted as-is per owner email 9/12.
One job per tab
- Right-click the Checklist tab, choose Move or Copy, tick Create a copy, and rename the new tab with the job number.
- Or keep a blank copy of this file and save one file per job. Either works. Pick one and stick with it.
Changing the list
- To add an item, insert a row inside the list, type the section name exactly as it appears on the rows around it, and fill in Item and Responsible. The progress count picks it up.
- To drop an item for good, delete the row. If it just doesn't apply to one job, mark it N/A instead.
- Responsible is a dropdown, but you can type a person's name over it.