## Mobilization
Cluster2 Airports
WP25007-JAZAN Airport
PROJECT MOBILIZATION CHECKLIST- Facility Management Service Provider (and all sub-contractors)
Item no. |  | Description
Mobilization Activities - Oversight
0 | 1 | Develop and submit meetings format/agenda/documentation/schedule requirements
| 2 | Develop Trackers around primary requirements, with weekly submission=>key aspects of the mobilsation (manpower/vehicles and specialty equipment)
| 3 | Develop Document delivery requirement as milestones
| 4 | Develop risk and mitigation process for potential late delivery of requirements
| 5 | Develop and implement submision and follow up process for document submission
| 6 | Implement escalation process (internal and external)
| 7 | Engagement of mobilisation team resource requirements (manpower/computers/printers/comms devices
| 8 | Contract and deliverables review
| 9 | Document Systems Implementation (ISO/Contractual deliverables/Mobilisation/Technical Library)
Mobilization Plan with Main Milestones and Deliverables (shall include but not limited to)
1 | 10 | Detailed Mobilization & transition plan with main milestones and deliverables.
| 11 | Develop and deploy mobilization requirements and resources
| 12 | Mobilization & transition plan with main milestones and deliverables.
| 13 | Mobilization chronogram (Gannt chart with resource allocations) with detailed time frame & duration.
| 14 | The description of mobilization activities including related safety measures.
| 15 | The staff deployment plan by Airport/area/block and systems with planned time frame.
| 16 | Systems and equipment list showing (installation date, operational dates, operational status and quantities)
| 17 | List of all Permits required for the operation (for manpower, vehicles, spare parts, tools & equipment … etc.) showing (current status if available, quantity, types, expiration date if available, … etc.)
| 18 | List of all Tools required to execute the needed services mentioning delivery date onsite for each one (copy of PO to show the delivery date for not available one)
| 19 | List of all equipment/Vehicles required to execute the needed services mentioning delivery date onsite for each one (copy of PO to show the delivery date for not available one)
| 20 | Spares and consumables takeover.
| 21 | Asset condition Assessment.
| 22 | Snag list
| 23 | Mobilization team and their roles & responsibility matrix.
| 24 | List of all insurance policies with validity dates and signed policies copies.
| 25 | GACA certificates required within the scope, and / or compliance of GACA requirements
Mobilize Subcontracted Services Plan Details (shall include but not limited to)
2 | 26 | Subcontractor Pre-Approval Documents & Forms
| 27 | Subcontracts Management Plan.
| 28 | Audit plan on subcontractors compliance to contractual obligations & deliverables.
| 29 | Subcontractors’ tracker sheet (including name, start - end dates, scope of work )
| 30 | Signed contracts copy with sub-contractors including not limited to (Terms and conditions, Scope of work, SLA, Expiration date)
| 31 | Handover checklist and handover form for all handed over systems, areas and services .
Risk and Safety Management Plans (shall include but not limited to)
3 | 32 | Risk Identification.
| 33 | Risk Assessment
| 34 | Risk response plan.
| 35 | Risk Monitoring and Reporting.
| 36 | Risk Assessment form
| 37 | Risk Register template
| 38 | Contingency Plans
| 39 | Business Continuity Plans
| 40 | ISO45001 implementation
| 41 | Safatey Management Plan
| 42 | Aerodrome Ssfety Plan
| 43 | Traffic Management Plan
| 44 | Aerodrome Safety Closure Plan
| 45 | Induction and Safety Training
Facility Management Strategy/Plan (shall include but not limited to)
4 | 46 | Service Delivery Plans-Detailed and summary
| 47 | Maintenance Strategies
| 48 | Preliminary maintenance schedules and activities take-over plan.
| 49 | Preliminary maintenance schedules and activities take-over plan.
| 50 | Master PPM plan and Detailed Job plan.
| 51 | O&M Manuals & As Built Drawings.
| 52 | Daily Inspection Plan and Procedures.
| 53 | Build a full and complete set of standardized documents to cover all guidelines, methods, checklists, procedures, and schedules to execute the Maintenance services.
| 54 | Preventive, Corrective and Reactive Maintenance procedures.
| 55 | Equipment / machine Maintenance Plan.
| 56 | Calibration master plan.
| 57 | List of Tools and Equipment with the expiration date of calibration certificate if needed.
| 58 | CM and PM Historical data and Top 10 faults.
| 59 | Third Party inspection plan / tracker and a copy of the latest certificates issued.
Operation Management Plan (shall include but not limited to)
5 | 60 | Service Delivery Plan.
| 61 | Standard Operations Procedures (SOPs) and Method of Statement for all activities.
| 62 | The operation, Process Failure Mode, and Effects Analysis.
| 63 | Organization chart to show the internal structure of the company and the project team showing all the details like Management structure, employees names, positions, numbers ... etc.
| 64 | Manpower list and operational dates and numbers and related documents
| 65 | CV’s for supervisors position and above, for interview and client approval.
| 66 | Human Resources / Recruitment Plan.
| 67 | Manpower Distribution Plan (including Monitoring and Dispatch Team, TOC, EOC … etc.)
| 68 | list of Offices, spaces and Accommodations (available Vs required table, specification, location, numbers, etc.)
| 69 | Staff Accommodation and Transportation management plan.
| 70 | Airside Driving License list.
| 71 | Build a full and complete set of standardized documents to cover all guidelines, methods, checklists, procedures, incident reports & register and schedules to execute the O&M services.
| 72 | Document Control center to finalize archiving system for the technical Library including soft & hard archiving
Quality Assurance System (shall include but not limited to)
6 | 73 | QA / QC manual to include all quality activities, policies, regulations and standard.
| 74 | Procedures to ensure the monitoring and continuing compliance of the service and subcontracted services for GACA and ISO standards
| 75 | Business Continuity Plan.
| 76 | Contingency Plan.
| 77 | Communication plan & Escalation plan.
| 78 | Comprehensive Training Program including Materials/Subject.
| 79 | Audit program for all contractor's scope of work (External Audit program is required for the subcontractors) and internal audit for the internal team.
| 80 | Client satisfaction program
| 81 | Certification validity tracking system
CAFM and Asset Management Plan (shall include but not limited to)
7 | 82 | CAFM system requirements and criteria (subject to Contracting Authority review and approval).
| 83 | The CAFM management system will be based on IBM’s Maximo product line.
| 84 | CAFM systems workflows.(planning, scheduling, executing, leading) for maintenance activities, inspection and audits)
| 85 | CAFM reporting system.
| 86 | Access for Contracting Authority .
| 87 | List of systems statuses.
| 88 | List of reporting system
| 89 | List of assets
| 90 | List of locations
| 91 | Location criticality
| 92 | Location Functions
| 93 | Asset Classification and categorization
| 94 | Issue Classification.
| 95 | Asset Specifications, failure modes, meter groups and other supported attributes
| 96 | Historical data and archiving
| 97 | Asset Condition Assessment.
| 98 | Asset Criticality Analysis.
| 99 | Life Cycle Plan and all supported documents.
| 100 | Uploading all documents (after client approval) to the CAFM
Call Center and Work Control Centre Plan Details (shall include but not limited to)
8 | 101 | Registration & Escalation process
| 102 | Helpdesk operation workflow
| 103 | Reporting and publication
| 104 | Customer satisfaction process
| 105 | Audit on process of helpdesk
| 106 | Helpdesk operation
| 107 | Customer care policy
| 108 | Complying and review
Inventory Management Plan (shall include but not limited to)
9 | 109 | Replenishment Plan.
| 110 | Inventory list status (the service provider shall collect and submit a list of full inventory & assets under his responsibility).
| 111 | List of spare parts, consumables & chemicals used onsite with all documentations.
| 112 | Criticality and analysis attributes for spare parts
| 113 | Spares and Store management including (procedures, Asset tracking system, turn in , turn out, critical spares, fast Moving Spares ,Long Lead Spares, Obsolete Spares, disposal)
| 114 | Warehouse, storage, and workshop requirements.
SMS , SEMS , EMS (Safety Management System, Security Management System, Environment Management System)
10 | 115 | Health and Safety system (SMS) - see also Risk and Safety section
| 116 | Security Management system (SEMS)
| 117 | Environment Management system (EMS)
| 118 | Comprehensive TBT and awareness program to cover al health and safety, Security and Environment risks and precautions
| 119 | Clear requirements and safety instructions for each main activity.
| 120 | Waste management and Environment Plan to include but not limited to hazardous waste management plan and pest control activities
| 121 | Personal Protective Equipment (PPE) and uniform list
| 122 | Vehicle and motors equipment inspection program
| 123 | Emergency Preparedness and Crisis Management Plan and Operation plan that shall include, but not limited to, responses to the following situations (the “Emergency”): • Natural disasters (sandstorms, flooding, etc.) • Utility failures (loss of electricity, potable water, sanitary drains, cooling etc.). • Acts of terrorism, strikes and walkouts. • Fire. • Flooding. • Incidents / Accidents within all the contract airports.
Mobilisation Dashboards and Trackers (shall include but not limited to)
11 | 124 | Key Personnel
| 125 | All Personnel
| 126 | SubContractors
| 127 | Spare Parts and Consumables
| 128 | Key Documents (SDPs)
| 129 | Training
| 130 | Handover
| 131 | Snagging, Condition Assessments, Asset Validation