## Open
Eggleston Parish Council Action Points March 2026 - Open
Ref | Date | Item | BY WHO | ACTION POINT | STATUS
1 2021 | 2021-07-07 | Recreation Park continued | Cllrs Donald/Hutchinson/ Oxby & Parish Clerk | 02/07/25 : See minutes. 02/07/25: It was suggested to involve the students at Bishop Auckland College to provide repair and maintenance assistance in the Recreation Park and Village Green as part of their course. This will be looked at in more detail in September onwards. 02/09/25: Parish Clerk to contact Middleton Forge on anticipated timeframe for the fence replacement. The round wing has been taken down by Cllr. Hutchinson as a safety precaution. 01/10/25: Middleton Forge have completed the fence along the new property. The work needs inspecting before payment. 05/11/25: Middleton Forge completed two sides of fence replacement instead of one as instructed. They acknowledge that the mistake is on their part and have agreed to invoice as per the contractual agreement. Mr. Evans has kindly brought down the basketball hoops. Cllr Souter to contact Mr. Evans to arrange collection and begin the installation of the replacement hoops. Cllr. Hutchinson will keep up with the weekly inspections. 03/12/25 : Clerk to invoice Mr. Evans for the difference in the fence height. The Parish Council is happy to accept Mr. Evans estimated figure in his previous email. 04/02/26: Payment has been received from Mr. Evans.The Parish Clerk to contact East Durham College (EDC) to express the Parish Council’s interest in becoming involved in the apprenticeship programme.04/03/26: Following discussion with EDC, the Parish Council will not be able to participate in the program as the apprentice must be taken on as an employee. | Ongoing
1905-07-15 | 2023-08-02 | Village Green | Cllr. M. Souter | 07/02/24: Parish Clerk to email Senior Tree Officer reference to crowning of 12 trees with 2 large branches needing removal. 06/03/24: Forms were received from the Senior Tree Officer. These to be completed by Cllr. Souter with support from the Parish Clerk. 03/04/24: The Parish clerk will drop the forms and accompanying documents to Cllr. M. Souter to complete. 01/05/24: No change - ongoing. 05/06/24: No change - ongoing. 14/08/24: Cllr. Souter will complete forms required for tree maintenance. 11/09/24: No change - ongoing. 09/10/24: No change - ongoing. 06/11/24: No change - ongoing. 08/01/25: No change - ongoing. 05/02/2025: Cllr. Souter will coordinate with Cllr. Hutchinson on completing the forms required for tree maintenance. The Parish Clerk will contact the Green Team at DCC on works they could assist with. 14/03/25: No change - ongoing. 02/04/25: Cllr. Souter will complete the forms required for trees needing attention. 07/05/25: The damaged tree has been felled as a matter of urgency by Mr. Davison following consultation with the Senior Tree Officer at DCC. Cllr. Souter to complete the required forms. 04/06/25: No change - ongoing . 02/07/25: No change - ongoing (see Recreation Park). 02/09/25: No change - ongoing. 01/10/25: No change - ongoing. 05/11/25: No change - ongoing. 03/12/25: No change - ongoing. 04/02/26: No change - ongoing. 04/03/26: No change - ongoing. | Ongoing
3 2022 | 2022-02-17 | Cutting of trees before nesting | Cllr. M. Souter/Parish Clerk | (see closed sheet). 03/04/24: No change - ongoing. 01/05/24: No change - ongoing. 05/06/24: No change - ongoing. 14/08/24: The monkey puzzle tree cannot be cut down and must fall on its own under laws governing trees in conservation areas. 11/09/24: No change - ongoing. 09/10/24: No change - ongoing. 06/11/24: No change - ongoing. 08/01/25: No change - ongoing. 05/02/25: No change - ongoing. 14/03/25: No change - ongoing. 02/04/25: Due to the bird nesting period, this will be revisited later in the year. 01/10/25: Works that need to be done can now be looked at. 05/11/25: Cllr. Souter will complete the form required for crowning works. 03/12/25: No change - ongoing. 04/02/26: No change - ongoing. 04/03/26: No change - ongoing. | Ongoing
2024 | 2024-08-14 | Footpaths | Cllr. E. Henderson | 14/08/24: Queries have been made by the community in terms of who is responsible for the maintenance of public footpaths. The councillors confirmed that the responsibility falls with the land owner but financial support is available through Durham County Council for maintenance as well as replacement of stiles. Cllr. R. Hutchinson will find out more on what assistance is available. 11/09/24: Financial assistance is available to land owners and information is available to differentiate between undergrowth and overgrowth thereby determining if it is the land-owners responsibility or DCC's responsibility to cut back vegetation. It was also discussed that some footpaths have been obstructed without permission from DCC. Further investigation will be done by Cllr. R. Hutchinson for footpaths affected. 09/10/24: No change - ongoing. 06/11/24: Cllr. Hutchinson will provide information on financial support available from DCC to A. Bainbridge . 08/01/25: No change - ongoing. 05/02/25: Financial support from DCC needs to be requested directly by the land owner. 14/03/25: No change - ongoing. 02/04/25: No change - ongoing. 07/05/25: Cllr. Hutchinson to discuss the options/support available with the respective farmers. 04/06/25: Cllr. Henderson will take over Footpaths . 02/07/25: Cllr. E. Henderson will assist A. Bainbridge with funding options available. 02/09/25: No change - ongoing. 01/10/25: No change - ongoing. 05/11/25: No change - ongoing. 03/12/25: No change - ongoing. 04/02/26: No change - ongoing. 04/03/26: Cllr Henderson has been in contact with the relevant departments and the footpaths will be cleared and tidied. | Ongoing
2024 | 2024-09-11 | Pinfold Sale | Cllr. W. Greenfield | 09/10/24: Documents have been requested by The Land Registry through Tilly Bailey & Irvine. Our solicitors have therefore requested for The Parish Council’s Constitution or Standing Order confirming the Vice Chair and Chair are able to validly execute Deeds on behalf of the Parish Council. See minutes. 09/10/24: No change - ongoing. 06/11/24: See meeting minutes for details. 08/01/25: All additional documents have now been completed. This is currently with Land Registry to complete transfer of the piece of land sold. 05/02/25: On-going. 14/03/25: No change - ongoing. 02/04/25: No change - ongoing. 07/05/25: No change - ongoing. 04/06/25: No change - ongoing. 02/07/25: No change - ongoing. 02/09/25: No change - ongoing. 01/10/25: No change - ongoing. 05/11/25: No change - ongoing. 03/12/25: No change - ongoing. 04/02/26: No change - ongoing. 04/03/26: No change - ongoing. | Ongoing
2025 | 2025-06-04 | Green Team | Cllr. E. Henderson | 04/06/25: Cllr. Henderson will contact the green team at DCC on works to be done as well as the benches at former Three Tuns Inn. 02/07/25: No change - ongoing. 02/09/25: No change - ongoing. 01/10/25: Cllr. Henderson to contact Green Team to see if there is any progress. Parish Clerk to contact the college. 05/11/25: Parish Clerk has contacted college. 03/12/25: An email was sent to the college by the Clerk; awaiting response. 04/02/26: Cllr. Henderson will continue to look into this. 04/03/26: Cllr Henderson is in contact with the Clean & Green and Find and Fix teams. | Ongoing
2025 | 2025-06-04 | Village Hall | Cllr. W. Greenfield | 04/06/25: Ammendements have been made to Village Hall Consortium (see minutes). 02/07/25: Cllr. W. Greenfield informed the meeting that work on Schedule 2 is progressing. 02/09/25: Village Hall meeting scheduled for 24th September. 01/10/25: McGarry & Co are looking at which Trustees are represented on the Charity's Commission based on historic documentation. The Village Hall Management Committee will be informed of the same to ensure transparency. 05/11/25: Mr A Lee affirmed that the accounts for the Village Hall had ben submitted to the Charity Commission on time. Mr D Hutchinson has set up a new constitution . 03/12/25: Ongoing. 04/02/26: No change - ongoing. 04/03/26: No change - ongoing. | Ongoing

## Closed Pre 2021
Eggleston Parish Council Action Points 2018 - Discharged
Ref | Date | ACTION POINT | BY WHO | UPDATE | STATUS
1 | 05/04/17 05 | Obtain dates of purchase and cost of rec park equipment. | Clerk | 03/05/17: Not yet complete 07/06/17: Will need to dig out all invoices, could take quite some time 06/09/17: Now being pursued with friends group. 06/06/18: Valuation list as of 2015 attached. Suzanne would probably be able to supply estimated dates for each phase of the project. 04/07/18: Chairman to contact. AUGUST: Email sent to Suzanne Herbert. 05/09/18 & 03/10/18: Still awaiting response. 03/11/18: Suzanne has found some certificates and is looking for others. 05/12/18: No response since last council meeting. 09/01/19: Response received and information is forthcoming. 06/02/18 & 12/03/19 : Response asking if dates and amounts needed - correspondance ongoing. 04/04/18 Papers rec'd: Clerk To check amounts to Asset register and file 01/05/19 Asset Register values to be used. | Closed
Cllr Greenfield
2 | 06/09/17 06 | Clerk to speak to Jayne Holmes re text giving | Clerk | 01/11/17: Information requested. 06/12/17: Can set up with Vodaphone after next newsletter. 07/02/18: Letters to Teesdale Mercury once up and running. 02/05/18: Clerk to speak to Jayne Holmes for instructions. June/July 18: Await new clerk to action. Sep/Oct/Nov/Dec 18: Clerk to pursue. 09/01/19: Clerk spoke to J Holmes, church is no longer retaining as only one donation made. Decision made to test for the year for the recreation park to test the viability. 06/02/18: Just Giving is ceasing - Crowdfunding ongoing, but has to be an individual and individuals bank account with end date. All agreed not viable - and will put notice with BACs detials asking for donation in park instead. See AP 2/2019. | Closed
3 | 06/12/17 08 | Refer issue of rail at Greenbank to DCC. | Cllr Henderson | 07/02/18: DCC have refused to do anything. Cllr Henderson will pursue for costs to be allocated in new financial year. 02/05/18: Cllr Henderson has requested this be classed as ongoing. Clerk requested to write to Highways re safety issues and to put financial amounts into future plans. Copy to parishioner. 05/09/18 & 03/11/18: No further update. 05/12/18: Carers have reported due to Parishioner falling - have been advised there will be a handrail within 2/3 months. 06/02/19: Carers been advised no rail will be placed. Clerk to write to DCC advising of situation and request update. 24/02/19: Request made, case no FS-Case-106927042. 12/03/19: Area has been measured by DCC Operative and they will be pricing for the job. 04/04/19: Rail now in place | Closed
4 | 02/05/18 07 | Write to parishioners regarding parking problems. | Cllr Oxby | 06/06/18: Complete, no response. Cllr Oxby to monitor before further action as not available for update. 04/07/18: This improved after the letter but has now reverted. Suggestions - police visit & Highways due to the erosion of the road opposite the house. 05/09/18: Cllr Oxby has spoken to local police representative. 03/10/18: Nothing heard to date. Council representative to talk to police representative at the Nov TAP meeting to see what can be done to take this forward. 03/11/18: Has improved, but it is still an issue. Police representative not at TAP meeting. Cllr Oxby is meeting up re speeding training, so will discuss. 05/12/18: Cllr Greenfield saw new police commisioner at TAP meeting and asked for patrols of area and roadway has now been repaired. All agreed all action available and now closed. | Closed
03 | 2018-05-02 | Cllr Souter to put topsoil in space at bottom of green. | Cllr Souter | JUNE 6th UPDATE To be done in next 2 weeks JULY Due to the dry weather this is not a good time to do this. Wait for rain
|  |  |  | SEPT 5 UPDATE – This should be done within the next week as it is now ready to do. OCT 3 UPDATE – This has now been completed. | Closed
04 | 2018-07-04 | Rights of way consultation over Wolsingham South Moor. | Cllr Gillard | JULY 4th To seek advice from Audrey Christie abut the proposal | Closed
SEPT 5 UPDATE – No further action needed.
02 | 2018-06-06 | 11th November 100th Anniversary of end WW1. | Cllr Hutchinson Cllr Souter Cllr Donald Cllr Gillard | Brazier and Water Stand for Brazier; combustibles & security tape. Informing Fire Brigade of plans and ask for advice if required. PR 03/11/18: All items discussed as agenda item at meeting - all in place. | Closed
|  |  | Clerk | 17/09/18: Silhouette £250, timetable for grant was 01/10, order had to be made by 08/10, therefore no time to ensure grant before ordering. Agreed with WG NFA taken. | Closed
03 | 2018-06-06 | Loose slabs on Footpath between Hilltop & Terraces | Cllr Gillard | JUNE write to landowner JULY 4th UPDATE Personal visit required to clear responsibilities | Closed
AUGUST Contact with DCC - they will fix on this occasion
SEPT 5 UPDATE – Cllr Gillard to confirm if this has now been done
02 | 2018-08-01 | Chairman to write to other teesdale councils ref 11th Nov | Cllr Greenfield | SEPT 5 UPDATE – Middleton have responded and stated that they have no actions planned. No response from other councils. | Closed
5 | 01/08/18 01 | Training for Road safety & speeding | Cllr Oxby | 01/08/18: Placed on Action sheet from minutes. 05/09/18: All forms now with Police. Await dates. 03/10/18: Still awaiting response – Council representative to talk to police representative at the Nov TAP meeting to see what can be done to take this forward. 11/10/18: Police representative will be able to pick the grab bag up in a couple of weeks and will be in touch when they have it to organise getting together for some training. 03/11/18: Grab back recieved. Cllr Oxby to organise mutual training date with volunteers and police representative. Cllr Oxby to organise retention of Grab bag with village hall, or at Moorcock Inn if hall not viable. 03/12/18: No battery charger with grab back so it couldn't be used, Cllr Oxby chasing. Agreed Moorcock Inn used for storage as village hall rarely open and keyholder needed to access. 09/01/19: Cllr Oxby to pick up a battery charger from the police station. Machine to be stored in Village Hall as the police thought it was a better place (in Cllr Oxby shed until moved). Further volunteers needed. 06/02/18: Volunteers trained, awaiting police. 01/05/19: Notice in Newsletter for volunteers 12/06/19 Notice for volunteers to go out in August Newsletter that training has been undertaken and for new volunteers. | Closed
6 | 05/09/18 01 | Gutters solid east of The Croft which could cause significant damage to adjoining property in heavy rain | Clerk | Clerk to contact Highways Council to take appropriate action – see minutes. 03/10/18: Clerk had no time to action this month 17/10/18: Issue reported to DCC - ref 31587999 03/12/18 Closed | Closed
02 | 2018-09-05 | Advice about the dying monkey puzzle tree | Clerk | Clerk to contact Tree Officer to see if dying tree would need replacing – see minutes. 03/10/18: Clerk had no time to action this month. 17/10/18: Spoke to Senior Tree Officer DCC, tree would not need replacing like with like, or at all should we choose not to. If tree is dying, to put application into DCC for it to be assessed and taken down. 03/11/08: Cllrs agreed to review situation of tree in spring and if not recovering, to get assessed for it to be taken down. | Closed.
03 | 2018-09-05 | Hall Bank road view obscured by trees and path needs clearing | Clerk | Clerk to contact Highways Council to take appropriate action – see minutes.. 03/10/18: Clerk had no time to action this month 17/10/18: Both reported to DCC - ref 31589606 Trees, 31589759 Path. 03/11/18: Ref 31589606 & 31589759 Actioned. | Closed
7 | 03/10/18 01 | Visibility at bottom of Green Lane obscured by large hedge. | Cllr Henderson | Cllr Henderson to action – see minutes 05/12/18: Cllr Henderson has confirmed that the trees can be cut back without permission being needed. Info to be relayed to parishioner. 09/01/18: WG spoke to parishioner and this has now been cut back to improve visibility. | Closed
10 | 2018-11-03 | To organise set up of new council website | Clerk | See Minutes 02/12/18: New website created. Renaming of current and historic documents continues in order to undertake uploading of historic and current documents to website. 09/01/19: Website developer unable to design website that we can update. Decision made to bring previous website up to date and reconsider action to take re new html website in May. Clerk to contact developer and action. 01/05/19: This is being brought up at smaller councils meeting. However, due to small number of website hits - never more than 15 people in a month propose that on the basis of costs to meet regulation for accessibilty for 240 households in Parish, it is beyond reasonable. Prosposed by Cllr Greenfield, Seconded Cllr Henderson. | Closed
1 | 2019-01-09 | Investigating the current paperwork and actions required should the council wish to amend current wayleave fees. | Cllr Greenfield | See Minutes 09/01/19 - Conversation ongoing with DCC representatives 09/02/19 Awaiting response from NALC. 12/03/19 - See minutes - decision made for Licence to be issued in regards to Eggleston Church property. Other properties to be reconsidered in due course. Clerk to take required action on approach by vendors solicitors. | Closed
2 | 2019-02-06 | Draft notice to be placed in Recreation Park for donation consideration. | Cllr Donald | See Minutes 12/03/19: Draft notice agreed - to be laminated and placed in park | Closed
| 2019-05-01 | Dead trees on village green and recreation park | Clerk | Closed | Closed
| 2019-12-04 | VE day celebrations | CLLR Greenfield | See Minutes 04/12/2019 Small lottery grant VE day 25 year grant from Lottery A number of different funding idea Action: Denise and Wendy to look at different funding | Closed
| 2020-08-05 | Printer provision for clerk | Clerk | Laser printer to be purchased. Clerk now to use her own with ink paid for by council. Previous printer donated to UTASS. Asset register for new laptop updated by RFO. | Closed
| 2020-10-08 | Reboot of laptop | RFO | Work paid for reboot of parish laptop | Closed
| 2020-10-08 | Pay increase for RFO | RFO | Pay increase for RFO agreed to ove up one point on incremental scale. | Actioned.
| 2020-10-08 | Remembrance Day celebrations | Cllr Souter | Cllr Souter to lay wreath on behalf of Council on 8 Nov. | Closed
| 2020-10-08 | Recreation Park Maintenance | RFO | Advert to be placed in Teesdale Mercury for contract. Jan 2021 - contract awarded. | Actioned.
| 2020-12-02 | Care in our Parish | Cllr Greenfield | Tea boxes and Christmas cards to be delivered by volunteers on 12 Dec | Actioned and discharged
2 | 2019-12-04 |  | By Cllrs L Oxby | See Minutes 04/12/2019 Muck/ run off along bottom road complaint Highways issue, Ross arrived at 7pm Between Mr Tully and Mr Tarns and Mr Ps When it rains a lot of run off, possibly blocked drains | Closed
7;2020 | 2020-10-08 | Continue unrecoverable costs for Pinfold survey and land registry costs | Cllr Greenfield | Ongoing issue with recovering costs. | Closed
8;2020 | 2020-10-08 | Newsletters | Cllr Greenfield | Tear off strip regarding online access for newsletters - hope for November newsletter but may need to be February | Closed
10;2020 | 2020-12-02 | 2021/2022 Budget | RFO | Figures for budget to be amended. 06/01/2021 DCC to be advised of precept requirements | closed
1;2021 | 2021-01-06 | DCC transport plan | Clerk | Feedback to DCC regarding the future transport plan before the end of January. | Closed
3; 2020 | 2020-08-05 | Website | RFO/Clerk | 05/08/2020 Jamie McBain to manage website at cost of £250 annually. 04/11/2020 To review at December meeting. 04/03/2021 Contract to be forwarded to run from 1 March for 12 months annually. March 2021 - contract and payment sent to Jamie McBain for annual contract for website. | closed
9;2020 | 2020-10-08 | Parish Councillor vacancy | Cllr. Henderson | November newsletter to include item regarding Parish Councillor vacancy. Postponed until into the New Year. | closed
5; 2020 | 2020-09-02 | Risk assessment | Clerk | Policy to be updated for May 2021 - on agenda for April 2021 meeting | closed
4; 2020 | 05/08 2020 | Road safety/grass cutback | Clerk | DCC to be approached regarding grass cutback at Gatehouse junction. (Done) Further white lining at Woodland junction to be pursued for extra safety following fatality. 04/03/2021 Will be done when DCC next in the area. 07/07/21 no action taken yet by the DCC highways department. | Closed
6;2020 | 2020-09-02 | Tidying of paths and roadside edges at Folly Top | Cllr Henderson | Approach 'Clean and Green' team at DCC to request tidying of paths and road edges on Folly Bank. | Closed
8 | 2018-11-03 | Request certificate of electrical work and plans for wiring for Christmas Lights on village green | Clerk | See Minutes 05/12/18-09/01/19-06/02/19:Requests sent to incorrect address - corrected and awaiting response 01/05/19: Correspondance from committee, work on certificate ongoing 12/06/19: Electricians report received. Clerk to write to David to ask them to confirm when 3 observations have been completed. 06/01/21 Ensure all correct certification is in place. 09/03/21 Electrical certificate received from Michael Tarn dated 01/06/2019 when all in order. 07/07/21 Still pursuing the confirmation of electrical certificate for the lower area of the village green. 05/08/2021 further contact made with light committee - received. | closed
8;2021 | 2021-08-07 | Queen's Jubilee Beacon | Cllr Souter/all | Arranging beacon lighting 2 June 2022. Inform organisers of our intentions - done
81;2021 | 2021-08-07 | Hill Top Glamping | Cllr Souter/all | Planning dispute with local residents - awaiting information from DCC. To refer to Standards Committee at DCC. Email from planning dept. matter closed 06/10/21 | closed
1;2021 | 2021-07-07 | Speeding in village | Cllr Oxby | To check the equipment and find volunteers 05/08/2021 Waiting from contact by the police representative. Training to take place on 21/10/21 | Closed
3;2021 | 2021-07-07 | Community litter pick | Cllr Stenson | Date to determine, volunteers to be found. 05/08/21 Delayed until later in the year/Spring 2022 Cllr Stenson orgainised this for 06/11/21 | closed

## Closed Items 2022 to 2023
Eggleston Parish Council Action Points 2022/23 - Closed
Ref | Date | Item | BY WHO | ACTION POINT | STATUS
| 2022-02-02 | Welcome to Middleton-in-Teesdale sign | Parish Clerk | 02/02/22: The Parish Clerk to write to the Clerk at Middleton-in-Teesdale to inform the Council of Eggleston Council’s decision. 09/03/22 The previous decision made not to replace the sign within Eggleston Parish boundaries was maintained. The Parish Clerk to respond to Middleton-in-Teesdale and Newbiggin Parish Council Clerk. 06/04/22 The Parish Clerk wrote to Middleton-in-Teesdale and Newbiggin Parish Council Clerk to inform them that the previous decision was maintained. No reply received. | Closed 06/04/22
| 2022-02-02 | Community Funding | Cllr. W. Greenfield | 02/02/22: Cllr. W. Greenfield will find out if there is any additional community funding that can be obtained following community emergencies. 06/04/22 Cllr. W. Greenfield informed the meeting that Durham County Council (DCC) had supported emergencies during Storm Arwen but no commitment was given for future emergency funding. | Closed 06/04/22
| 2022-01-05 | Printer Purchase | Cllr. J. Donald/C. Wake | 05/01/2022 Cllr. J. Donald offered to donate a printer that is surplus to her needs to the Parish. C. Wake to liaise with Cllr. J. Donald. 06/04/22 Printer is working okay. | Closed 06/04/22
| 2021-11-03 | Village Information Booklet | Cllr. Stenson (to be lead + R. Stables & P. Fraser)/Cllr. Greenfield and C. Wake | Information booklet to be made to provide new village residents with essential contacts and add to website when completed. 05/01/2022 Cllr. Stenson will make the suggested additions/changes discussed. The Information Booklet will be available on the website and updated where necessary by Cllr. W. Greenfield and C. Wake. 06/04/22 The information booklet is current available on the website. 04/05/22 Hard copies can be made available. This matter will now be closed. | Closed 05/05/22
| 2022-04-06 | Village Litter Pick | Cllr. L. Stenson | 06/04/22 Cllr. L. Stenson proposed Saturday the 14th of May 10:30am to 1:30pm as a Village Litter Pick. The information will be put on the Parish website. 04/05/22 Cllr. L. Stenson has requested 15 Adult litter picking kits and 15 children's litter picking kits from DCC. The Village Hall is booked from 10-30 to 1pm on the 14/05/22; Tea, coffee, juice and biscuits will be available. Contact has been made with Scouts, Guides Brownies and Cubs (adults to accompany under 12s). The event is advertised on the Parish Council's webpage. | Closed 01/06/22
| 2022-04-17 | Asset of Community Value | Cllr. W. Greenfield/Cllr. L. Stenson | 17/03/22 Cllr. W. Greenfield and Cllr. L. Stenson will submit an application to register Three Tuns Inn as an Asset of Community Value. 06/04/22 The Parish Council has submitted an application and supports the community application. 04/05/22 Parish Council awaiting response. 06/07/22 ACV registration application has been denied. | Closed 06/07/22
| 2018-11-03 | Pinfold History | Cllrs Hutchinson/ Donald/OxbyGreenfield and C.Bell | See Minutes 05/12/08: Ongoing - history being looked into and old pictures being located. 09/01/19: Cllrs to put email of info together for propostion of wording/pictures for all to consider. 04/03/2021 Now that the small area of land is not being purchased by the potential buyer any plans/grants for any improvement to the area to be considered. 06/02/19: After researching history decision made to restore to 1/3 wall but no gate, with dress stone to put plaque with historic info. Cllr Hutchinson to obtain cost of stone and build. Cllr Greenfield to draft plaque wording. When light enough prior to meeting - Cllrs to inspect Pinfold to measure and make final decisions on exact wall standing. 04/04/19: Cost of stone approx £35 per ton/apprx 1 ton of stone per metre wall 01/05/19: Work ongoing re information board. Research potential information for information board for Pinfold - part of village green. To consider stone seat. 12/06/19: All agreed to stone seat - Ross to get priced. Wording for seat to be agreed. Cllr Greenfield to seek grant from DCC for the work. 04/03/2021 Now that the strip of land is not being purchased by the potential buyer any plans/grants for improvement work to be considered. 07/07/21 Cllr. Greenfield to look at possible grants - to report back at the August 2021 meeting. 05/08/2021 Cllr Greenfield provided visual display of possible options, costings to be obtained. 06/10/21 potential purchase of some of the area. 03/11/21 Progress being made via the solicitors for the purchase of the 1.38m strip of land. Could add Jubilee bench within this area. 05/01/2022 The grant application can be made specifying that the garden will be a Jubilee Garden. It was proposed that Mrs C. Bell our RFO complete the grant application form with input from various councillors. Cllr. W. Greenfield to meet with George F. White in order to obtain a detailed map of what is being proposed for sale as requested by the solicitors. 02/02/22: Cllr. W. Greenfield will inform the Parish council once a response has been obtained from the surveyors at George F. White. 09/03/22 Cllr. W. Greenfield to continue with discussions on the pinfold. | Closed 06/07/22
| 2022-02-02 | Planning | Parish Clerk | 02/02/22: The Parish Clerk to send a letter to the Planning Department to enquire the way forward on new structure at The Houghs. 09.03/22: Cllr. R. Hutchinson and Cllr. J. Donald to compete the Planning Enforcement Complaint Form and return it to the Parish Clerk to then be forwarded to Durham Planning Department. 06/04/22: The Senior Enforcement Officer aims to provide an update by 18th of April 2022 on The Houghs. There were no objections to planning applications that have come through for Gatehouse Farm, Folly Top and Whistle Crag. 04/05/22: Egglesburn, Chapel: There were no objections. The Tree Tuns: Parish Clerk to respond to the solicitors on behalf of the Parish Council. 01/06/22: The Parish Clerk to send letters to Planning Department as per the minutes. 06/07/22: Retrospective planning application was submitted for stables at The Houghs. No objections raised. | Closed 03/08/22
| 2021-08-07 | The Queens' Platinum Jubilee | Cllrs Greenfield/Oxby/Hutchinson/Souter | Arranging beacon lighting 2 June 2022. Inform organisers - Clerk. 05/01/22 3 trees will be planted in the Pinfold. Cllr. W. Greenfield will include information in the next Parish News Letter informing residents of the upcoming Platinum Jubilee and residents will be invited to plant trees in their own gardens to mark the occasion if they so wish. Cllr. W. Greenfield will also contact the Carnival Committee on the matter. Cllr. L. Oxby will contact Lynn Hawdon on her availability to play the bugle at 9:35pm with an initial arrival time of 9:15pm on 2nd June 2022. It was suggested that Cllr. R. Hutchinson and Cllr. M. Souter to set up the beacon at The Leaf sculpture between Middleton-in-Teesdale and Eggleston. 02/02/22: Cllr W. Greenfield will include information on the Jubilee in the February Parish Newsletter. 09/03/22 Carnival Committee to be contacted on assistance on games and event planning. 06/04/22 Commemorative Coin: Councillors to determine the number of children in junior school (see minutes). 04/05/22: Details of planned activities have been included in the Parish Council newsletter for circulation. No road closures necessary. Councillors to see what games can be offered. Coins will be issued to children with permanent residence within the Parish Council and in junior school. 01/06/22: The Parish Clerk to request for the Electoral Roll for Eggleston Parish in order to identify households within the village for events purposes. 06/07/22: See minutes for lessons learned. 03/08/22: Item closed. | Closed 03/08/22
| 2018-12-05 | Parish Grounds Maintenance/Village Green | Cllr Souter + all Councillors | See Minutes 09/01/19 & 06/02/19 & 12/03/19 - None received. Councillors reminded to consider. 04/04/19: Discussed at meeting - Village green needs a tidy up re timber, twigs etc from trees - Cllrs Hutchinson and Souter to do before grass cutting commences. 01/05/19 Ongoing 12/06/19: Agreed annually -Empty both troughs and paint railings around troughs/weedspray pinfold/paint and tidy around roadsign/maintain and clear around fingerposts. 06/01/21 Extra soil to be added in worn areas on the village green (by post box) and wild flower planting planned. 02/09/21 Clerk applied for free bulbs to plant on village green. 02/12/21 Matthew Davison do 'odd jobs' around the village - benches etc. Councillors to send suggestions for maintenance needs to clerk to assess for contract in 2019/20 financial year. 02/02/22: Cllr Souter to arrange the tidying up of the village green at the agreed cost of £180.00. 06/07/22: Invoices received from C A Stamp to be forwarded to RFO for payment. 03/08/22: Tidying up has been recently done as contracted. 07/09/22: Maintenance is ongoing. | Closed 07/09/22
| 2022-01-05 | Laptop Purchase | Cllr. W. Greenfield/Parish Clerk | 05/01/2022 A budget of £700.00 has been agreed to be included in the 2022/23 budget. Cllr. W. Greenfield to contact Jenny Cartwright at Reboot for quotations for a new laptop. 06/04/22: Protech who will be supplying a refurbished laptop need to know the current status of the Microsoft Office licence. The Parish Clerk to liaise with Pamela S and C. Bell on the status of the license. 04/05/22: The Parish Clerk to obtain licence code if available. 06/07/22: The Parish Clerk to obtain costs of a Microsoft Office license. 03/08/22: In order to receive security updates and software upgrades it was decided that an annual Microsoft license is required. Costing £4.50/Month (excluding VAT). Proposed by Cllr. W. Greenfield seconded by Cllr. L. Oxby. All councillors in agreement. 07/09/22: The Parish Clerk collected the reconditioned laptop from Protech Group. A Microsoft licence needs to be installed, data transferred and tested. The invoice will follow. 05/10/22: The Parish Clerk is in the process of transferring the data. | Closed 7/11/2022
| 2022-01-05 | Environment Agency | Parish Clerk/All | 05/01/2022: Bill Stephenson, the Environment Agency representative would be asked about the location of all becks within the area if necessary after his presentation. C. Wake to inform Bill Stephenson of next meeting. 02/02/22: The Parish Clerk to contact Mr. Bill Stephenson on his availability for the next meeting. 06/04/22: Mr. Stephenson and L. Dobson attended the meeting on 09/03/22 giving a presentation on Flooding and Emergency Planning (see minutes for full details). DCC Environmental Agency team will support the Parish Council in developing an Emergency Plan. 04/05/22: B. Stephenson has changed departments. Parish Council is awaiting details of his replacement. | Closed 02/11/22
| 2022-10-05 | Rural Grant | Parish Clerk/All | 05/10/22: Parish Clerk to look at funding available from Rural England Prosperity Fund. 02/11/22: The Parish Clerk to look at funding option for the replacement slide. 07/12/22: Current Funding through the Rural Prosperity Fund is already earmarked for specific larger projects. | Closed 07/12/22
1 2021 | 2021-07-07 | Recreation Park | Cllrs Donald/Hutchinson/Oxby & Parish Clerk | Repairs to decorative wooden posts - grants available to determine. 05/08/2021 Quotes for repairs to be sourced prior to applying for grants. 03/11/21 recent vandalism to the small slide to address. Continued attempt to find local tradesmen to do the original repairs. 02/12/21 Tidying of park has not been completed by the contracted tradesman - contract to be terminated. Matthew Davison has agreed to do this work at £14/hr with this not exceeding the amount by which we need to find 3 tenders. He will also do 'odd jobs' around the village - benches etc. 05/01/22 Tenders would be required for the normal maintenance costs of 60 hours. Cllr. L. Oxby, and Cllr. J. Donald have agreed to meet up on the 20th of January 2022 at 9:30am to reassess the planned work that is needed. C. Wake will join them for the assessment. Cllr. R. Hutchinson to contact Phil Townsend on any tiles that need replacing. 02/02/22: The Parish Clerk to send tender requests for 2 lots of works to be carried out on the at the Recreation Park. 09/03/22 The Parish Clerk to inform M Davison Garden & Grounds and CA Stamp Grounds & Agriculture that they have been successful in their tender bids. | Closed 1/03/23
2 2021 | 2021-11-03 | Village Notice Board - Residents | Parish Clerk | Apply for funding to upgrade - contact made with TAP (02/12/21). 05/01/22 It was suggested an aluminium noticeboard similar to the one already in situ to be sourced but freestanding and with no lockable catch. C. Wake to source 3 quotes. 02/02/22: The Parish Clerk to obtain a more detailed quote to included additional options for the 2-bay, A1, AF30 Aluminium Noticeboard. 09/03/22 Cllr. W. Greenfield will contact Cllr. E. Henderson and Cllr. R. Bell on funding. 06/04/22: Annalisa Ward will get back to Cllr. W. Greenfield by May on availability of funding. 04/05/22: Funding is available from the County Council. Cllr Hutchinson will arrange for the installation of the notice board at no cost to the Parish Council. 01/06/22: The Parish Clerk to complete grant application. 06/07/22: Grant application has been submitted by the Parish Clerk to TAP for checking. Match Funding has been agreed by councillors. Pending documents to be submitted with application. 03/08/22: The grant application has been sent off for appraisal. 07/09/22: The application is being processed. 05/10/22: Application still being processed. 02/11/2022: Application is with DCC for approval. 07/12/2022: Funding has been approved. Funds should be in the Eggleston Parish Bank account within 2 weeks. 04/01/23: Parish Clerk to check if grant payment has been made. 01/02/23: The new residents noticeboard to be delivered to Cllr. R. Hutchinson's farm, who will organise the removal of the old and installation of the new noticeboard at no cost to the Parish Council. 01/03/23: The new noticeboard has been delivered. See minutes. 05/04/23: The noticeboard has been erected. 1 key to be kept in the Village Hall and the other on a chain and placed on the noticeboard at the entrance of village hall. The Parish Clerk to retain the other two. Details of key locations to be put in newsletter. | Closed 2/05/23
4 2022 | 2022-04-06 | Pinfold Sale | Cllrs Hutchinson/ Donald/Oxby/Greenfield and C.Bell | 06/04/22: Cllr. W. Greenfield informed meeting that a new marked OS map had been sent by G.F white to the Parish’s solicitor. G.F. White will cover the legal costs. The invoice from G.F. White, for the new OS plan, will be addressed to Strathmore Renewables Ltd and sent via their solicitor. Cllr. E. Henderson and Cllr. L. Oxby to complete required signatures. Cllr. M. Souter will get the planners to view pinfold when they attend the village next for an initial assessment. 04/05/2022: The new survey will need to be paid for. Sale can’t be completed until all required documents are signed. Cllr. E. Henderson and Cllr. L. Oxby to complete required signatures. 01/06/22: Awaiting completion of required signatures to complete sale. 06/07/22: Awaiting completion of required signatures to complete sale. 03/08/22: Ongoing with plans submitted by Cllr. W. Greenfield. 07/09/22: Cllrs Stenson/Oxby and Greenfield met with the buyer and his son and agreed on a curb of about 12" high to be erected instead of a wall. They are now waiting for their solicitor to act. 02/11/2022: Buyer to discuss with solicitors to push for completion of the sale. 07/12/2022 & 04/01/2023: Sale is progressing well. 01/02/23: Sale documents have been circulated for completion by the Chair and Vice Chair once completed to be sent to Parish Councils lawyers with a covering letter by the Parish Clerk. 01/03/23: Sale documents awaiting signature for completion. 05/04/23: No change to any item - all ongoing. 02/05/23: Sale complete and file now closed with solicitors. | Closed 05/07/23
6 2022 | 2022-08-03 | Village Flower Festival | Cllr Donald | 03/08/22: A budget will be determined at the next meeting. 05/10/22: It was agreed that subject to confirmation on availability of funds from The RFO, upto £180.00 will be made available to Cllr. J. Donald. 02/11/22: All councillors to try and come up with a film theme that is reflective of the Parish Council. Dependant on her availability, Cllr. J. Donald will try and create a flower display for the festival. 04/01/23: The church Vicar is discussing with parishioners to seek participation. 01/02/23: Flowers will be done for the month of May. 01/03/23: No change to any item - all ongoing. 05/04/23: No change to any item - all ongoing. 02/05/23: No change to any item - all ongoing. 05/07/23: Over £400 was raised by the church. | Closed 05/07/23
1 2022 | 2022-01-05 | Emergency Planning | Cllrs. W. Greenfield/Stenson/Henderson | 05/01/2022 Following the recent power outage, it was identified the need for an Emergency Plan for the Parish residents. Information on the Focal Points need to include names and contact details. Cllr. W. Greenfield agreed to collate the required information. Cllr. L. Stenson will find out about hire and installation of generators with a sight visit possibly required. Cllr. E. Henderson to look into the future use of The Three Tuns with the possibility of providing emergency accommodation. 09/03/22 Cllr. W. Greenfield will email the draft Emergency Plan prepared by the parish to Laura Dobson. 06/04/22 It was agreed that all councillors needed to sit together at a scheduled informal meeting to complete the initial proforma sent by DCC. Cllr. W. Greenfield and Cllr. L. Stenson to attend Session for Community Emergency Plans on the 17th of May 2022. The Parish Clerk will attend the online session. 04/05/22: Cllr. W. Greenfield has compiled most of the information required that now needs to be transferred onto the template provided by DCC. All councillors to sit down to complete. Parish Clerk to get a Map from DCC on all the becks within the Parish Council both over and underground. 06/07/22: Cllr. L. Oxby and The Parish Clerk attended the online emergency Planning session. Detailed presentation will be shared once available. The Environmental agency has provided a map of the water courses and culverts in and around the village. Awaiting additional information from DCC on becks if available. Cllr. L. Stenson, Cllr. R. Hutchinson and resident P. Fraser will work together with the Parish Council on developing the plan as well as any other residents who may volunteer. 03/08/22: Parish council residents to be invited in the next Newsletter to participate in development of the emergency Plan. 07/09/22: Cllr. W. Greenfield will meet with the (Emergency Planning Committee) councillors and volunteers from the village who have offered to help in developing the plan at the end of September. 05/10/22: The Warm Spaces initiative part of the emergency plan was discussed and Rev. R. Stables to gauge need within the community. Information to be included in the next Parish Newsletter to find out who would need/benefit from the initiative. 02/11/22: Cllr. L. Oxby will be attending a Warm Spaces meeting on 03/11/222. 07/12/22: First draft is complete. Item donations will be requested. Donations to include; stoves, dried and quick to prepare foods such as tinned soups, dried pasta etc. Items will be stored at the Village Hall - Youth Cafe Box. Funding will be sought for Hi Vis Vests, torches, stoves and other items to be used by councillors. Primary centre for emergency operations will be the Village Hall, secondary Moorcock Inn. Contact: The Parish Clerk, Lead - Cllr. W. Greenfield, Chair - Cllr. L. Oxby. All Councillors will be involved as well as Focal Points. 04/01/23: Cllr. W. Greenfield is waiting for feedback from committee. Cllr. W. Greenfield to arrange next meeting in a couple of weeks. 01/02/23: The emergency planning team will secure High Vis jackets, batteries, head torches, 2 gas stoves and cylinders, pots and pans through TAP funding. Cllr. E. Henderson will try to secure emergency planning packages that are surplus to the council but can be used by the parish council. 01/03/23: Cllr. W. Greenfield stated that the document is nearing completion. 05/04/23: No change to any item - all ongoing. 02/05/23: Cllr. W. Greenfield stated the completed document has been circulate to the planning group for editing and will be emailed to all concerned once complete. 05/07/23: Cllr. W. Greenfield stated the final document is now with DCC for approval. The document did not contain personal details of any parishioners needing specific help due to GDPR legislation. A document with individual needs will be updated and held by the Parish Clerk. A grant will be applied for through TAP once all parties are satisfied with the document. 02/08/23: Closed | Closed 02/08/23
1 2021 | 2021-07-07 | Recreation Park continued | Cllrs Donald/Hutchinson/Oxby & Parish Clerk | 06/04/22 Cllr. R. Hutchinson informed the meeting the tendered works have begun. Cllr. W. Greenfield will spread flower seeds along the steps. The Parish Clerk to forward tender documents to C. Bell. 04/05/22: Cllr. Hutchinson stated that the works have been completed and signed off. Cost of the repairs will be covered by income from the Pinfold as discussed and agreed in earlier meetings. An inspection of the pay park will be carried out in June 2022. No specific date can be booked. Cllr. Donald to look at the insurance claim to cover repairs on the yellow slide. 06/07/22: Cllrs Donald has forwarded the quotation to The RFO who will forward the documents to the insurance company. 03/08/22: The RFO is handling the matter with the insurers. 07/09/22: The insurers will not cover the cost of a replacement slide due to lack of a police report. Funding options for the slide was discussed. See meeting minutes. 05/10/22: Cllr. R. Hutchinson will enquire on the cost of removal and installation of the side. It was proposed that Cllrs Donald will complete the grant form once costing are available. RFO for 2023/24 budget. Cllr. Hutchinson to look at the state of the noticeboard. 02/11/22: Cllr. R. Hutchinson contacted Richard but no costings yet. Cllr. Hutchinson to look at replacing the legs on the noticeboard so that it can be back up. 07/12/22: Find and Fix service from DCC have been contacted for repair services at no cost. Cllr. W. Greenfield and Cllr. L. Oxby will attend a meeting with the relevant department at DCC once scheduled. Repair of the old noticeboard will be discussed as well as other projects within the Recreation Park and Village Green that can be undertaken through the scheme. The Parish Clerk to liaise with RFO on current costs for the slide replacement. 04/01/23: Parish Clerk to check with Komplan on cost of supply and delivery of slide. Atkinsons to be contacted on installation costs. 01/02/23: Cllr. R. Hutchinson will organise for the noticeboard to be re-erected. 01/03/23: Planted bulbs have not come up, possibly due to trampling. Matthew will begin works in the Spring. The Parish Clerk to approach TAP for £2600.00 in funding for the slide due to vandalism. This request will fall in the new financial period when more funds may be available. 05/04/23: Cllr. R. Hutchinson stated Matthew has carried out works in the park which will be completed. He noted a lot of damage due to rabbits. Cllr. R. Hutchinson will organise the relocation of the noticeboard to near the bin. 02/05/23: Cllr. R. Hutchinson is organising the relocation of the fallen noticeboard to near the bin. Cllr. R. Hutchinson confirmed Matthew has completed the tidy up and C A Stamp has cut the grass. Cllr. R. Hutchinson stated he can organise the installation of the slide once ordered. The Parish Clerk to contact Annalisa on progress of grant availability. Cllr. W. Greenfield will prepare an internal recreation park inspection form for weekly signing to ensure insurance validity. SEE BELOW. | Closed 06/12/23

## Closed Items 2024
Eggleston Parish Council Action Points 2024 - Closed
Ref | Date | Item | BY WHO | ACTION POINT | STATUS
2 2022 | 2022-02-02 | Internet Banking | Cllr. L. Oxby | 02/02/22: Cllr. L. Oxby to ask Mrs. C. Bell to take a deeper look at how double signatures will be achieved. 09/03/22 Cllr. L. Oxby will discuss the matter with Mrs. C. Bell. 06/04/22 Cllr. L. Oxby will discuss the matter with Mrs. C. Bell. 04/05/22, 06/07/22: Cllr. L. Oxby is discussing the matter with Mrs. C. Bell. 03/08/22: Cllr. L. Oxby is discussing the matter with Mrs. C. Bell. 07/09/22: Cllr. L. Oxby is discussing the matter with Mrs. C. Bell. 05/10/22: Cllr. L. Oxby is discussing the matter with Mrs. C. Bell. 04/01/23: No change to any item - all ongoing. 01/02/23: The RFO is only able to access internet banking via her personal account. Direct access is being sorted out. 01/03/23: Benefits of online banking out way the risks. The banking must be separate from all personal banking. 05/04/23: No change to any item - all ongoing. 02/05/23: To be discussed once bank mandate changes have been made. 05/07/23: No change to any item - all ongoing. 02/08/23: No change to any item - all ongoing. 06/09/2023: No change to any item - all ongoing. 04/10/2023: No change to any item - all ongoing. 08/11/2023: No change to any item - all ongoing. 06/12/23: No change - ongoing. 03/01/24: No change - ongoing. 07/02/24: Internet banking is now in place. | Closed 06/03/24
7 2022 | 2022-10-05 | Bus Shelter | Parish Clerk/All | 05/10/22: Cllr. E. Henderson is looking at funding. 02/11/22: The Parish Clerk to send Cllr. E. Henderson a reminder on funding options from County Council. 07/12/22 & 04/01/23: A survey will be done by DCC. 01/02/23: No change to any item - all ongoing. 01/03/23: Cllr. Henderson stated that highways are due to come out and look at the location proposed. 05/04/23: No change to any item - all ongoing. 02/05/23: No change to any item - all ongoing. 05/07/23: No change to any item - all ongoing. 02/08/23: No change to any item - all ongoing. 06/09/23: No change to any item - all ongoing. 04/10/23: Cllr. Hutchinson stated that the highway team has been out and he is awaiting their suggestions for the shelter. 08/11/2023: No change to any item - all ongoing. 06/12/23: No change - ongoing. 03/01/24: No change - ongoing. 07/02/24: Currently awaiting a reply from Highways. 06/03/24: No change - ongoing. 03/04/24: The location will be remeasured by DCC traffic engineer. Funding is available to cover the cost of the shelter and the application will be supported by one of the county councillors. 01/05/24: The bus shelter will be installed on the 15th of July 2024. 05/06/24: No change - ongoing. 14/08/24: The bus shelter has now been installed. Matter closed 14/08/24. | Closed 14/08/24
5 2022 | 2022-04-06 | Pinfold Garden | Cllrs Hutchinson/ Donald/Oxby/ Greenfield | 06/04/22: C. Bell will begin the completion of the TAP grant application form. 04/05/2022: Costings for the pinfold are required in order to secure a grant. Cllr. M. Souter discussed with the planning officer on works and is awaiting a final approval. Signage must be similar to that at Whistle Crag and the Recreation Park. 06/07/22: Cllr Oxby is working on the Information board. Cllr Greenfield awaiting costings. A wall must be erected to create a boundary between the Pinfold Garden and the next property. Electricity Pole is within the parish council property for which a wayleave compensation payment is received. 03/08/22: Planning will be required though full planning application may not be required. 07/09/22: The Pole will remain within the Parish Councils remit. 05/10/22: Pricing needed for project. 02/11/2022: Planning is required as frontage is being changed. Cllr Oxby and Cllr. M. Souter to provide Cllr Greenfield with the costing in order for grant application to be completed. 07/12/2022: The funding application has gone through the task group and agreed. A full funding application form now needs to be completed. Cllr. Greenfield will handle completion of the form. 04/01/23: Cllr. Greenfield will complete the grant form. 01/02/23: Cllr. Greenfield awaiting costings to complete the grant form. 01/03/23: Completed grant form has been approved at the initial TAP forum. It will now go to the board members for approval before progressing to the AGM for final approval by county councillors. 05/04/23: Cllr. Greenfield awaiting final costings for stone seat. Cllr. Hutchinson to follow up on removal of bins to the back of the property. 02/05/23: Awaiting funding. | Section Closed 9/10/24. Continued on active sheet from 05/07/2023

## Closed Items 2025
2024 | 2024-08-14 | .gov.uk | Cllr. W. Greenfield | 14/08/24: See detailed minutes. This will be at a cost of £100.00 and will be managed by James McBain who manages our website. The initial setup costs will be covered but the Parish Council will have to cover the ongoing costs. Proposed by Cllr. W. Greenfield and seconded by Cllr. E. Henderson. All councillors in agreement. Cllr. W. Greenfield to inform Mr. James McBain to proceed. 11/09/24: Cllr. W. Greenfield states that Jamie has begun the .gov.uk application. 09/10/24: Mr. James McBain is awaiting a quotation.09/10/24: No change - ongoing. 06/11/24: The 4 .gov email account details will be provided to Mr. James McBain to forward onto Somerset Web Services 08/01/25: Mr. McBain has kindly agreed to create a new website on Webflow at no cost to the Parish Council. Hosting cost will however be £200.00 per year. £72.00 payment for the .gov emails was approved at the meeting. | Closed Jan 2025
5 2022 | 2022-04-06 | Pinfold Garden | Cllrs Hutchinson/ Donald/Oxby/ Greenfield | 05/07/23: Progress has been good. The resin path has been constructed and the wall will go up once the ground is cleared. Councillors have been kept abreast through emails from Cllr. W. Greenfield. 02/08/23: See meeting minutes. 06/09/2023: The new owner has applied to Land Registry to make the necessary changes following purchase however, this should not delay the agreement for a wall to be erected. The Parish Council will wait a further month and then instruct our solicitor if no plans are in place to commence the agreed wall. 04/10/23: Cllr. Greenfield stated it is 98% complete. One more bag of green slate chippings will be required once the retaining edge has been erected. The Parish council will give the owner of the adjourning property till February to erect the retaining edge as they have a legal obligation based on the sale of the land. Cllr. Souter will drill holes in the plant container to allow for water drainage. 08/11/23: Cllr. Greenfield will arrange for the ragged edges on the planter to be replaced or smoothed. 06/12/23: No change - ongoing. 03/01/24: No change - ongoing. 07/02/24: Cllr. W. Greenfield to email Rhiannon to do a letter to the owner of the adjourning property on his obligation to erect the retaining wall based on the terms of sale. Photographs of the continual mess caused by the bins will also be forwarded to the solicitors. 06/03/24: Quarterly report to be completed by Parish Clerk. 03/04/24: Legal notice will be served through our solicitors for breach of terms of sale. This will be managed by Cllr. W. Greenfield. 01/05/24: No change - ongoing. 05/06/24: Works to contruct a stone planter is ongoing. Stones delivered by Foly Top Stone Supplies. End of Project Monitoring report submitted. 14/08/24: Construction of the stone wall will be done after the summer holiday break. 11/09/24: Cllr. W. Greenfield has chased up Richard Ayes to finish the stonework. 09/10/24: No change - ongoing.. 06/11/24: No change - ongoing. 08/01/25: Cllr. Greenfield informed the meeting that Mr. Ayes will complete the stonework which has been started. Arrangements need to be made to tidy up the garden. 05/02/25: No change - ongoing. | Closed March 2025
2024 | 2024-08-14 | Defibrillator | Cllr Souter | 14/08/224: The defibrillator is ready for installation. Cllr. M. Souter will continue to manage this. Cllr. M. Souter to coordinate installation. Cllr. L. Oxby will collect donated funds from Moorcock Inn. 11/09/24: No change - ongoing. 09/10/24: No change - ongoing. 06/11/24: The defibrillator has been intalled at Moorcock Inn. 08/01/25: A total of £117.80 has been raised to go towards the defibrillator from the local community. Cllr. Henderson has kindly offered to cover the cost of the additional pads for the defibrillator through the County Council community funds. Cllr. Oxby will arrange for the post code to be placed on the defibrillator. 05/02/25: Cllr. Oxby stated that no post code is required on the defibrillator. Cllr. Henderson will liaise with Cllr. Oxby to transfer the funds required for the spare pads which he is kindly personally donating. 14/03/25: No change - ongoing. 02/04/25: S. Bainbridge will conduct weekly checks. Cllr. Oxby will be the guardian. | Closed April 2025
8 2023 | 2023-08-02 | Emergency Planning Expenditure and Practice Exercise | Emergency Planning Committee | 06/09/23: Funding will be applied for once all quotations are obtained. The emergency exercise will be on flooding with emphasis around homes likely to be affected. The exercise to be conducted in April 2024. 04/10//23: Cllr. Greenfield stated that final costing are ongoing. 08/11/2023: Pricing ongoing. 06/12/23: No change - ongoing. 03/01/24: No change - ongoing. 07/02/24: No change - ongoing. 06/03/24: No change - ongoing. 03/04/24: A meeting will be set in 6-8 weeks. The team is currently awaiting to see if funds are available from DCC. Cllr. W. Greenfield will share The Emergency Plan with Romaldkirk, Middleton-in-Teesdale and Newbiggin and Marwood Parish councils as it has been approved by DCC. 01/05/24: No change - ongoing. 05/06/24: No change - ongoing. 14/08/24: No change - ongoing. 11/09/24: Cllr. W. Greenfield has sent our Emergency plan to the chairmen of Middleton-in-Teesdale, Romaldkirk and Marwood. Cllr. W. Greenfield is still waiting for finance information from DCC. 09/10/24: DCC have requested for the last three bank statements. 06/11/24: No change - ongoing. 08/01/25: No change - ongoing. 05/01/25: No change - ongoing. 05/02/25: No change - ongoing. 14/03/25: Cllr. Greenfield has resubmitted the funding application. 02/04/25: Cllr. Greenfield has resubmitted a funding request for £681.00. 07/05/25: Cllr. Greenfield is awaiting a decision on the application. 04/06/25: No change - ongoing. 02/07/25: No change - ongoing. | Closed Sept 2025
2025 | 2025-02-05 | Website .gov | Cllr. W. Greenfield | 05/02/25: Mr. McBain has begun creating a new website on Webflow. Any quality available photographs can be forwarded to the Parish Clerk to be included on the new website. 14/03/25: Cllr. Greenfield will provide additional information to be included on the website to Mr. McBain. 02/04/25: The website is progressing well. Councillors can view it through the link previously sent for final checks. 07/05.25: No change - ongoing. 04/06/25: Ammedments will be made and the new website will go live on the 30/06/25. 02/07/25: The website is live and with a link to The Carnival Commitee and The Village Hall Consortium websites. D. Hutchinson will provide the newsletters to go on the website. | Closed
1 2021 | 2021-07-07 | Recreation Park continued | Cllrs Donald/Hutchinson/ Oxby & Parish Clerk | 05/07/23: See minutes. 02/08/23: Comments were made on social media. The Councillors are aware of the discontent and the meeting was informed. 06/09/23: Cllr. R. Hutchinson is maintaining the weekly inspection with 2 copies to be kept of the reports. Cllr. R. Hutchinson to check on reported broken basketball hoops. The Parish Council are aware of the broken basketball board and Cllr. R. Hutchinson will take measurements and get costings for a replacement. 04/10/23: Cllr. R. Hutchinson stated that the hoops are in reasonable condition. Cost of replacing the basketball board is approx. £100.00. Cllr. R. Hutchinson will look at the base of the seating shelter to ensure it is in reasonable condition.08/11/23: Park Inspections are being carried out by Cllr. R. Hutchinson. Reports need to be put in the noticeboard. A quarterly reporting system will be agreed in the January meeting. Cllr. W. Greenfield will prepare a list of all councillors and their roles to go into the noticeboard so residents are aware who to approach when needed. 06/12/23: No change - ongoing. 03/01/24: No change - ongoing. 07/02/24: Park Inspections Form to be changed so handover dates coincide with the monthly meeting with transfer being done at the meeting. Cllr. R. Hutchinson to place a lock with three keys for the noticeboard in the recreation park. The basketball board to be replaced in April. 06/03/24: Cllr. R. Hutchinson will continue to try and secure three keys for the noticeboard in the recreation park. Costings needed to replace tension wire at the entrance to the MUGA. 03/04/24: Cllr. M. Souter will cost the wooden fence posts that need replacing due to their deterioration. 01/05/24: No change - ongoing. 05/06/24: Cllr. Hutchinson will obtain costing for the fencing. Once costings are in, the materials required will be purchased by the Parish Council and labour provided by Mr. M. Davison. 14/08/24: See meeting minutes for costings 11/09/24: The councillors present decided that for the long-term stability of the whole fence, the entire length of the fence will be replaced instead. Funding can be applied to cover the costs. 09/10/24: It was decided that the whole fence will need to be replaced for longevity. Cllr. M. Souter will draft the detailed tender requirements requiring each contractor to state in detail the type of materials as well as detailing precisely how timber will be secured into the ground. 06/11/24: No change - ongoing. 08/01/25: The basketball hoops will be assessed again when the weather improves. Cllr Oxby will follow-up with Cllr. Souter on the draft tender requirements for the entire fence replacement. 05/02/25: The details for the tender requirements are progressing with Cllr. Souter. Funding options from the Towns and Villages Fund needs to be explored. The new owners of the plot next to the Recreation Park have offered to pay the additional cost of extending the fence that will be erected from 1.2m to 1.8 m. 14/03/25: The new owners are putting in an application to Planning Department in order to cut back the overhanging branches. The matter on repairing the fence is ongoing. 02/04/25: There was no objection to the new owners on Plot 1 cutting back the branches as per the planning application submitted. The matter on repairing the fence is ongoing. 07/05/25: Cllr. Souter will look at the basketball boards. Cllr. Oxby will also discuss this with Neil. 04/06/25: The Parish Clerk will request for Tenders for the Fence replacement. 02/07/25 : See minutes. 02/07/25:see active sheet. | Ongoing
1905-07-15 | 2023-08-02 | Village Green | Cllr. M. Souter | 02/08/23: Planning Officer still concerned about nails in the trees. Cllr. W. Greenfield to contact carnival committee. 04/10/23: Cllr. Souter will contact CA Stamp on the possibility of crowning the trees without requiring authority from DCC. The matter of Christmas lights on the trees is still pending resolution with the Carnival Committee. The Parish Clerk to see if the report from DCC Tree Officer is available. 08/11/23: D. Hutchinson presented a letter of where the Carnival Committee stand with regards to the Christmas tree lights. This was accompanied by a report from a botanist. It was agreed to forward the documents to the Senior Tree Officer and await their advice on the matter. 06/12/23: Parish Clerk awaiting response from Senior Tree Officer. 03/01/24: Having taken advice, The Senior Tree Officer states that the Planning Enforcement Team have said that it would not be expedient in this case to pursue a prosecution in this matter. 07/02/24 see ative sheet. | Ongoing
3 2022 | 2022-02-17 | Cutting of trees before nesting | Cllr. M. Souter/Parish Clerk | 17/02/22: Cllr. M. Souter will inform the Carnival Committee on the work required and its effect on their lights. The Parish Clerk to follow up on the availability of a Council tree officer for inspection. 09/03/22: The Parish Clerk is following up on costs for an inspection. 17/03/22: Cllr. R. Hutchinson and Cllr. M. Souter to be present when Mr Alderson comes to inspect the trees on the 24th March 2022. 06/04/22: Costs received from DCC were prohibitive therefore an initial general inspection was done by Mr Alderson on the 24th March 2022. Cllr. R. Hutchinson informed the meeting that a virus was identified on one of the conker trees and that the monkey tree should be left to its own devises to determine its strength. The Parish Clerk to follow up Mr. Alderson for the official report. 04/05/22: Mr Alderson has provided a report which has been circulated to all Councillors. Cllr. M. Souter to print the report and forward it to the Carnival Committee. 06/07/22: Cllr. L. Stenson to forward report to the Carnival Committee. 03/08/22: The report from Mr. Alderson together with the photographs have been forwarded to the Carnival Committee. The Carnival Committee will be contacting Cllr. M. Souter and the Tree Officer at DCC as indicated by P. Fraser (member of the Carnival Committee). 07/09/22: Cllr. R. Hutchinson waiting for the tree officer. Canker is in one of the trees caused by infection in the trunk due to screws. Monkey puzzle tree to continue to be observed. 05/10/22: Discussions are ongoing between the Village Hall Committee and Parish Council. The Tree Officer to be called out again. 04/01/23: No change to any item - all ongoing. 01/02/23: No change to any item - all ongoing. 01/03/23: Planning permission may be requested to cut down trees in line with the Tree Officers report on the diseased trees. 05/04/23: No change to any item - all ongoing. 02/05/23: To be readdressed late 2023. 03/01/24: Cllr. M. Souter and Cllr. R. Hutchinson will organise to meet at the Village Green and assess what needs to be done. 07/02/24: No change - ongoing. 06/03/24: No change - ongoing. 03/04/24 : contunues on active sheet .