## Sheet1
Columbia (MD) Chapter Implementation Plan - Year 1
Priority 1 - Amplify a culture of friendship and engagement
Goal 1: Amplify a culture of friendship and engagement
|  | Year 1 |  |  |  | Year 2 | Year 3
Key Activities | Current State/Activities | Q1 | Q2 | Q3 | Q4 |  |  | Outcomes | Responsible Person(s)
Green Table Talk for September Retreat | Never Done previously |  | x |  |  | Annual Event | Annual Event | Culture of friendship and honesty | Regina Clay/Eastern Area OE
Monthly Membership Moments | This was done last year |  | x | x | x | Annual Event | Annual Event | Membership Engagement | Membership Committee
Pop Up Meet up Once a Quarter with Link sisters | Beginning in October |  | x | x | x | Same | Same | Friendship | Membership Committee
Goal 2: Increase participation in membership Chapter meetings, average 80% in attendance in 2023-2025
Key Activities | Current State/Activities | Q1 | Q2 | Q3 | Q4 | Year 2 | Year 3 | Outcomes | Responsible Person(s)
Make meetings shorter and more time for fellowship | Partially there Implemented last year | x | x | x | x | Continue | Continue | Members want to come to meetings | Membership Committee and Executive Leadership
In Consultation with Sergeant-of-Arms, find a meeting location and catering | Not completed | [6 empty] | Members like the meeting space | Membership/Hostess Committee
Review Meeting day and time | Not completed |  |  |  | x | Annual Review | Annual Review | To increase attendance
Priority 2 -Amplify a culture of transformational community service
Goal 1: Plan, implement an umbrella program; align with National priorities by 2023-2025
Key Activities | Current State/Activities | Q1 | Q2 | Q3 | Q4 | Year 2 | Year 3 | Outcomes | Responsible Person(s)
Walk To Wellness-Sponsor a family-oriented walk, most likely at Centennial Park- Provide info on local fitness vendors. | In Progress |  | X |  |  | Continue | Continue | Increased participation in exercise contributing to a healthy lifestyle | HHS
Healthy Food, Healthy Life-Partner with HCC and NKF, providing nutrition and health information on the importance of eating and preparing fresh food for cardiovascular and kidney health. Potentially partner with food trucks or conduct session that exposes students to Mediterranean, African or Indian foods and non-Western meditation and therapy traditions. | New- Not completed |  |  | X |  |  |  | Increased knowledge and awareness of the relationship between health eating, physical and mental health and how to purchase and prepare healthy foods | NTS/STYHHS
Mental Health Forum- Host and expand mental health forum at HCC leveraging last year’s successful event. Incorporate topics including body dysmorphia, gender identify, bullying/social media, meditation, art/ music therapy. | In Progress |  |  |  | X | Continue and Expand | Continue | Increased knowledge and awareness of the relationship between healthy eating and mental and physical wellness | STY/HHS
Black Kare- leverage and expand last year's successful Black Kare activities and resources | In Progress |  |  | X | X |  |  | Increased knowledge and awareness regarding kidney health | HHS/STY
Goal 2: Plan, implement one or more integrated programs, align with National priorities 2023-2025
| Current State/Activities | Q1 | Q2 | Q3 | Q4 | Year 2 | Year 3 | Outcomes | Responsible Person(s)
Priority 3 - Amplify a culture of fiscal responsibility
Goal 1: Provide Training To The Chapter at Least twice a year to ensure consistency in Financial Practices and Fiscal Responsibility and Accountability (Cascading Goal from National)
Key Activities |  | Q1 | Q2 | Q3 | Q4
Through some type of polling, identify the type of fiscal training the Chapter Needs ( namely budget process, budgeting cycle, Chapter schedules, etc.) | In-process | X
Collect and Analyze Polling data and Pick at least 2 topics for the training | to be scheduled (TBS) |  | X
arm | TBS |  | X
Develop and Vet the Training Material | TBS |  |  | X
Finalize the Training Material | TBS |  |  | X
Conduct at least 1 training Session | TBS |  |  |  | X
Goal 2: Work with Facets and Committees to Codify and Refine the Budget Process
Key Activities | Current State/Activities | Q1 | Q2 | Q3 | Q4 | Year 2 | Year 3 | Outcomes | Responsible Person(s)
Review FY23 and FY24 Budget Process Lessons Learned | TBS | X
Setup and Discuss Budget Insights with Link Shaydra | TBS | X
Document Budget Lessons Learned and Insights | TBS |  | X
Review and existing Links (National and Eastern Area) Training Material That exists | TBS |  | X
Work with the Strategic Planning Committee to Develop Some Budget Guidance | TBS |  | X | X
Document that Guidance and Vet with Committee and Facets | TBS |  |  | X
Get Feedback and Incorporate | TBS |  |  | X
Finalize the Budget Guidance and Distribute Of Use in FY27 | TBS |  |  |  | X
Priority 4 - Amplify a culture of organizational excellence and alignment
Goal 1: Create an environment that fosters engagement, measured by 90% engagement satisfaction o he chapter by 2025
Key Activities | Current State/Activities | Q1 | Q2 | Q3 | Q4 | Year 2 | Year 3 | Outcomes | Responsible Person(s)
Priority 5 - Amplify a culture of brand awareness
Goal 1: Increase utilization of strategically targeted media by 20% from 2023-2025
Key Activities | Current State/Activities | Q1 | Q2 | Q3 | Q4 | Year 2 | Year 3 | Outcomes | Responsible Person(s)
Goal 2: Increase our social media followers by 10% by 2025
Key Activities | Current State/Activities | Q1 | Q2 | Q3 | Q4 | Year 2 | Year 3 | Outcomes | Responsible Person(s)
Priority 6 - Amplify a Culture of Leadership and Professional development
Goal 1:
Key Activities | Current State/Activities | Q1 | Q2 | Q3 | Q4 | Year 2 | Year 3 | Outcomes | Responsible Person(s)