## Activity Schedule
ACTIVITY SCHEDULE
Item no. | Description | Amount
1 | Preliminaries & General (mobilization, Insurance, Health & Safety, Implementation of the Contractor’s Environmental and Social Management Plan (CESMP) including applicable Consent processes, etc.)
2 | Removal of the existing palisade fence including disposal offsite
3 | Concrete footings (25MPa)
4 | Concrete nib (20MPa)
5 | Fibremesh fence
6 | Install 7 new Fibre gates [4 x Pedestrian, 3 x double (vehicle)]
7 | Clean up and demobilize
8 | Concrete Testing
9 | The Contractor shall supply additional fencing materials and essential installation tools for use as spare parts and future maintenance. These items are not part of the permanent works and shall be handed over to the Client at completion. The quantity of spare materials shall be based on the full material requirements needed to install 50 m of the fence system, including posts, panels, brackets, fixings, proprietary components, and the basic tools required for minor repairs and adjustments. All materials and tools shall be new, unused, and identical to those used in the Works.
| Subtotal 1 | 0 | #DIV/0!
| VAGST (15%) | 0
| GRAND TOTAL | 0

## Schedule of Rates
Schedule of Rates
Description | Unit | Rate (SAT Incl. Vagst & markups)
Construction Manager | Hr
E&S Specialist | Hr
Foreman | Hr
Labourer | Hr
5T Excavator | Hr
20T Excavator | Hr
Dump Truck 7-10m3 | Hr
Generator | Hr
Rock Breaker | Hr
Demolition of Fence | m
Bulk Excavation | m3
Rock Excavation | m3
Concrete nib | m
Fibremesh Fence 1.8m High | m
20MPa Concrete | m3
25MPa Concrete | m3
Imported Scoria Hardfill | m3

## Payment Schedule
| Payment Terms | Sub-activity %
Item No. 1 | P&G
| Mobilization | 45%
100% once mobilized onsite
| Insurance & PG's | 5%
100% once insurance & all PG's received
| ESHS including health & safety | 25%
7.5% for each month and remaining amount in the final month
| Monthly Reports | 25%
7.5% for each month and remaining amount in the final month
Item No. 2 | Removal of the existing palisade fence including disposal offsite
| Removal of fence | 90%
10% when works commence and then % of the works completed each month
| Disposal | 10%
100% when completed
Item No. 3 | Concrete footings (25 Mpa)
| Construction | 100%
10% when works commence and then % of the works completed each month
Item No. 4 | Concrete nib (20 Mpa)
| Construction | 100%
10% when works commence and then % of the works completed each month
Item No. 5 | Fibremesh fence
| Supply & installation | 100%
25% after order is placed, 25% after materials arrive and then % of the works completed each month
Item No. 6 | Install 7 new Fibre gates
| Supply & installation | 100%
25% after order is placed, 25% after materials arrive and then % of the works completed each month
Item No. 7 | Clean up & Demobilize
| Clean Up | 50%
100% when works are completed
| Demobilization | 50%
100% when works are completed
Item No. 8 | Concrete Testing
| Monthly Testing | 100%
% of the works completed each month
Item No. 9 | Additional fencing materials and essential installation tools
| Fencing materials | 75%
100% when supplied
| Essential Installation tools | 25%
100% when supplied