## Sheet1
Firm Name
Verification Period
STEP | ACTION ITEM | PARTY RESPONSIBLE | DUE DATE | REVISED DUE DATE | ACTUAL DATE | COMMENTS
Initial Data Request
1 | Initial Data Request | Verifier | 2021-01-01
2 | Initial Data Provided | Firm | 2021-01-14
Sample Data Request
3 | Sample Data Request | Verifier | 2021-01-21
4 | Sample Data Provided | Firm | 2021-01-28
5 | Follow Up Items Request #1 | Verifier | 2021-02-04
6 | Follow Up Items Provided #1 | Firm | 2021-02-11
7 | Follow Up Items Request #2 | Verifier | 2021-02-18
8 | Follow Up Items Provided #2 | Firm | 2021-02-25
9 | Final Follow Up Items Request | Verifier | 2021-03-04
10 | Finalize Open Items | Firm | 2021-03-11
11 | Rep Letter Sent |  | 2021-03-18
12 | Rep Letter Signed |  | 2021-03-25
13 | Opinions Issued |  | 2021-04-01
*Note that any of these steps may need to be repeated more time than illustrated above. The additional rounds will be due to a number of items including 1) not providing the verifier will all data requested in a given round, 2) data provided to verifier is not sufficient for verifier sign off, or 3) errors are discovered in the data.
**Date Key: DUE DATE = Date both parties originally agree upon for data turnaround time. ACTUAL DUE DATE = Date that the action item was actually delivered in full REVISED DUE DATE = New due date if the actual date was ahead or behind the original schedule.