# Framing & Commitments Toolkit

# Your Planning Workbook

The Framing & Commitments Toolkit is an onboarding and planning tool that helps a heritage place or practice team set a clear foundation for Stage B of a locally led climate–heritage process. It provides you a space to document essential information about your heritage place or cultural practice, and the shared commitments of what “success” looks like. It guides teams through a light desk review of what is already known, what is missing, and where plural knowledge systems must be centred, clarifies local roles and responsibilities for facilitation, logistics, wellbeing and documentation, and establishes how evidence will be collected to support both the climate risk assessment process and emerging adaptation actions. Finally, it anticipates constraints and sensitivities, documents stakeholders and rightsholders, and gathers key appendices (maps, photos, background documents) so the work stays accountable, locally owned, and implementation-ready over time, aligned with widely used principles for locally led adaptation.

# 1. Heritage place or practice details

- ​​Heritage place or cultural practice name:

- Country/region:

- Steward(s) names:

- Type of place or practice:
(e.g. urban neighbourhood, sacred landscape, coastal village, archaeological site, cultural route, library)

## Description (Max 100 words)

What climate-related changes are already being felt or observed in your heritage place or for your heritage practice, and how are they affecting the places, practices, their values, and the people connected to them?

Why does a locally led risk assessment and adaptation plan matter for you and how will local leadership shape decisions, priorities, and ownership of your adaptation plan?

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

# 2. What does success look like to you?

## 2.1 Definition of Success for Stage B

These indicators will be visited quarterly to evaluate your progress. Think about what effect you were hoping to make within the community, and how you might keep track of impacts within and beyond your community. Below the table you will find examples of qualitative and quantitative indicators.

You can add rows to the table below.

| What does success look like for you? (Targeted Outcomes) | Qualitative indicators | Quantitative indicators |
| --- | --- | --- |

Examples of qualitative indicators:

- Participants report a shared understanding of key climate risks affecting priority values and attributes.

- Participants describe feeling heard, respected, and safe during workshops.

- Evidence that multiple knowledge systems (local, Indigenous, scientific) are referenced in discussions and outputs.

- Clear articulation of why specific values or attributes matter to different groups.

- Increased confidence among stakeholders and rights holders to discuss climate risks and adaptation options.

- Recognition of previously underrepresented voices in documented outputs.

- Emergence of new or strengthened relationships between stewards, communities, and technical actors.

- Ability of participants to explain climate risks in their own words, using locally meaningful language.

- Documented acknowledgement of uncertainties, tensions, or disagreements, rather than forced consensus.

- Evidence of community ownership, such as participants referring to “our plan,” “our priorities,” or “our risks.”

Examples of quantitative indicators:

- Number of participants engaged in engagement activities, workshops, or the process in general

- Enlisted community member/s to support your work

- Diversity of participants (e.g. number of women, youth, elders, under-represented groups).

- Number of adaptation actions identified or refined during Stage B.

- Percentage of planned workshop outputs completed.

- Number of documented maps, diagrams, or visual outputs produced.

- Number of quotes, stories, or testimonies documented (with consent).

- Number/diversity of desk research conducted

- Number of local actors or institutions engaged in the process.

## 2.2 Tracking your own Progress

| Indicators (qualitative or quantitative) | 1st quarter | 2nd quarter | 3rd quarter | 4th quarter |
| --- | --- | --- | --- | --- |

# 3. Challenges, Constraints & Sensitivities

Consider what challenges, constraints, and sensitivities might negatively impact meeting your success indicators listed above.

Anticipated challenges: (Max 100 words)

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

Internal and external constraints (policy, funding, seasonality, political instability, conflict): (Max 100 words)

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

Sensitivities or power dynamics: (Max 100 words)

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

- …………………………….…………………………….…………………………….…………………………….…………………………….………………

# 4. Desk Review

# What We Already Know

Effective engagement builds on what is already documented and focuses community time where it is most needed. If you arrived from Stage A, you already collected a great deal of information in your Stage A worksheets.  You will want to collect these together in one place for easy reference as that information is going to come in hand. In addition to reengaging with the information you collected in Stage A, you will also complete a “desk review” looking at key documents you will need to take account of in undertaking your workshop, assessing risk and beginning to plan adaptation actions.

# 4.1 Stage A Worksheets

In this section, you will link and revisit the worksheets you completed during Stage A. You will not directly use these same worksheets as final answers for your risk assessment. Instead, they act as reference points, a record of your initial thinking, observations, and understanding before moving into deeper engagement.

In Stage A, you worked through these worksheets largely on your own or with a small team. In Stage B, the process shifts. You will begin to listen, test, and expand this understanding with your stakeholders and rights-holders. The values, attributes, hazards, and impacts you identified earlier will be explored again, but this time through dialogue, participation, and multiple knowledge systems in Stage B: Engage.

Because of this, what you documented in Stage A should not be treated as fixed or complete. It is a starting point. By linking your worksheets here, you are creating an easy place to return to them throughout Stage B. You may find that some elements remain relevant, while others evolve, deepen, or even change entirely as new perspectives emerge.

As you review them, take note of:

- what still feels accurate

- what may need updating

- and where there are gaps or uncertainties

These gaps are especially important, as they often point to where your engagement activities can be most meaningful.

If you joined directly in Stage B, this section offers a useful place to begin building your foundation. You are encouraged to review and complete these worksheets now, as they will help orient you before moving into community engagement.

| Stage A Section | Blank Worksheet | Your Worksheets from Stage A |
| --- | --- | --- |
| Values and Stakeholder Mapping | Worksheet 1 - Table of Site Values.docx Worksheet 2 - Value and Attribute Mapping.docx |  |
| Climate Impacts and Risk Assessments | Historical and Present Exposures and Impacts Worksheet.docx Historical and Present Vulnerabilities .docx Historical and Present Response Worksheet.docx Impact Categories Worksheet.docx Bringing Them All Together - Inherent and Residual Impact.docx |  |

# 4.2 Desk Review

Alongside revisiting your Stage A worksheets, this next step invites you to look outward. Before you begin engaging with your community, it is important to understand what already exists in terms of plans, policies, data, and research related to your heritage place or cultural practice.

This is what we call a desk review.

At its simplest, a desk review is a way of gathering and reviewing existing information. It might include site management plans, climate policies, risk assessments, or research reports. Some of this you may already know. Some of it you may need to go looking for online, through institutions, or by asking the right people. The goal is not to collect everything. It is to make sure you have a clear and practical sense of what is already known, what is already planned, and what is missing.

This step helps you:

- avoid repeating work that has already been done

- connect your risk assessment to existing efforts and decision-making processes

- and strengthen the credibility of your work by grounding it in both existing knowledge and identified gaps

It also helps you notice where existing plans and data fall short. You may find that climate risks have been studied without considering heritage. Or that heritage plans exist without addressing climate change. Or that community knowledge has not been captured at all. These gaps are not problems to fix immediately. They are entry points for your engagement activities.

As you complete this section, focus on identifying a small number of relevant documents and sources. Note what they tell you, what they leave out, and what questions they raise. This will ensure that when you move into engagement, you are not starting from scratch, but you are also not limited by what already exists.

| Type of Documentation | Tips for Desk Review | Use this section to list key documents reviewed (noting URLs where applicable), note main insights, gaps, and priority questions to carry into engagement activities and workshops. Make sure to note knowledge gaps, uncertainties, or outdated information |
| --- | --- | --- |
| Existing heritage designations, condition assessments, inventories, or general management plans | This was touched on in Stage A Section 1 |  |
| Existing adaptation, disaster, or climate action policies or plans that cover your site at site, municipal, regional, national and sectoral levels. Note: when you get to the Adaptation Planning (Part 1) Toolkit, you will be asked to elaborate on alignment, gaps and opportunities between these plans and the adaptation actions you are considering. | This was touched on in Stage A Section 2 |  |
| Existing climate projections for your site, if available |  |  |
| Existing climate risk assessments that cover your site, if available | Stage A Unit 2 |  |
| Other existing policies, governance arrangements or legal frameworks influencing the site |  |  |
| Other relevant, existing projects, studies, or reports related to climate, heritage, or development |  |  |
| Areas where plural knowledge systems will be especially important to explore further |  |  |

# 5. Local team and roles

Please add in this section the individuals you anticipate working with to conduct and write your risk assessment and adaptation plan.

| Role | Name(s) | Email(s) | Phone number(s) (What’sApp) | Engagement activities, workshop or both | Responsibilities |
| --- | --- | --- | --- | --- | --- |
| Lead facilitators |  |  |  |  | Design, flow, timekeeping, safety |
| Co-facilitator(s) |  |  |  |  | Group support, mapping |
| Administration lead/support |  |  |  |  | Budget, permissions, transactions… |
| Logistics lead/support |  |  |  |  | Venue, materials, food, … |
| Communication lead/support |  |  |  |  |  |
| Documenter(s) |  |  |  |  | Notes, photos, file naming |
| Documentation lead |  |  |  |  | Coordination, quality control |
| Wellbeing focal point |  |  |  |  | emotional support |
| Report writing lead |  |  |  |  |  |
| Consultant (climate data, …) |  |  |  |  |  |
| ….. |  |  |  |  |  |
| ….. |  |  |  |  |  |
| ….. |  |  |  |  |  |
| ….. |  |  |  |  |  |

# 6. Stakeholder & Rights-Holder List

## Who to Engage?

Over the next 6 steps, you will design the engagement activities that will complete your risk assessment and adaptation planning. Diverse voices must guide the identification of:

STEP 2: Map and Prioritize Places, Values, and Attributes

STEP 3: Explore Present Climate Hazards

STEP 4: Assess Present Climate Impacts

STEP 5: Explore Future Climate Hazards

STEP 6: Assess Future Exploratory Climate Impacts

STEP 7: Develop Comprehensive Future Risk Assessment and Adaptation Strategy .

In order to design these engagement methods and activities, you first need to identify participants - stakeholders and rightsholders - based on process requirements, rather than predefined categories.

They should seek:

- People with deep knowledge of the site, its history, values, changes, and lived realities, who can meaningfully inform a robust climate risk assessment

- Representatives of organisations, agencies, or groups with a formal mandate to preserve, protect, manage, or support the site

- Individuals and groups who are invested in the site’s future and long-term stewardship

- People with expertise or experience in heritage and/or climate-related issues

- Knowledge holders across generations, genders, livelihoods, and knowledge systems

- Those who may be affected by climate risks or adaptation decisions

Depending on context, this may include (but is not limited to):

- Local associations or community groups

- Community elders

- Cultural bearers, artists, craftspeople

- Religious leaders or spiritual knowledge holders

- Youth groups

- Women’s groups

- Farmers, fishers, pastoralists, or other livelihood groups

- Local government representatives

- Researchers or educators

- NGOs or local institutions

- Others relevant to the site and its governance

## 6.2 Stakeholder notes table

Who are the stakeholders and rights holders you need to engage during your engagement activities, and why is their participation essential at this stage? Fill in the table below individuating the group of stakeholders, their relationship to your heritage place or cultural practice, how they best respond to engagement, notes on sensitivity, and themes to explore:

| Group / Individual | Role or relationship to heritage | Preferred engagement method | Inclusion / Sensitivity Notes | Themes you want to explore with them | Notes |
| --- | --- | --- | --- | --- | --- |

# 7. Accessibility, Safeguarding & Care

With a stakeholder and rightsholder list complete, it is now time to think about accessibility for these specific groups or individuals. Use the section below to write down how you will design an inclusive and accessible risk assessment process.

- Languages & interpretation approach: Describe the languages spoken and how interpretation will be provided.

…………………………………………………………………………………………………………………………………………………………

…………………………………………………………………………………………………………………………………………………………

…………………………………………………………………………………………………………………………………………………………

- Accessibility considerations: Note any physical, sensory, gender, age, linguistic or cultural needs.  Consider mobility access, seating arrangements, time of day, childcare, dietary restrictions, and any accommodations for neurodiverse participants.

………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

- Safeguarding & wellbeing measures in place: Outline protocols for participant safety, including informed consent for recordings or photos, safe spaces for sharing, referral pathways for distress, and confidentiality agreements.  Provide contact information for safeguarding leads.

……………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………………

# 8. Data collection, analysis and documentation

It is critical to document all engagement activities and their outcomes with stakeholders and rightsholders throughout the risk assessment and adaptation planning process. This document will support the writing of the climate risk assessment, and the adaptation actions or emerging planning elements developed during Stage B.

How will you document and provide evidence of your climate risk assessment process and the adaptation actions or planning elements developed during Stage B?

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

…………………………….…………………………….…………………………….…………………………….…………………………….………………….…………

Examples might include:

- Risk assessment and adaptation planning reports (e.g., engagement activity reports, synthesis notes, final reports)

- Engagement activities summaries and detailed notes

- Maps, diagrams, and visual outputs

- Documented quotes or stories (with informed consent)

- Attendance records

- Photographs, audio, or video recordings (with informed consent)

- Any additional locally relevant forms of documentation

(Detailed documentation guidance is provided in the Engagement Activities and Workshop Toolkits).

## Quick ethics + documentation checklist (use before every session)

It is not only important to plan how you will collect and document your activities; you must plan for how to gain consent for this documentation. Use the checklist below before your engagement sessions to ensure that you have the appropriate consent and have respective cultural protocols.

- Purpose explained (what this is, what it is not)

- Consent forms shared and collected (recording/photos/quotes):

  - none

  - photos

  - audio

  - video

  - written data

- Data storage location decided (folder/link):

# Cultural protocols respected (sacred knowledge, restricted spaces, etc.)

# 9. Appendices

- Site maps or photos

- Relevant background documents