## Sheet1
AFRUDEC FARM DETAIL IMPLEMENTATION PLAN-2025
|  | SEASON ONE | [23 empty] | SEASON TWO
S/No | ACTIVITIES | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | Responsible person
| WEEKS | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | PRIMARY & SECONDARY TILLAGE OPERATION | [48 empty] | Agronomist | bar: NOV 3 to DEC 2
a | First ploughing | bar: JAN 1 to JAN 4; JUN 1 to JUN 2
b | Second ploughing | bar: FEB 1 to FEB 4; JUN 3 to JUN 4
2 | PROCUREMENT OF SEED AND AGROCHEMICALS | [48 empty] | Agronomist/Finance Assistant
a | Maize | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
b | Sunflower | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
c | Groundnuts | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
d | Rice | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
e | Cassava | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
f | Beans | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
g | Banana | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
h | Pineapple | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
i | Coffee | bar: FEB 1 to FEB 2; JUN 3 to JUN 4
j | Vegetables | bar: FEB 1 to FEB 2; JUN 3 to JUN 4; NOV 1
k | Agrochemicals | bar: FEB 1 to FEB 2; JUN 3 to JUN 4; NOV 1
3 | PLANTING | [48 empty] | Agronomist
a | Maize | bar: MAR 1 to MAR 2; JUL 1 to JUL 2
b | Sunflower | bar: APR 1; JUL 1
c | Groundnuts | bar: MAR 4 to APR 2; AUG 1 to AUG 3
d | Rice | bar: MAY 1; JUL 2 to JUL 3
e | Cassava | bar: MAR 1 to APR 4
f | Beans | bar: MAR 4 to APR 2; JUN 3 to JUN 4
g | Banana | bar: APR 1 to MAY 4
h | Pineapple | bar: APR 1 to MAY 4
i | Coffee | bar: APR 1 to MAY 4
j | Vegetables
4 | CROP PROTECTION | [48 empty] | Agronomist
a | Maize | bar: APR 1 to APR 2; MAY 2 to MAY 3; AUG 1 to AUG 2; SEP 2 to SEP 3
b | Sunflower | bar: APR 4 to MAY 1; MAY 4 to JUN 1; JUL 4 to AUG 1; SEP 1 to SEP 2
c | Groundnuts | bar: MAY 1 to MAY 2; JUN 1 to JUN 2; SEP 2 to SEP 3; OCT 2 to OCT 3
d | Rice | bar: MAY 4 to JUN 2; JUL 2 to JUL 4; AUG 4 to SEP 2; OCT 2 to OCT 4
e | Cassava | bar: MAY 2 to MAY 3; AUG 3 to SEP 2
f | Beans | bar: MAY 1 to MAY 2; JUN 2 to JUN 3; JUL 3 to JUL 4; AUG 4 to SEP 1
j | Banana | bar: JUN 3 to JUL 3; NOV 1 to DEC 4
k | Pineapple | bar: JUN 3 to JUL 3; NOV 1 to DEC 4
l | Coffee | bar: JUN 3 to JUL 3; NOV 1 to DEC 4
m | Vegetables
5 | HARVEST & POST-HARVEST HANDLING | [48 empty] | Agronomist
a | Maize | bar: JUL 2 to AUG 4; DEC 1 to DEC 4
b | Sunflower | bar: AUG 1 to AUG 4; DEC 3 to DEC 4
c | Groundnuts | bar: AUG 3 to SEP 2; DEC 3 to DEC 4
d | Rice | bar: OCT 1 to OCT 4; DEC 3 to DEC 4
e | Cassava | bar: JUL 3 to DEC 4
f | Beans | bar: JUL 2 to AUG 1; NOV 1 to NOV 4
j | Vegetables
6 | STORAGE & MARKETING | [48 empty] | Agronomist/Finance Assistant
a | Maize | bar: SEP 1 to DEC 4
b | Sunflower | bar: SEP 1 to DEC 4
c | Groundnuts | bar: SEP 1 to DEC 4
d | Rice | bar: SEP 1 to DEC 4
e | Cassava | bar: SEP 1 to DEC 4
f | Beans | bar: SEP 1 to DEC 4
g | Vegetables
5 | TRAINING FARNM STAFF OF COFFEE, BANANA AND PINEAPPLE PRODUCTION AND MANAGEMENT | [48 empty] | General Farm Manager | bar: JUN 1 to JUN 2
6 | ESTABLISHMENT OF COFFEE DEMONSTRATION AND MOTHER GARDENS | [48 empty] | General Farm Manager | bar: JUN 1 to AUG 4
7 | APICULTURE | [48 empty] | Animal Husbandry Officer
a | Re-location of site | bar: JUN 1 to JUL 4
b | Smocking | bar: NOV 1 to NOV 2
c | Harvesting | bar: DEC 2 to DEC 4
8 | DEMONSTRATION FISH POND | [48 empty] | Animal Husbandry Officer
a | Restocking | bar: JUN 4 to JUL 1
b | Harvesting | bar: DEC 3 to DEC 4
9 | CONSTRUCTION OF MODERN PIGSTY (HOG BARN) | [48 empty] | General Farm Manager | bar: JUN 1 to OCT 4
10 | FOLLOW-UP ON SMALL-SCALE IRRIGATION TO PADER DISTRICT GOVERNMENT | [48 empty] | General Farm Manager | bar: MAY 1 to JUL 4
11 | EXPOSURE VISITS | [48 empty] | General Farm Manager
a | National Coffee Research Institute (NACORI) | bar: AUG 1; DEC 1
b | Established Similar Farm in Northern Uganda | bar: OCT 4
12 | PERIODIC MONITORING AND FOLLOW UP BY BOG, PTA AND MANAGEMENT TEAM | [48 empty] | General Farm Manager | bar: MAR 4; JUN 4; SEP 4; DEC 4
13 | QUARTERLY REVIEW MEETING | [48 empty] | General Farm Manager | bar: MAR 4; JUN 4; SEP 4; DEC 4
14 | HFU/DONOR VISIT TO THE FARM | [48 empty] | Program oordinator | bar: JUL 1 to JUL 4
15 | REPORTING (Monthly, Quaterly and Annual) | FEB 1: Annual | General Farm Manager