## How to use
AI Use Case Prioritization Framework — Scoring Sheet
ClearWork · free to use and adapt · clearwork.io
1. Fill one canvas per use case first (see the AI Use Case Canvas template). This sheet ranks canvases; it does not frame them.
2. On "Criteria & weights", keep the default weights or change them (yellow cells). They must total 100%.
3. On "Scoring sheet", enter one use case per row. Yellow cells are inputs; white cells are formulas.
4. Gates first: answer Y or N for the four gates. Any N parks the use case; it is not scored into the ranking.
5. Score each criterion 1–5 using the anchored scale on "Criteria & weights". 5 is always better (higher value, simpler, safer).
6. Set Evidence for each row: Validated (confirmed by the people doing the work), Estimated (informed judgment), or Assumed (no evidence yet).
7. Read the Adjusted score and Rank. Then read the Next action column: an unvalidated high-value use case is a discovery task, not a pilot.
Evidence multipliers: Validated 1.00 · Estimated 0.85 · Assumed 0.70 (editable on "Criteria & weights").
Quadrant: Quick win (value ≥ 3.5, feasibility ≥ 3.5) · Strategic bet (value ≥ 3.5, feasibility < 3.5) · Fill-in (value < 3.5, feasibility ≥ 3.5) · Deprioritize (both < 3.5). Feasibility = average of data readiness, process clarity and technical simplicity.
"Worked example" shows six use cases scored end to end. The example row on "Scoring sheet" (row 6) can be overwritten.

## Criteria & weights
Criteria, weights and anchored scales
# | Criterion | Weight | 1 = | 3 = | 5 =
1 | Business value | 25% | Under $50k/yr or no baseline | $50k–$250k/yr, baseline measured | Over $250k/yr or revenue/risk impact, baseline measured
2 | Strategic fit | 10% | Nobody senior is asking for it | Supports a stated goal | Named in the strategy and sponsored by an executive
3 | Data readiness | 15% | Data does not exist or cannot be accessed | Exists, needs cleaning or joining | Clean, accessible, labeled examples available
4 | Process clarity | 15% | How the work is done is undocumented or disputed | Documented but not checked with the people doing it | Current state validated by the people doing the work, exceptions listed
5 | Technical simplicity | 10% | New platform, many integrations, custom models | One or two integrations, proven pattern | Off-the-shelf capability in tools you already run
6 | Risk containment | 10% | A wrong answer is costly and hard to catch | A wrong answer is caught in review | A wrong answer is cheap and obvious; easy human override
7 | Adoption readiness | 15% | Users not consulted; workflow change is large | Users consulted; moderate change | Users asked for it; fits the current workflow
| Total (must be 100%) | 100% | OK
Evidence multipliers
| Evidence | Multiplier | Meaning
| Validated | 1 | Scores rest on a current state confirmed by the people doing the work
| Estimated | 0.85 | Informed judgment by the process owner or team; not checked with the doers
| Assumed | 0.7 | No evidence yet; a placeholder until discovery is done
Quadrant thresholds
| Value threshold | 3.5
| Feasibility threshold | 3.5

## Scoring sheet
Scoring sheet — one row per use case
Yellow = input. Gates: Y/N. Scores: 1–5 (5 is better). Evidence: Validated / Estimated / Assumed.
Use case | G1 Owner + baseline | G2 Permissible | G3 Data exists | G4 Process described | Business value | Strategic fit | Data readiness | Process clarity | Technical simplicity | Risk containment | Adoption readiness | Evidence | Gate | Weighted score | Adjusted score | Feasibility | Quadrant | Rank | Next action
Example: replace with your first use case | Y | Y | Y | Y | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Estimated | PASS | 3 | 2.55 | 3 | Deprioritize | 1 | Shortlist for pilot
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## Worked example
Worked example — six use cases from a mid-sized operations team (illustrative)
Yellow = input. Gates: Y/N. Scores: 1–5 (5 is better). Evidence: Validated / Estimated / Assumed.
Use case | G1 Owner + baseline | G2 Permissible | G3 Data exists | G4 Process described | Business value | Strategic fit | Data readiness | Process clarity | Technical simplicity | Risk containment | Adoption readiness | Evidence | Gate | Weighted score | Adjusted score | Feasibility | Quadrant | Rank | Next action
AP invoice exception routing | Y | Y | Y | Y | 5 | 3 | 3 | 2 | 3 | 3 | 4 | Estimated | PASS | 3.5 | 2.975 | 2.6667 | Strategic bet | 3 | Run discovery, then rescore
Customer email triage | Y | Y | Y | Y | 3 | 3 | 4 | 4 | 4 | 4 | 4 | Validated | PASS | 3.65 | 3.65 | 4 | Fill-in | 2 | Shortlist for pilot
Contract clause extraction | Y | Y | Y | Y | 4 | 4 | 3 | 3 | 3 | 2 | 3 | Estimated | PASS | 3.25 | 2.7625 | 3 | Strategic bet | 4 | Run discovery, then rescore
Sales forecast assistant | Y | Y | Y | Y | 5 | 5 | 3 | 2 | 3 | 3 | 4 | Assumed | PASS | 3.7 | 2.59 | 2.6667 | Strategic bet | 5 | Run discovery, then rescore
IT ticket triage | Y | Y | Y | Y | 4 | 2 | 5 | 4 | 4 | 4 | 5 | Validated | PASS | 4.1 | 4.1 | 4.3333 | Quick win | 1 | Shortlist for pilot
Onboarding knowledge assistant | N | Y | Y | Y | 3 | 3 | 2 | 1 | 4 | 4 | 3 | Assumed | PARK | 2.75 | 1.925 | 2.3333 | Deprioritize | - | Parked: fix the failed gate first
-
-
-
-
-
-
-
-
-
Illustrative scores, not benchmarks. Read the Adjusted score and Next action columns: the sales forecast assistant ranks 2nd on the weighted score and 5th once its assumed evidence is discounted; AP routing has the highest value but needs discovery before a pilot.