## Master Timeline
MASTER TIMELINE - Event Run of Show
HOW TO USE: This is your single source of truth on event day. Only ONE person edits live. Everyone else uses view access. Update the Status column in real time. Log any timing changes in the Issues Log tab.
Start Time | End Time | Duration (min) | Segment Name | Segment Type | Lead Owner | Backup Owner | Room / Location | Vendor Confirmed? | Coordination Notes | Risk Level | Fallback Action | Status
PRE-EVENT SETUP
7:00 AM | 7:30 AM | 30 | Venue access & load-in | Setup | Operations Mgr | Floor Lead | Loading dock / Main hall | Y | Confirm dock access with venue by 6:45 AM | Low | - | Ready
7:30 AM | 8:00 AM | 30 | AV & production check | Setup | AV Vendor Lead | Stage Mgr | Main stage | Y | Vendor running own check - confirm completion by 8:00 | Med | Push check-in start by 10 min | Ready
7:45 AM | 8:15 AM | 30 | Registration setup | Setup | Registration Lead | Ops Mgr | Lobby entrance | Y | Confirm badge printer and scanner test by 8:00 | Low | - | Ready
8:00 AM | 8:15 AM | 15 | Staff briefing | Briefing | Operations Mgr | Floor Lead | Backstage / staff area | - | Cover timeline, escalation contacts, and key cues | Low | - | Ready
GUEST ARRIVAL & PROGRAM
8:30 AM | 9:00 AM | 30 | Registration & check-in open | Registration | Registration Lead | Check-in Staff | Lobby entrance | Y | Staff positioned by 8:20 - confirm with staffing lead | Med | Open secondary entrance if lines exceed 5 min wait | Ready
8:30 AM | 9:00 AM | 30 | Welcome coffee & networking | F&B | Caterer Contact | Floor Lead | Lobby / foyer | Y | F&B timing confirmed with caterer - service ends 8:55 | Low | - | Ready
9:00 AM | 9:05 AM | 5 | Opening remarks | Program | Emcee / Host | Lead Producer | Main stage | Y | AV vendor has walk-in music and opening slide queued | Low | - | Ready
9:05 AM | 9:45 AM | 40 | Keynote presentation | Program | Lead Producer | Stage Mgr | Main stage | Y | Speaker slide deck received and loaded - confirm at 8:30 | High | Shorten Q&A to recover if keynote runs long | Ready
9:45 AM | 9:50 AM | 5 | BUFFER - Post-keynote recovery | Buffer | Lead Producer | - | - | - | If on time, use as quick break. If behind, absorb delay here. | - | - | -
9:50 AM | 10:30 AM | 40 | Panel discussion | Program | Moderator | Stage Mgr | Main stage | Y | 3 panelists confirmed - mic check by 9:30 | Med | Cut final audience question if timing slips | Ready
10:30 AM | 10:45 AM | 15 | Networking break | Break | Floor Lead | Ops Mgr | Lobby / expo area | Y | Confirm refreshment station with caterer by 10:00 | Low | Shorten to 10 min if running behind | Ready
MID-PROGRAM
10:45 AM | 11:30 AM | 45 | Breakout Session A - Track 1 | Breakout | Session Moderator | Floor Lead | Breakout Room A | Y | Room reset confirmed with venue - AV check by 10:30 | Med | Delay start 5 min max, cut closing remarks | Ready
10:45 AM | 11:30 AM | 45 | Breakout Session B - Track 2 | Breakout | Session Moderator | Floor Lead | Breakout Room B | Y | Room reset confirmed with venue - AV check by 10:30 | Med | Delay start 5 min max, cut closing remarks | Ready
11:30 AM | 11:35 AM | 5 | TRANSITION - Room release to main stage | Transition | Floor Lead | Crowd Mgmt | Hallways | - | Stagger room releases by 2 min to reduce hallway congestion | Med | Hold Room B release if hallway crowded | -
11:35 AM | 12:15 PM | 40 | Closing keynote | Program | Lead Producer | Stage Mgr | Main stage | Y | Speaker confirmed and slide deck loaded | Med | - | Ready
12:15 PM | 12:20 PM | 5 | Closing remarks & wrap | Program | Emcee / Host | Lead Producer | Main stage | - | Thank sponsors, announce next steps | Low | - | Ready
POST-EVENT
12:20 PM | 1:00 PM | 40 | Lunch service / networking | F&B | Caterer Contact | Floor Lead | Dining area | Y | Lunch timing confirmed with caterer - stations open by 12:15 | Low | - | Ready
1:00 PM | 2:00 PM | 60 | Breakdown & load-out | Breakdown | Operations Mgr | Floor Lead | All areas | Y | Venue requires clear-out by 2:00 PM - confirm with venue mgr | Low | - | Ready

## Speaker & Content
SPEAKER & CONTENT LOG
HOW TO USE: Track speaker confirmations and content delivery. This tab keeps presentation details off the Master Timeline so the live schedule stays clean. Share relevant rows with your AV vendor so they can pre-load decks.
Time Slot | Segment Name | Speaker / Presenter | Topic / Title | Slide Deck Received? | Slide Deck Link | Introduction Notes | Special Requirements | Speaker Contact | Status
9:05–9:45 AM | Keynote presentation | Jane Smith | The Future of Experiential Marketing | Yes | [link to deck] | Introduced by emcee - 30-second bio provided | Clicker, confidence monitor, water on stage | jane@company.com | Confirmed
9:50–10:30 AM | Panel discussion | 3 panelists (see notes) | Building Teams That Scale | N/A - no slides | - | Moderator introduces each panelist | 3 handheld mics, panel seating, timer visible | moderator@email.com | Confirmed
10:45–11:30 AM | Breakout A | Mark Johnson | Data-Driven Event Planning | Yes | [link to deck] | Self-introduction - no emcee needed | Laptop hookup, whiteboard | mark@company.com | Confirmed
10:45–11:30 AM | Breakout B | Sarah Lee | Sponsor ROI Measurement | Pending | - | Introduced by session moderator | Standard AV setup | sarah@company.com | Deck pending
11:35 AM–12:15 PM | Closing keynote | CEO / Keynote | Closing Vision | Yes | [link to deck] | Introduced by emcee - full bio provided | Teleprompter, confidence monitor | ceo@company.com | Confirmed

## Staffing Coordination
STAFFING COORDINATION
HOW TO USE: This is NOT a task list for your staff - it's your confirmation tracker. Record WHO is handling each role, WHEN they arrive, and whether they've been briefed. Your staffing provider or venue team handles the operational details for their people.
Role | Assigned To / Provider | Headcount | Shift Start | Shift End | Location / Zone | Reports To | Briefing Time | Confirmed? | Coordination Notes
PRODUCTION & AV
AV / Production Team | Vendor: [AV Company Name] | 4 | 6:30 AM | 2:00 PM | Main stage + breakouts | AV Vendor Lead | 7:00 AM | Y | Vendor manages own crew - confirm load-in access by 6:15 AM
Stage Manager | [Name] | 1 | 7:00 AM | 1:30 PM | Main stage | Lead Producer | 7:15 AM | Y | Manages speaker walk-ons and stage cues
REGISTRATION & GUEST FLOW
Check-in Staff | Provider: [Staffing Co] | 4 | 7:45 AM | 10:00 AM | Lobby entrance | Registration Lead | 8:00 AM | Y | Staffing provider confirmed - badges and scanners tested
Crowd Management | Provider: [Staffing Co] | 3 | 8:00 AM | 1:00 PM | Hallways + main entrance | Floor Lead | 8:00 AM | Y | Cover hallway transitions between breakout sessions
Greeters / Ushers | Provider: [Staffing Co] | 2 | 8:15 AM | 12:30 PM | Main entrance + breakout rooms | Floor Lead | 8:00 AM | Y | Direct attendees to correct rooms during breakouts
FOOD & BEVERAGE
Catering Team | Vendor: [Caterer Name] | 6 | 7:00 AM | 2:00 PM | Lobby (AM) + Dining (lunch) | Caterer Contact | 7:15 AM | Y | Caterer manages their own staff - confirm service windows
Bartenders | Provider: [Staffing Co] | 2 | 11:30 AM | 1:30 PM | Dining area bar | Caterer Contact | 11:15 AM | Y | Bar opens at 12:15 PM - confirm setup with caterer by 11:45
OPERATIONS & MANAGEMENT
Lead Producer / Show Caller | [Name] | 1 | 6:30 AM | 2:00 PM | Backstage / mobile | - | - | Y | Single point of authority for all timing decisions
Operations Manager | [Name] | 1 | 6:30 AM | 2:30 PM | Mobile - all zones | Lead Producer | - | Y | Manages vendor coordination and issue escalation
Floor Lead | [Name] | 1 | 7:00 AM | 2:00 PM | All guest-facing areas | Operations Mgr | 7:15 AM | Y | Owns attendee flow and room release timing

## Sponsor Activations
SPONSOR ACTIVATIONS
HOW TO USE: Track sponsor timing windows and confirm setup. The brand team manages their own activation details (measurement, staffing, creative). Your job is making sure their time slot doesn't conflict with the main program and their setup is confirmed.
Activation Name | Sponsor / Brand | Brand Contact | Time Window | Location | Setup Confirmed? | Staff Assigned? | Activation Type | Coordination Notes | Status
Product demo booth | Sponsor A | contact@sponsorA.com | 8:30 AM – 12:30 PM | Expo floor - Booth 1 | Y | Y - brand's own team | Interactive demo | Brand brings own equipment - confirm power supply with venue | Confirmed
Branded lounge | Sponsor B | contact@sponsorB.com | 8:30 AM – 1:00 PM | Lobby lounge area | Y | Y - brand's own team | Experiential | Lounge opens with registration - brand managing their own signage | Confirmed
Keynote intro sponsorship | Sponsor C | contact@sponsorC.com | 9:00 – 9:05 AM | Main stage | Y | N/A - emcee reads | Verbal mention + logo | 60-second sponsor mention before opening remarks - script confirmed | Confirmed
Networking break activation | Sponsor A | contact@sponsorA.com | 10:30 – 10:45 AM | Lobby near coffee station | Pending | Y - brand's team + 2 staff | Sampling / giveaway | Confirm setup doesn't block coffee line - discuss with caterer | Setup pending
Post-event survey + raffle | Sponsor D | contact@sponsorD.com | 12:15 – 12:45 PM | Dining area entrance | Y | Y - brand's team | Digital engagement | QR code display - brand handles data collection | Confirmed

## Issues Log
ISSUES LOG - Day-of Changes & Decisions
HOW TO USE: Log every timing change, issue, and decision here during the live event. This creates a single record so all teams work from the same information. Review after the event for post-mortem learnings.
Time Logged | Issue Description | Affected Segment | Impact Level | Decision Made | Decided By | Communicated To | Resolved? | Notes
9:42 AM | Keynote running 5 min over expected time | Keynote presentation | High | Absorb with post-keynote buffer - no downstream change | Lead Producer | Stage Mgr, Floor Lead | Y | Buffer row used as intended - program back on track by 9:55
10:32 AM | Refreshment station delayed - caterer needed 3 extra min | Networking break | Low | Extend break to 10:48 - shorten next transition by 3 min | Ops Manager | Caterer, Floor Lead | Y | Caterer resolved quickly - minimal guest impact
11:28 AM | Breakout Room B speaker laptop not connecting to projector | Breakout Session B | Med | AV vendor switching to backup laptop - 3 min delay | AV Vendor Lead | Session Moderator, Ops Mgr | Y | Resolved by 11:33 - session started 3 min late