## Enterprise AI Transformation Ch
Domain | Question | Answer
Strategy & Governance | Published AI strategy aligned to corporate goals
Defined AI North Star metrics and value themes
AI Council or governance board in place
Risk tiers and review processes defined (aligned with NIST/ISO guidance)
AI ethics and acceptable-use policy documented
Organization & Talent | Named executive owner (CIO/CTO/CDO) for AI outcomes
Central AI/ML platform team staffed
Embedded AI product teams in at least one BU
Training programs for executives and frontline staff
Hiring / upskilling plan for critical AI skills
Data & Platform | Unified data platform with catalog and lineage
AI sandboxes and workbenches for experimentation
Initial vector/RAG infrastructure for knowledge use cases
MLOps tooling for versioning, CI/CD and monitoring
Cost governance in place for AI workloads
Portfolio & Delivery | Central AI initiative portfolio with prioritization criteria
2–3 lighthouse use cases identified with clear KPIs
Standard delivery lifecycle (discovery → pilot → production → scale)
Playbooks and templates for common patterns (RAG assistants, copilots, classification models)
Regular portfolio reviews and retrospectives
Adoption & Change Management | AI literacy programs underway
Co-design workshops with end-users for key workflows
Communication plan for AI initiatives (why, what, how)
Metrics for adoption and satisfaction per AI solution
Mechanisms for continuous feedback and improvement

## Enterprise AI Transformation Ro
Disclaimer: The timelines outlined are indicative and for illustrative purposes only. Actual implementation timelines may vary based on project complexity and detailed requirements.
Phase | Outcome | Category | Actions | Timeline
|  |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15+
Phase 1 | Strategy, Assessment & Foundations | AI Strategy & North Star | Define 3–5 strategic AI objectives tightly linked to corporate goals. | bar: Timeline Month 1
Example: “Reduce claims processing time by 30% in 12 months,” “Increase revenue per seller by 10% with AI copilot support.” | bar: Timeline Month 1
|  | Maturity & Readiness Assessment | Use frameworks from MIT CISR, McKinsey, Deloitte or Appinventiv to assess current maturity across strategy, data, tech, org, skills and governance. | bar: Timeline Month 1
Identify critical gaps blocking scale (for example, missing data catalog, no AI governance council). | bar: Timeline Month 1
|  | Design AI Operating Model | Decide on central vs. federated structures and define the CoE role. | bar: Timeline Month 2
Stand up an AI governance council and draft initial policies (risk tiers, review processes, acceptable use, data handling). | bar: Timeline Month 2
Identify initial platform investments (data lakehouse, vector DB, MLOps tools). | bar: Timeline Month 2
|  | Foundational Initiatives | Launch AI literacy program for executives and key business leaders. | bar: Timeline Month 1 to Timeline Month 3
Start consolidating critical data sources and improving information architecture, especially in collaboration suites (Microsoft 365, Google Workspace). | bar: Timeline Month 1 to Timeline Month 3
Phase 2 | High-Impact Pilots on Shared Platforms | Use-Case Selection & Design | Run cross-functional workshops to prioritize 5–10 candidate use cases by business value and feasibility. | bar: Timeline Month 4
Select 2–3 lighthouse use cases across different functions (for example, customer support knowledge assistant, finance forecasting assistant, sales copilot). | bar: Timeline Month 4
|  | Pilot Build on Common Platform | Build each use case on shared data and AI platforms, not bespoke stacks. | bar: Timeline Month 5
Implement human-in-the-loop workflows and define clear KPIs upfront (time saved, accuracy, satisfaction, revenue impact). | bar: Timeline Month 5
|  | Governance & Risk Controls in Pilots | Classify each use case by risk tier and apply appropriate review/approval steps. | bar: Timeline Month 5
Capture documentation for models, prompts, training data and evaluation. | bar: Timeline Month 5
|  | Measurement & Case Studies | Run pilots for 8–12 weeks; collect robust before/after measurements. | bar: Timeline Month 5 to Timeline Month 7
Create internal case studies highlighting value, lessons and user feedback. | bar: Timeline Month 6 to Timeline Month 7
Phase 3 | Scale Successful Pilots & Harden the Platform | Productionization of Pilots | Promote the most successful pilot(s) to production following a pilot-to-production framework. | bar: Timeline Month 7 to Timeline Month 8
Add SLAs, monitoring, incident response and rollback mechanisms. | bar: Timeline Month 7 to Timeline Month 8
|  | Platform Hardening | Expand MLOps capabilities for versioning, CI/CD, monitoring and cost governance. | bar: Timeline Month 8
Standardize APIs, SDKs and templates for new AI projects. | bar: Timeline Month 8
Implement role-based access control and audit logging across AI services. | bar: Timeline Month 8
|  | Operating Model in Practice | Embed AI product managers and ML engineers in 1–2 business units. | bar: Timeline Month 9
Run quarterly portfolio reviews via the AI Council to reprioritize initiatives. | bar: Timeline Month 9
|  | Change Management & Training at Scale | Offer training programs for frontline users on new AI tools. | bar: Timeline Month 9
Launch communities of practice and internal “AI champions” networks. | bar: Timeline Month 9
Phase 4 | Expand Across Functions, Embed “AI Ways of Working” | Scale to Adjacent Use Cases | Use successful pilots as blueprints for similar workflows in other BUs or geographies (for example, claims summarization → underwriting support → risk reporting). | bar: Timeline Month 10 to Timeline Month 12
Reuse prompts, patterns, and components wherever possible. | bar: Timeline Month 10 to Timeline Month 12
|  | Institutionalize AI Product Management | Require every major AI initiative to have a named product owner, clear KPIs and a roadmap. | bar: Timeline Month 10 to Timeline Month 12
Adopt a “crawl-walk-run” approach: assistive → augmentative → autonomous. | bar: Timeline Month 10 to Timeline Month 12
|  | AI in the Operating Rhythm | Include AI metrics in regular business reviews (for example, quarterly operations reviews). | bar: Timeline Month 12 to Timeline Month 14
Integrate AI considerations into budgeting, portfolio planning and performance management. | bar: Timeline Month 12 to Timeline Month 14
|  | Governance & Risk Maturity | Align with frameworks such as NIST AI RMF and consider pursuing ISO 42001 certification for AI governance, as organizations like Zendesk have done. | bar: Timeline Month 13 to Timeline Month 14
Conduct regular model audits and scenario reviews for high-impact use cases. | bar: Timeline Month 13 to Timeline Month 14
Phase 5 | Toward “AI Future Ready” | Explore new AI-enabled business models and agentic systems once foundations are stable. | AI agents coordinating multi-step processes (for example, end-to-end loan processing, complex field-service scheduling)
New data and AI products offered to customers or partners
Enterprise-as-code concepts where aspects of the operating model are captured as code and policies.