This project has received funding from the European Union’s Horizon 2020 research and innovation programme under grant agreement No 957824

# Implementation plan for common eSAF recommendations based on national initiatives

# Tool 2.14

There are many factors that must be included in a political implementation process related to aviation policy issues.

The first checklist supports the implementation plan by offering a step-by-step model for turning national sustainable aviation proposal, such as Denmark’s 2024 policy, into actionable measures. It is as a transferable template to help both public and private stakeholders to structure efforts, align goals, and coordinate roles in advancing eSAF adoption and broader aviation sustainability.

| Step-by-Step implementation model National sustainable aviation proposal – A transferable model Objective: To demonstrate and promote a way to a more sustainable aviation through private end public support. Based on Danish governments aviation policy decisions 2024 |  |  |  |
| --- | --- | --- | --- |
| Step | Element | Description |  |
| 1 | Political anchoring | Identify sustainable aviation as a strategic objective in national climate plans or aviation strategies |  |
| 2 | Definition of tender/project | Define route or technology, SAF/eSAF (electric-long term), climate emission reduction requirements, and minimum share of future operation |  |
| 3 | Financing model | Clarify financial needs and identify support mechanisms: direct subsidies, charges, green fund, public-private partnership |  |
| 4 | EU approval | Prepare state aid notification and engage with the EU Commission (DG COMP) – follow CEEAG rules |  |
| 5 | Execution and partnership | Enter agreements with airlines, fuel producers, providers, airports, authorities, researchers, and specialists |  |
| 6 | MRV and traceability | Implement Monitoring, Reporting, and Verification (MRV) systems and include use of the Union Database (UDB) for fuel traceability |  |
| 7 | Evaluation and learning | Set up ongoing evaluation to support scaling up and transfer of knowledge national and internationally |  |

The second checklist provides a structured approach by turning national initiatives into coordinated actions. It breaks the process into concrete steps, helping stakeholders plan, align, and track progress in the national implementation of eSAF recommendations.

| Checklist for National Implementation |  |  |
| --- | --- | --- |
| Area | Key question |  |
| Strategy | Is a future sustainable aviation anchored in national objectives? |  |
| Market | Are there operators, producers, and suppliers ready to participate? |  |
| Legislation | Is the national legal framework compatible with public tenders, project implementation models etc.? |  |
| Other aspects | Be aware of criticism and scepticism regarding SAF sustainability content etc. |  |
| Financing | Is there clarity on cost options, coverage and sources of funding, subsidies or? |  |
| EU Approval | Has the model, tender or project been notified and approved by the EU (DG COMP)? |  |
| Infrastructure | Is SAF availability, quality, certification, refueling, and logistics infrastructure in place, available or planned? |  |
| Data & MRV | Are there systems for monitoring and verification (MRV/UDB)? |  |
| Communication | Is the purpose clearly communicated to citizens and industry, media/PR? |  |
| Scaling Up | Are there plans for learning and replication to other airlines, airports, routes? |  |
| Technology development | Preparation of developments, investments, and prioritized areas of focus (SAF, eSAF, electrification etc. |  |