## Migration Playbook
Webflow Migration Playbook
The step-by-step checklist LBT uses to move B2B startups to Webflow without losing SEO. Tick Status as you go. Yellow callout rows flag where a specialist should check the work.
How to use: work top to bottom — each phase depends on the one above it. Set Status to Done / In progress / Not started. Assign an Owner. See the Content Audit and Redirect Map tabs for the two working sheets.
Phase | Step | Task | Type | Detail | Owner | Status
0 - Readiness Gate | 0.1 | Confirm content is ready and signed off before any build starts | Checklist | Content readiness is the single biggest timeline killer, not the build. Lock copy and assets first. |  | Not started
0 - Readiness Gate | 0.2 | Assign one migration owner to steward the project end to end | Checklist | Migrations stall when nobody owns stakeholder feedback and decisions. Name one person. |  | Not started
0 - Readiness Gate | 0.3 | Check the calendar: no product launch or fundraise in the migration window | Checklist | The worst time to migrate is mid-launch or mid-raise. Best time is right after either closes. |  | Not started
0 - Readiness Gate | 0.4 | Capture baseline metrics BEFORE touching anything | Checklist | Record current LCP, mobile PageSpeed score, monthly organic traffic, and non-brand keyword rankings. You cannot prove success without a baseline. |  | Not started
0 - Readiness Gate | 0.5 | Define what success looks like | Checklist | Agree the target: speed-to-market, performance scores, ranking recovery timeline, publishing independence. |  | Not started
0 - Readiness Gate | CALLOUT | When to bring in help | Callout | Most self-run migrations fail at Phase 0: they skip the baseline and cannot tell later whether the move helped or hurt. If SEO matters, lock this phase before proceeding.
1 - Audit and Inventory | 1.1 | Run a full site crawl | Checklist | Use Screaming Frog or Sitebulb. Export URL list, meta titles, meta descriptions, and status codes. See the Content Audit sheet. |  | Not started
1 - Audit and Inventory | 1.2 | Tag every URL: keep, consolidate, or kill | Checklist | Pages with zero traffic and zero backlinks in 12 months can usually be killed. Log the decision per URL. |  | Not started
1 - Audit and Inventory | 1.3 | Flag protected URLs | Checklist | Mark high-traffic and backlinked URLs as protected. These cannot be dropped or broken during the move. |  | Not started
1 - Audit and Inventory | 1.4 | Inventory plugins and their functions | Checklist | Note what each active plugin does. Identify which have Webflow-native equivalents and which get dropped. |  | Not started
1 - Audit and Inventory | 1.5 | Export a clean URL structure map | Checklist | Review slug patterns. Flag inconsistent or overly nested URLs to standardize in the new build. |  | Not started
1 - Audit and Inventory | CALLOUT | When to bring in help | Callout | If the crawl surfaces more than a few hundred URLs or a tangled legacy structure, an audit done wrong here compounds through every later phase.
2 - CMS Architecture | 2.1 | Map content types to Webflow collections | Checklist | Static pages stay static. Blog posts, case studies, and team members become CMS Collections. |  | Not started
2 - CMS Architecture | 2.2 | Define collection fields | Checklist | Per collection, plan the fields: title, slug, body, author, category, featured image, published date, meta title, meta description, reading time. |  | Not started
2 - CMS Architecture | 2.3 | Set up reference fields correctly | Checklist | Authors and Categories must be Reference fields, not plain text. Plain-text authors become a maintenance nightmare after post 40. |  | Not started
2 - CMS Architecture | 2.4 | Plan collection relationships | Checklist | Decide Reference vs Multi-Reference for posts-to-authors and posts-to-categories before the build. |  | Not started
2 - CMS Architecture | 2.5 | Finalize URL structure | Checklist | Simplify slugs, remove unnecessary nesting, and standardize patterns across the site. |  | Not started
2 - CMS Architecture | 2.6 | Decide what NOT to migrate | Checklist | Retire low-value pages and outdated posts now rather than porting them by default. |  | Not started
2 - CMS Architecture | CALLOUT | When to bring in help | Callout | Reference-field and filtering decisions are hard to undo after content is imported. Getting the schema right before the build saves weeks of rework.
3 - Redirect Map | 3.1 | Build the redirect map: every old URL to its new equivalent | Checklist | One row per old URL. Miss a URL and Google drops it from the index. See the Redirect Map sheet. |  | Not started
3 - Redirect Map | 3.2 | Match orphaned-but-linked pages to closest topical match | Checklist | Pages with backlinks but no traffic get redirected to the nearest relevant page, not deleted. |  | Not started
3 - Redirect Map | 3.3 | Upload the redirect map to Webflow | Checklist | Add as 301 redirects in Webflow Publishing settings. CSV upload supported. |  | Not started
3 - Redirect Map | 3.4 | Test every redirect resolves correctly | Checklist | Verify each redirect returns 301 and lands on the right page. Log tested and live status per row. |  | Not started
3 - Redirect Map | CALLOUT | When to bring in help | Callout | Phase 3 is where most self-run migrations lose rankings. If you have measurable organic traffic, have a specialist check the redirect map before launch.
4 - Content and Metadata | 4.1 | Export source content | Checklist | For WordPress, use WP All Export to pull posts and metadata as CSV or XML. |  | Not started
4 - Content and Metadata | 4.2 | Clean content in a spreadsheet | Checklist | Strip shortcodes, fix broken rich-text formatting, and normalize custom fields before import. |  | Not started
4 - Content and Metadata | 4.3 | Import to Webflow CMS | Checklist | Import the cleaned CSV into the matching collections. Expect manual cleanup on rich text and embeds. |  | Not started
4 - Content and Metadata | 4.4 | Preserve metadata | Checklist | Move meta titles, descriptions, canonical tags, and Open Graph data with each page. Preserve now, optimize later. |  | Not started
4 - Content and Metadata | 4.5 | Rebuild structured data | Checklist | Rebuild schema (Organization, BlogPosting, Product, FAQPage) in Webflow CMS or via custom code embeds. Lost schema loses rich results. |  | Not started
4 - Content and Metadata | 4.6 | Rebuild internal linking | Checklist | Reconstruct the internal link graph. Google uses internal links to understand site architecture. |  | Not started
4 - Content and Metadata | 4.7 | Spot-check 20 to 30 key pages | Checklist | Confirm meta, canonicals, and OG data transferred correctly on your most important pages. |  | Not started
4 - Content and Metadata | GOTCHA | Source platform gotchas | Note | WordPress: shortcode and custom-field cleanup. Wix: no clean export, content moves manually. Squarespace: exports blog and pages as XML, ecommerce does not map. Framer: no clean export, rebuild manually. Custom Next.js or Silverstripe: API or DB export then CSV cleanup.
5 - Launch and Monitoring | 5.1 | Regenerate XML sitemap and robots.txt on Webflow | Checklist | Confirm both are correct before cutover. |  | Not started
5 - Launch and Monitoring | 5.2 | DNS cutover | Checklist | Point the domain to Webflow. Confirm SSL and www vs non-www resolve. |  | Not started
5 - Launch and Monitoring | 5.3 | Submit new sitemap to Google Search Console on launch day | Checklist | Do this the day you launch. Do not wait. |  | Not started
5 - Launch and Monitoring | 5.4 | Test redirects live in production | Checklist | Re-verify the full redirect map resolves on the live site. |  | Not started
5 - Launch and Monitoring | 5.5 | Monitor GSC coverage daily for the first two weeks | Checklist | Watch indexed pages and coverage errors, then monitor for the full first 30 days. |  | Not started
5 - Launch and Monitoring | 5.6 | Expect a dip, do not panic | Note | A 5 to 15 percent traffic dip in the first two weeks is normal reindexing. Full recovery is typical by week six. |  | Not started
5 - Launch and Monitoring | SCOPE CHECK | Scope check | Callout | Worked through this and realized it is more than your team can steward? Send us your site and we will return a scoped migration plan, timeline, and quote in 48 hours.

## Content Audit
Content Audit & Inventory
One row per URL from your Screaming Frog / Sitebulb crawl. Tag each: keep, consolidate, or kill. Sample rows are illustrative — replace them. Yellow cells are for you to fill.
Old URL | Page Title | Meta Title | Meta Description | Status Code | Monthly Organic Traffic | Backlinks | Decision (keep/consolidate/kill) | Protected? (Y/N) | Notes
olddomain.com/ | Home | Home ¦ Acme | Acme helps B2B teams do X | 200 | 1200 | 45 | keep | Y | Primary landing page
olddomain.com/pricing.html | Pricing | Pricing ¦ Acme | See Acme plans and pricing | 200 | 320 | 8 | keep | Y | High-intent page
olddomain.com/features/analytics/ | Analytics | Analytics ¦ Acme | Acme analytics features | 200 | 90 | 3 | keep | N
olddomain.com/blog/wordpress-to-webflow-2023 | Old blog post |  |  | 200 | 15 | 12 | consolidate | Y | Has backlinks, redirect to new resource
olddomain.com/team/john-doe/ | Team member |  |  | 200 | 0 | 0 | kill | N | Zero traffic, zero backlinks
olddomain.com/blog/category/product-updates/ | Category archive |  |  | 200 | 5 | 0 | consolidate | N | Redirect to filtered resources view
[Add one row per URL from your Screaming Frog or Sitebulb export]

## Redirect Map
301 Redirect Map
Every old URL marked keep or consolidate in the audit needs a row here. Miss a URL and Google drops it from the index. Upload as 301s in Webflow Publishing settings, then test each live.
Old URL | New URL | Redirect Type | Reason | Uploaded to Webflow? (Y/N) | Tested Live? (Y/N)
olddomain.com/product-page/ | newdomain.com/product | 301 | Direct match
olddomain.com/features/analytics/ | newdomain.com/product/analytics | 301 | Restructured under product
olddomain.com/blog/wordpress-to-webflow-2023 | newdomain.com/resources/wordpress-to-webflow | 301 | Blog moved to resources
olddomain.com/case-study/acme-inc | newdomain.com/work/acme-inc | 301 | Case studies moved to work
olddomain.com/team/john-doe/ | newdomain.com/about#team | 301 | Team consolidated onto about
olddomain.com/careers.html | newdomain.com/careers | 301 | Extension dropped
olddomain.com/pricing.html | newdomain.com/pricing | 301 | Extension dropped
olddomain.com/blog/category/product-updates/ | newdomain.com/resources?category=product-updates | 301 | Category to filtered view
olddomain.com/wp-content/uploads/2022/ebook.pdf | newdomain.com/resources/ebook | 301 | Asset moved to resources
olddomain.com/thank-you/ | newdomain.com/thank-you | 301 | Direct match
[Add one row per old URL: every audit URL marked keep or consolidate needs a redirect]