## Risk Assessment
Get a Free Forever Oboloo Account
Oboloo Free Contract Risk Assessment Template
download this free procurement template or sign up for a free forever oboloo account to manage suppliers, contracts, savings, sourcing & procurement workflows in one place
Risk ID | Contract ID | Supplier Name | Risk Category | Risk Description | Likelihood | Impact | Risk Score | Mitigation Plan | Owner | Status | Review Date | Risk Level | Comments
RISK-001 | CON-001 | officeco | commercial | pricing escalation clause risk | 3 | 4 | 12 | renegotiate pricing cap | procurement | in progress | 2026-08-01 | medium
RISK-002 | CON-002 | tech solutions ltd | compliance | missing data processing agreement | 4 | 5 | 20 | implement updated data protection terms | legal | open | 2026-07-15 | high
RISK-003 | CON-003 | global freight inc | operational | supplier service disruption risk | 2 | 5 | 10 | develop contingency supplier plan | operations | mitigated | 2026-09-01 | medium

## Risk Dashboard
Get a Free Forever Oboloo Account
Oboloo Contract Risk Dashboard
track supplier contract risks, mitigation activities and procurement governance exposure
Metric | Value
Total Risks | 3
Open Risks | 1
High Risks | 1
Mitigated Risks | 1
Average Risk Score | 14

## Risk Guidance
Get a Free Forever Oboloo Account
Oboloo Contract Risk Guidance
use this template to identify, assess and manage supplier contract risks proactively
Section | Guidance
risk identification | identify commercial, operational, legal and compliance contract risks.
likelihood and impact | score each risk based on likelihood and business impact severity.
risk scoring | calculate risk exposure using likelihood multiplied by impact.
mitigation planning | define mitigation activities, owners and remediation timelines.
governance | review contract risks regularly with procurement, legal and stakeholder teams.
best practice | maintain centralized visibility of supplier and contract risks for audit readiness.