Ecko Health

# Practice Switching Checklist

Changing the system your practice runs on, without losing a record, a booking or a client's trust. Work through it in order.

The principle. Your records are yours, and your obligation to hold them does not pause because a contract ended. Get a complete, readable export before you cancel anything, and keep the old system readable until you have proved the new one holds everything.

## Four weeks out. Get your data out first

☐  Ask your current provider, in writing, for a full export of client records, clinical notes, documents and attachments, in an open format such as PDF or CSV.

☐  Confirm what is not included in the export. Attachments, letters and outcome measures are the usual omissions.

☐  Ask how long they retain your data after you leave, and how it is destroyed. Keep the reply.

☐  Export the appointment history and the financial and billing records separately.

☐  Open a sample of exported files. An export you have not read is not a backup.

☐  Store the export somewhere secure that is not a personal laptop.

## Three weeks out. Set the new system up properly

☐  Decide what actually migrates. Active clients, always. Discharged files can often stay in the archive.

☐  Load a handful of clients first and check the fields landed where you expect.

☐  Rebuild your note templates and letter templates before go live, not after.

☐  Set roles and access so clinicians see their own clients and administrative staff see what they need.

☐  Reconnect billing, Medicare and any online booking links.

☐  Check outcome measures carry across with their dates, so trend lines survive.

## Two weeks out. Tell people

☐  Tell clients what is changing and what is not. Most care about two things only: is my information safe, and will my appointment still be there.

☐  Update your privacy policy to name the new provider and describe how information is handled, including any AI involvement.

☐  Refresh consent where the new arrangement is materially different from what clients agreed to.

☐  Tell referrers and your GP network the practical details: new booking link, same fax and email if possible.

☐  Brief the front desk on the questions they will be asked, with the answers written down.

## Go live week. Run both, briefly

☐  Keep read access to the old system for at least a month. Do not cancel on day one.

☐  Reconcile a sample: pick ten clients and check every note, document and measure is present in the new system.

☐  Watch the first week of billing closely. Payments are where migrations break quietly.

☐  Log issues in one place rather than in messages between staff.

☐  Ask each clinician at the end of week one what is slower than before, and fix that first.

## Closing out

☐  Only cancel the old subscription once the reconciliation passed and the export is stored.

☐  Get written confirmation that the old provider has deleted or returned your data.

☐  Remove departed staff and old integrations from both systems.

☐  Record the date of the switch in your practice's own records, with who did what.

☐  Diarise a review at ninety days.

### Ask any provider before you sign

Can I export everything, myself, without asking you?

In what format, and does it include attachments?

Where is the data held, and by whom?

What happens to it if I leave?

Who can see it inside your company?

### Red flags

Export available only on request, or for a fee.

No clear answer on data location.

Notes exportable only as a single unreadable file.

Deletion timeframes that are not written down.

A contract that auto renews before your review date.

### Do not forget

Records for clients seen as children, retained far longer.

Supervision records, which live outside client files.

Consent forms, which are part of the record.

Anything sitting only in a clinician's own drive.

General guidance, not legal advice. Your practice remains responsible for its record keeping obligations throughout a migration. Ecko Health, v1.0, August 2026.

Ecko Health  ·  support@eckohealth.ai  ·  editable copy, v1.0, August 2026