## Summary
M&A Day 1 Readiness Checklist
BD Emerson (now Andersen Consulting). Companion workbook to https://www.bdemerson.com/article/day-1-readiness-checklist
How to use: give every item an owner and a due date, mark status on each function's sheet, and review this summary at each readiness gate. An item counts as Ready only when its test has passed and the evidence is filed.
Function | Items | Ready | In progress | Blocked | Not started | Percent ready
Legal entity
Banking and treasury
Finance and close
Payroll and HR
IT and access
Security
Customers
Suppliers
Communications
Regulatory
Facilities
TSA cutover
Total

## Legal entity
Legal entity
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
LE-01 | New entity formed, registered, and in good standing wherever it operates | Legal | Formation and foreign qualification filings accepted | Filed certificates and good standing letters | Not started
LE-02 | Federal and state tax identification numbers issued | Tax | EIN and state tax registrations confirmed | IRS EIN notice and state registration confirmations | Not started

## Banking and treasury
Banking and treasury
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
BT-01 | Operating, payroll, and collection accounts open with authorized signatories | Treasury | Test deposit and test payment completed | Bank confirmations and signatory list | Not started
BT-02 | Customer remittance instructions updated | Treasury | Test customer payment lands in the new account | Updated remittance letters and bank statement | Not started

## Finance and close
Finance and close
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
FC-01 | Chart of accounts and opening balance sheet ready | Controller | Opening entries posted in a test environment | Approved opening balance sheet | Not started
FC-02 | Order to cash works in the new entity's name | Finance operations | Test invoice shows the new legal name, tax ID, and remittance details | Sample invoice | Not started
FC-03 | Procure to pay works | Finance operations | Test purchase order and supplier payment processed | Sample purchase order and payment record | Not started
FC-04 | First month-end close calendar agreed | Controller | Calendar walked through with every owner | Approved close calendar | Not started

## Payroll and HR
Payroll and HR
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
PH-01 | Employees set up in the payroll of the employing entity | Payroll | Parallel payroll run reconciles to the prior period | Parallel run reconciliation | Not started
PH-02 | Benefits continue for transferring employees | HR | Enrollment files accepted by carriers | Carrier confirmations | Not started
PH-03 | Form I-9 approach decided for transferring employees | HR and legal | Approach documented against USCIS guidance | Decision memo | Not started

## IT and access
IT and access
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
IT-01 | Accounts, email, and devices work for transferring employees | IT | Sample users from each function sign in and send email | Test log | Not started
IT-02 | Access removed for people who stay with the seller | IT and security | Access review of shared systems completed | Signed access review | Not started
IT-03 | Service desk routing defined for Day 1 | IT | Test tickets reach the right team | Ticket records | Not started

## Security
Security
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
SE-01 | Privileged accounts and shared credentials rotated | Security | Credential inventory shows rotation complete | Rotation record | Not started
SE-02 | Monitoring, endpoint protection, and incident contacts in place | Security | Test alert reaches the on-call team | Alert test record | Not started
SE-03 | Data access between buyer and seller restricted | Security and legal | Access tests confirm each side sees only its own data | Test results | Not started

## Customers
Customers
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
CU-01 | Contracts that need consent identified and consents obtained | Commercial and legal | Consent tracker complete for Day 1 contracts | Consent letters | Not started
CU-02 | Customer notifications and FAQs ready | Commercial | Letters approved and scheduled | Approved letters | Not started

## Suppliers
Suppliers
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
SU-01 | Critical suppliers can bill and ship to the new entity | Procurement | Supplier confirmations received | Updated contracts or confirmations | Not started
SU-02 | Each software license assigned, replaced, or covered by the TSA | Procurement and IT | License inventory shows a route for every license | License tracker | Not started

## Communications
Communications
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
CO-01 | Employee, customer, supplier, and media messages approved | Communications | Legal and leadership sign-off | Approved message pack | Not started
CO-02 | Day 1 employee briefing scheduled | HR and leadership | Agenda and presenters confirmed | Invitation and briefing deck | Not started

## Regulatory
Regulatory
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
RE-01 | Licenses, permits, and registrations transferred or reissued | Legal and compliance | Each license has a confirmed Day 1 status | License tracker | Not started

## Facilities
Facilities
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
FA-01 | Building access and occupancy agreements in place | Facilities | Badges work for transferring employees | Access test record | Not started

## TSA cutover
TSA cutover
Status values: Not started, In progress, Ready, Blocked. Add rows as needed; the Summary sheet counts rows 5 to 200.
ID | Item | Owner | Test | Evidence | Status | Due date | Notes
TS-01 | Every Day 1 service has a named seller contact, service level, and escalation path | Separation management office | Service catalog walked through with the seller | Signed service catalog | Not started
TS-02 | TSA invoicing and dispute process agreed | Finance | Test TSA invoice reviewed | Agreed process document | Not started
TS-03 | Exit plan drafted for each TSA service | Separation management office | Exit dates and dependencies documented | TSA exit plan | Not started