## Instructions
Background
This tool was developed by Point of Reference to help companies establish a formal customer advocate program (CAP). It is based on our experience working with clients with programs at various stages of evolution, but particularly those that came to us with little more than a desire to bring order to their chaotic customer reference practices. This timeline view was developed to complement the CAP marketing plan outline. It ties to various activities in the ouline but displays them chronologically, and in many cases, concurrently---the way a program would realistically be implemented.
How to Use It
When you see notations such as "(B 1-3)" in a workbook cell it indicates these are the activities on the outline within the corresponding phase (e.g., Secure Program Approval). The first column shows the 11 elements of the Customer Reference Program maturity model developed by Point of Reference. By placing the activities in the context of the 11 elements we've ensured that no critical tasks/perspectives are overlooked.
If you need the corresponding outline document:
Microsoft Word / CAP Marketing Plan Outline

## CAP Marketing Plan Timeline
Program Element | I. Program Scope Definition |  |  |  |  | II. Launch Preparation and User Adoption Plan | [7 empty] | III. Launch & User Adoption | IV. Program Sustainability
Add Dates ->
Program Vision / Like any serious endeavor, it’s important to know where you’re going or you may never get there. It’s also important that other, influential stakeholders “catch fire,” are able to track progress and provide sustaining support. | (A 1-2) Identify current pain and develop problem statement. | (A 3-4) Develop future state vision, and related success criteria. | (A 5-6) Define strategic scope (e.g., win-rates, renewals, brand awareness, etc.). Define tactical scope (e.g., what departments will be served: sales, PR, digital, events, etc.). | (E 1-3) Review user feedback, validate pain points, and future state vision by audience. | [6 empty] | (D 5) Determine program branding consistent with vision. |  |  |  | (A) Periodic review to ensure CAP is on track. |  | (D1) Execute any additional program phases defined as part of the initial program scope
Program Metrics / Metrics fall into two buckets, activity-based (tactical) that are important to operational execution, and outcome-based (strategic that demonstrate enterprise impact in the form of revenue influenced. |  | (A 4) Define success metrics |  | (E 4) Validate & refine success criteria/measurement by audience. |  |  | (A 3) Refine set of meaningful program measurements. | (A 3) Identify systems and processes to achieve repeatable reporting. | (A 3) Determine format of metrics report for program team and execs. |  | (A 3) Dry run producing performance metrics/reports. |  |  |  | (A) Execute ongoing program measurement and success reporting. | (A) Periodic review to ensure CAP is measuring what's important, useful.
Managing Upward / Support from the right executives can make or break a CAP. Done effectively, the recruitment of executive support never ends with a single exec sponsor. The ideal is an addition level or two up or horizontal, even CEO visibility/support. | (B 1) Identify executive sponsor(s) and understand their goals and perspective. | (B 1) Establish a program advisory board representing key stakeholders (sales, marketing, customer success, executives). |  | (D 1-4) Establish resource needs and budget. (E 2-3) Validate pain points, and future state vision). | (F 1-2) Gain executive support and budget approval. |  | (D1) Establish regular meetings with sponsor(s) and advisory board. |  | (D1) Continue to expand awareness of CAP w/in exec ranks |  | (D 1) Develop & communicate plan for exec involvement in launch communications and tie to overall promotional plan. | (E 1-3) Develop launch plan incorporating all sub-plans. |  | (A) Gain approval to proceed with launch from executive sponsor(s) and advisory board. (C) Execute executive portion of launch communications. | (A) Stay consistent on reporting on program impact on organization. Solicit feedback to ensure execs continue to get needed data. | (B) Continue amplifying/reinforcing strategic value of program. | (D3) Gain approval for the implementation of identified program enhancements.
Horizontal Integration / A highly evolved CAP has a web of peer connections to related functions such as PR, analyst relations, support, consulting, etc. Nirvana is a holistic, proactive and coordinated effort to leverage customer interactions for maximum benefit, and insure against overuse. | (B 2-3) Identify influencers, users and champions, and understand their perspective. | (B 2-3) Establish steering committee including executives, key influencers, and users. Solicit feedback from non-Sales users to scope needs. | (A 3-4) Compile feedback results, integrate into program scope relative to Sales, PR, digital, events, etc. | (E 2-3) Validate pain points, and future state vision. |  |  | (A 4-5) Meet with related teams and formulate gap correction plan, priorities, coordination plan, protocols, processes. |  |  |  | (D 3) Develop communications/education plan and tie to overall promotional plan. |  | (D 3) Insert CAP training into new hire orientation, online learning tools. | (B) Ensure all stakeholders are briefed/trained on new processes/protocols. | (C 1-2) Periodically review progress and areas for improvement. Revise processes as needed. | (E) Continue to reach out to additional groups within the organization to incorpoate visibility of their reference-related activities into the global view.
Field Relationship / Without a strong relationship with Sales management and the Sales force in general, why bother? The savvy CAP takes every opportunity for face time, employs carrots, and has great listening skills to improve the CAP “product” for Sales. | (B 2-3) Identify influencers, users and champions, and understand their perspective. | (B 3) Survey field to determine what's most important, what's working/not working in order to scope needs. | (A 3-4) Compile feedback results, integrate into proposed program scope relative to sales. | (E 2-3) Validate pain points, and future state vision. |  |  | (A 4) Validate gap correction plan and priorities with field focus group. | (D 2) Develop communications/education plan for field. |  |  | (D 2) Build plan for staying in touch w/ field ongoing (onboarding/training, team meeting attendance, surveys, testimonials for the program, etc.). |  | (D 2) Insert CAP training into new hire orientation, online learning tools. | (B) Train field on program use, nominations, SLAs, etc. | (C) Offer ongoing training on program to new and existing salespeople. Execute on plan to stay in touch with field. | (C) Continue to seek opportunities for face time with field personnel to put a face on the program.
Content Strategy / There’s only one thing worse than having no content and that’s having poorly organized, out-of-date and unsearchable content. As the library grows a thoughtful strategy is required to gain maximum benefit from these assets. |  |  | (C 1) Review current asset library and development needs. | (C 1-2) Develop prelimary estimate of content needs through high level gap analysis (e.g., by industry, geo, product coverage, etc.). | (D 1-3) Develop preliminary estimate of budget needs related to content development effort. |  |  |  | (A1) Determine how much/coverage/type is needed to make good first impression w/ field. | (A 1) Develop plan to address/prioritize content gaps by industry, product, stage, etc. | (A1) Develop new content needed for launch. |  | (A 6) Determine customer content management processes, build plan to ensure currency of Content. |  | (C) Execute on periodic review/update/archive processes. | (C) Continue to conduct gap analyses, determine current usage, and future need for assets. | (D) Identify program enhancements based on review and feedback. Implement additional program enhancements.
Customer Reference Relationships / Accomplished CAPs confirm that having direct relationships with customers, full visibility of customer use, and a clear value proposition puts them in the best position to help Sales and any other "consumers" of the program’s services. |  |  | (C 1) Review current reference pool and practices. | (C 1-2) Develop preliminary high level gap analysis (e.g., by industry, geo, product coverage, etc.). | (D 1-3) Develop preliminary estimate of budget needs related to resource needs for recruiting and/or profile updating effort. |  |  |  | (A 2) Put plan in place to fill in gaps (lead sources, incentives, communications). | (A2) Determine how many refs/coverage are needed to make good first impression w/ field. | (D4) Survey to find out what customers value. Use to develop program benefits. | (D 4) Build plan to communicate program benefits to customers for recruiting activities. | (A 7) Build engagement plan for ongoing relationship building/maintenance (e.g., quarterly outreach, community marketing). |  | (C) Continue to add value to program members, find new ways to leverage relationships. | (C) Continue to grow number of direct customer relationships and executing on engagement plan. Revise as needed. | (D) Identify program enhancements based on review and feedback. Implement additional program enhancements.
Information Systems / Encompassing all processes and assets of a CAP in a single software solution is the holy grail. The progression to the “grail” includes increased user access, focus to avoid collecting extraneous information, self-service elements to boost productivity and integration with key customer systems to avoid building data silos. |  |  | (C 1) Determine technology needs relative to current capabilities and expertise. | (D1-3) Develop preliminary technology investment requirements for budgeting. |  |  |  | (B 1-5) Begin thorough data review to identify gaps. | (B 1-5) Apply "Will it help us sell?" test to avoid extraneous data. | (B 1-5) Assess location and quality/completeness of existing data. | (B 1-5) Review technology options for supporting program. | (B 3-5) If valuable data in other systems, build plan to clean, import and/or regularly sync data. | Test all systems to ensure no glitches at launch. | (B) Provide customized training for different users of CAP systems. | (C) Continuously review the accuracy and completeness of database. Add ease-of-use features based on periodic/continuous Sales feedback and process improvements. |  | (D) Identify program enhancements based on review and feedback. Implement additional program enhancements.
Program Promotion / If a CAP is deep in the forest but has great references to share, does anyone notice it? No. The programs with buzz tap all possible channels, gain executive involvement and get creative in spreading the word for the initial launch and on an ongoing basis. |  |  | (D 4) Review all communications channels and promotion best-practices. | (D 1-4) Develop preliminary estimate related to communications needs and budget. |  |  |  | (D) Inventory all communications channels and upcoming events for CAP communications. | (D) Determine best channels (events, Slack/Teams, etc.) for launch then ongoing CAP communications. |  | (D) Develop a promotion launch plan including communication plan, branding, incentives, contests, etc. that will resonate best within your organization. | (D) Build content for launch and ongoing communications. |  | (C) Execute promotional launch plan (e.g. clear, concise launch announcement to field. Include pain points solved. Must include exec support). | (B) Develop ongoing comms schedule and content to keep program top-of-mind (e.g. "Did you know" tips, sales success using program, performance stats, contests, etc.).
Outside Expertise / Cross-pollination has led to some of the best ideas. CAPs are no exception. There is wisdom all around us but if opportunities to exchange knowledge with peers, partners, and other experts aren’t taken a CAP’s growth is limited and can become insular/quirky in its practices. |  |  | (C 1-2) Determine outside resource needs relative to current capabilities and expertise. | (D 1-3) Develop preliminary estimate of outside resource needs. |  |  |  | (C 1-2) Based on scope and existing resources/expertise, identify outside resources needed. | (C 3) Research potential vendors and rank based on fit. | (C 4-5) Make final selections. | (D6) Begin engagements/ implementations. |  |  |  | (C) Plan periodical reviews of responsibilities and staff capabilities to ensure required expertise is aligned.
Staff Composition, Organization & Perspective / No CAP ever seems to have enough bandwidth, but the way the team is staffed, and duties assigned, even if it’s a “one man show,” makes all the difference. We see 3, and possibly 4 distinct domains to make a complete CAP: strategy, recruitment, fulfillment and content. Each role really has a different skill set and personality profile. For any CAP position, a work history in the field or otherwise working closely with Sales provides a huge advantage. |  |  | (D 1-2) Determine resource needs relative to defined scope and current staff options. | (D 3) Develop preliminary estimate of resource needs. |  |  |  | (F 1-3) Hiring plan where F/T resources will be used (including job descriptions). | (F 1-3) Train resources new to the CAP. |  |  |  | (F 1-3) Ensure full staff is trained and processes are well-understood. |  | (C) Plan periodical reviews of responsibilities and staff capabilities to ensure team mix is appropriate.