## Instructions
AI Monitoring Evidence
Logs, Dashboards, and Reports Demonstrating Ongoing Oversight
1. | Complete one workbook per AI system per monitoring period.
2. | Record performance metrics on the Performance Log tab.
3. | Log all incidents on the Incident Log tab.
4. | Document human oversight on the Oversight Log tab.
5. | Summarize on the Period Summary tab at period end.
Reference: Cherry Hill Advisory AI Internal Audit Encyclopedia (Dec 2025), pp. 33-34, Continuous Auditing. IIA AI Auditing Framework. NIST AI RMF 1.0, Manage Function.

## System ID
AI System ID | AI-001
System Name | Customer Credit Scoring Model
Monitoring Period | 10/01/2025 to 12/31/2025
Prepared By | S. Patel, Lead ML Engineer
Review Date | 01/15/2026

## Performance Log
Date | Metric | Target | Actual | Variance | Within Tolerance? | Action Required | Action Taken | Notes
10/01/2025 | Model Accuracy (AUC-ROC) | 0.85 | 0.87 | +0.02 | Yes | No | N/A | Strong performance. Above target.
10/01/2025 | False Positive Rate | < 15% | 11.2% | -3.8% | Yes | No | N/A | Well within tolerance.
10/01/2025 | False Negative Rate | < 5% | 3.8% | -1.2% | Yes | No | N/A | Acceptable. Monitor trend.
10/01/2025 | Avg Prediction Latency | < 200ms | 145ms | -55ms | Yes | No | N/A | No performance degradation.
10/01/2025 | Disparate Impact Ratio (Gender) | 0.80 - 1.25 | 0.92 | N/A | Yes | No | N/A | Within EEOC four-fifths rule.
11/01/2025 | Model Accuracy (AUC-ROC) | 0.85 | 0.86 | +0.01 | Yes | No | N/A | Slight decrease from Oct. Still above target.
11/01/2025 | False Positive Rate | < 15% | 12.4% | -2.6% | Yes | No | N/A | Minor uptick. Within tolerance.
11/01/2025 | False Negative Rate | < 5% | 4.1% | -0.9% | Yes | No | N/A | Approaching threshold. Flagged for watch.
11/01/2025 | Avg Prediction Latency | < 200ms | 152ms | -48ms | Yes | No | N/A | Normal range.
11/01/2025 | Disparate Impact Ratio (Gender) | 0.80 - 1.25 | 0.91 | N/A | Yes | No | N/A | Stable.
12/01/2025 | Model Accuracy (AUC-ROC) | 0.85 | 0.84 | -0.01 | No | Yes | Triggered data drift analysis. Root cause: seasonal application pattern shift. | Below target. Retraining evaluated.
12/01/2025 | False Positive Rate | < 15% | 14.7% | -0.3% | Yes | No | N/A | Near threshold but within tolerance.
12/01/2025 | False Negative Rate | < 5% | 4.9% | -0.1% | No | Yes | Escalated to Model Owner. Interim manual review layer added for borderline scores 580-620. | At threshold. Risk of missed defaults.
12/01/2025 | Avg Prediction Latency | < 200ms | 148ms | -52ms | Yes | No | N/A | Normal range.
12/01/2025 | Disparate Impact Ratio (Gender) | 0.80 - 1.25 | 0.88 | N/A | Yes | No | N/A | Slight decrease. Within tolerance but trending down.

## Data Drift Log
Date | Drift Type | Feature | Detection Method | Severity | Retraining? | Retrain Date | Post-Retrain Perf | Notes
12/05/2025 | Input | Applicant Income Distribution | Population Stability Index (PSI) | Medium | No | N/A | N/A | PSI = 0.18 (threshold: 0.20). Holiday seasonal pattern. Monitor in Jan.
12/05/2025 | Input | Employment Tenure | Kolmogorov-Smirnov Test | Low | No | N/A | N/A | KS statistic = 0.04. No significant drift detected.
12/10/2025 | Output | Score Distribution | Chi-Square Test | Medium | Evaluated | N/A | N/A | Score distribution shifted left by ~15 points. Correlated with income drift. Decision: defer retraining pending Jan data.
12/15/2025 | Input | Debt-to-Income Ratio | PSI | Low | No | N/A | N/A | PSI = 0.08. Normal seasonal variation.

## Incident Log
Incident ID | Date Detected | Date Resolved | Severity | Description | Root Cause | Impact | Resolution | Escalated To | Status
INC-2025-041 | 11/14/2025 | 11/14/2025 | Low | Model returned null score for 3 applications during 2:15-2:22 AM batch run. | Database connection timeout during scheduled maintenance window. | 3 applications delayed by 4 hours. No customer impact (overnight batch). | Adjusted batch schedule to avoid maintenance window. Added retry logic. | S. Patel, ML Lead | Closed
INC-2025-058 | 12/03/2025 | 12/08/2025 | Medium | AUC-ROC dropped below 0.85 threshold for first time since deployment. | Seasonal shift in applicant income distribution (holiday lending patterns). | Model accuracy degraded for applicants with seasonal employment income. | Added manual review layer for scores 580-620. Scheduled retraining evaluation for Jan 2026. | J. Martinez, VP Credit Risk | Closed
INC-2025-062 | 12/18/2025 | 12/19/2025 | Medium | Disparate impact ratio for age group 18-25 dropped to 0.78, below 0.80 threshold. | Insufficient training data representation for younger applicants with thin credit files. | Potential adverse impact on younger applicants. 47 applications affected in December. | Implemented interim manual review for all 18-25 applicants scoring below 650. Added age cohort to Q1 2026 retraining dataset. | J. Martinez, VP Credit Risk; AI Governance Council | Closed

## Oversight Log
Date | Reviewer | Role | Activity Type | Scope | Findings | Override? | Justification | Follow-up
10/15/2025 | J. Martinez | VP Credit Risk | Quarterly Performance Review | Full model performance metrics, accuracy, fairness, latency for Q3 2025. | All metrics within tolerance. No action required. Model performing as expected. | No | N/A | Standard quarterly review. Next: Jan 2026.
11/05/2025 | K. Wong | Data Governance Lead | Data Quality Audit | Training data completeness, accuracy, and representativeness assessment. | Training dataset covers 94% of current applicant demographics. Gap identified in 18-25 age cohort (3.2% of training vs 8.1% of current applications). | No | N/A | Recommended supplementing training data for underrepresented age cohort in next retrain.
11/20/2025 | External Auditor | Cherry Hill Advisory | Annual Bias Audit | Full fairness assessment across gender, race/ethnicity, age, and geographic protected classes per ECOA and fair lending requirements. | Gender and race/ethnicity ratios within tolerance. Age cohort 18-25 flagged as trending toward threshold. Geographic analysis clean. | No | N/A | Formal report issued Dec 2025. One recommendation: augment training data for younger applicants.
12/08/2025 | J. Martinez | VP Credit Risk | Incident Response Review | Review of INC-2025-058 (accuracy drop) and remediation adequacy. | Confirmed seasonal pattern as root cause. Approved interim manual review layer. Deferred full retraining to Jan 2026 pending post-holiday data. | Yes | Overrode standard retraining trigger (AUC < 0.85 for 2 consecutive periods). Rationale: root cause is known seasonal pattern, not model degradation. Full dataset with Jan 2026 data will produce better retrain. | Retraining scheduled for Jan 2026. Monitor weekly until completed.
12/22/2025 | AI Governance Council | Cross-Functional | Quarterly Governance Review | Q4 2025 model portfolio review. AI-001 through AI-012 status update. | AI-001: Two medium incidents in Q4. Remediation adequate. AI-003: Bias audit overdue. AI-008: No governance framework. AI-009: Shadow AI retroactive assessment in progress. | No | N/A | AI-003 bias audit expedited to Jan 2026. AI-008 added to Q2 audit plan. AI-009 assessment target: Feb 2026.

## Dashboard Evidence
Date | Report/Dashboard | Source | Key Findings | Attachment Ref | Reviewed By
10/31/2025 | Q3 2025 Model Performance Dashboard | DataRobot MLOps | All KPIs green. AUC 0.87, FPR 11.2%, latency 145ms. No drift detected. | Exhibit A - Q3_Dashboard_Screenshot.pdf | J. Martinez
11/30/2025 | November 2025 Monthly Monitoring Report | Internal (Jupyter Notebook) | AUC 0.86 (slight decline). Income distribution PSI approaching threshold. False negative rate trending up. | Exhibit B - Nov_Monthly_Report.pdf | S. Patel
12/15/2025 | Cherry Hill Advisory Annual Bias Audit Report | Cherry Hill Advisory | Formal bias assessment across all protected classes. One finding: age cohort 18-25 trending toward threshold. Recommendation to augment training data. | Exhibit C - CHA_Bias_Audit_2025.pdf | J. Martinez, R. Hughes (Legal)
12/31/2025 | Q4 2025 Model Performance Dashboard | DataRobot MLOps | AUC dipped to 0.84 in Dec (below target). Two medium incidents. Manual review layer active. Retraining planned Jan 2026. | Exhibit D - Q4_Dashboard_Screenshot.pdf | J. Martinez
12/31/2025 | Q4 2025 Fairness Monitoring Report | Internal (Aequitas toolkit) | Gender DI ratio: 0.88. Race/ethnicity DI ratio: 0.93. Age 18-25 DI ratio: 0.78 (below threshold). Remediation active. | Exhibit E - Q4_Fairness_Report.pdf | K. Wong, J. Martinez

## Period Summary
Monitoring Period | 10/01/2025 to 12/31/2025
Overall Health | Degraded
Performance Summary | AUC-ROC declined from 0.87 (Oct) to 0.84 (Dec), dropping below 0.85 target in December. False negative rate approached 5% threshold. Latency stable. Root cause identified as seasonal applicant income distribution shift.
Incidents This Period | 3 total: 1 Low (database timeout, resolved same day), 2 Medium (accuracy drop and age cohort bias, both resolved with interim controls).
Data Drift | Yes. Income distribution PSI = 0.18 (threshold 0.20). Score distribution shifted left ~15 points. Correlated with seasonal lending patterns.
Retraining | Deferred to January 2026. Rationale: root cause is seasonal. Post-holiday data will produce a more representative retrain. Override approved by Model Owner 12/08/2025.
Key Concerns | 1. Age cohort 18-25 disparate impact ratio at 0.78, below 0.80 threshold. Interim manual review active. 2. AUC below target for December. 3. False negative rate at threshold boundary.
Recommended Actions | 1. Complete model retraining with augmented 18-25 age cohort data by 01/31/2026. 2. Validate post-retrain fairness metrics across all protected classes. 3. Continue weekly monitoring until AUC returns above 0.85. 4. Present Q4 findings to AI Governance Council at Jan 2026 meeting.
Model Owner Attestation | I attest that the monitoring evidence presented in this workbook is complete and accurate for the period 10/01/2025 to 12/31/2025. J. Martinez, VP Credit Risk. Signed: 01/15/2026.
Reference: NIST AI RMF 1.0, Manage Function. Cherry Hill Advisory AI Internal Audit Encyclopedia (Dec 2025), pp. 33-34.

## About Cherry Hill Advisory
About Cherry Hill Advisory
Cherry Hill Advisory delivers internal audit, risk advisory, and AI governance services to high-growth technology and commercial organizations. We combine Big 4 expertise with boutique delivery, acting as a direct extension of your internal audit function.
HOW WE CAN HELP WITH AI GOVERNANCE
• AI Governance Framework Design: Build or assess your AI governance policy, risk appetite, and oversight structure.
• AI Audit Program Development: Establish AI-specific audit procedures, testing protocols, and continuous monitoring.
• AI Risk Assessment: Identify, score, and prioritize AI risks using the IIA AI Framework and NIST AI RMF.
• AI Inventory and Registry Setup: Catalog all AI systems, assign ownership, and define risk tiers.
• Regulatory Compliance: Align AI operations with the EU AI Act, state-level AI laws, and sector-specific requirements.
• Training and Enablement: Upskill your audit team on AI auditing, prompt engineering, and AI risk evaluation.
RELATED CHERRY HILL ADVISORY RESOURCES
• Ethical AI in Internal Audit (December 2025)
• AI Internal Audit Encyclopedia (December 2025)
• AI Auditing Guide (December 2025)
Email: info@cherryhilladvisory.com ¦ Web: cherryhilladvisory.com
2026 Cherry Hill Advisory. All rights reserved.