## Checklist
Website Migration Checklist by Notum
Last updated October 21, 2026. Full guide: https://www.notum.tech/services/headless-cms-migration/website-migration-checklist
How to use: make a copy (File > Make a copy), then pick a Status for each step from the dropdown. Progress on the right updates as you go.
# | Stage | Step | Owner | Status | Notes | Progress
1 | Before You Migrate | Get access to the current site, CMS, hosting, and analytics |  | Not started |  | Steps done | 0
2 | Before You Migrate | Audit the content: every content type, every template, and how many pages use each |  | Not started |  | In progress | 0
3 | Before You Migrate | Decide what happens to every page: migrate, merge, rewrite, or archive |  | Not started |  | Total steps | 66
4 | Before You Migrate | Decide who moves existing content and who writes new content: your team, ours, a script, or an AI tool |  | Not started |  | Complete | 0%
5 | Before You Migrate | Decide whether you launch in parts or all at once |  | Not started
6 | Before You Migrate | Find out where the design stands: new or existing, and who owns it |  | Not started
7 | Before You Migrate | Go through the sitemap and flag every URL that will change |  | Not started |  | By stage | Done | Steps | Complete
8 | Before You Migrate | Record performance on your most important pages before you touch anything |  | Not started |  | Before You Migrate | 0 | 11 | 0%
9 | Before You Migrate | List what the new site has to support: languages, browsers and devices, GDPR, and accessibility |  | Not started |  | Set Up the New Platform | 0 | 5 | 0%
10 | Before You Migrate | Agree on what a correct migration looks like, so everyone checks against the same standard |  | Not started |  | Content Migration | 0 | 11 | 0%
11 | Before You Migrate | Write down the risks you already know about |  | Not started |  | SEO and GEO Essentials | 0 | 6 | 0%
12 | Set Up the New Platform | Set up dev and staging environments, hidden from search engines |  | Not started |  | Integrations | 0 | 9 | 0%
13 | Set Up the New Platform | Design, build, and check every CMS component your content needs, and get your approval before anyone fills it |  | Not started |  | Before Launch Day | 0 | 10 | 0%
14 | Set Up the New Platform | Make sure content can move between environments, from staging to production |  | Not started |  | Launch Day | 0 | 7 | 0%
15 | Set Up the New Platform | Agree how you'll test and accept finished work |  | Not started |  | After Launch | 0 | 7 | 0%
16 | Set Up the New Platform | Train your editors on the new CMS before content migration starts, so they can work in it from day one |  | Not started
17 | Content Migration | Approve the list of pages and content items to migrate |  | Not started
18 | Content Migration | Agree on a content freeze, so the source doesn't change mid-migration |  | Not started
19 | Content Migration | Test the script that compares migrated content with the source |  | Not started
20 | Content Migration | Map the pages and split the work: who fills what, in which order |  | Not started
21 | Content Migration | Fill the content, page by page or component by component |  | Not started
22 | Content Migration | Spot-check a random sample to catch systemic errors early |  | Not started
23 | Content Migration | Compare every page with the source to find missing fields, gaps, and formatting differences |  | Not started
24 | Content Migration | Review every difference: keep the intended ones (merged pages, cleaned-up formatting), fix the rest |  | Not started
25 | Content Migration | Fix what needs fixing |  | Not started
26 | Content Migration | Run the script again until it finds nothing left to fix |  | Not started
27 | Content Migration | Review the content on staging and sign off |  | Not started
28 | SEO and GEO Essentials | Build a redirect map that covers every changed URL, and test it before launch |  | Not started
29 | SEO and GEO Essentials | Carry over titles, meta descriptions, canonicals, and hreflang |  | Not started
30 | SEO and GEO Essentials | Put structured data in the HTML itself, not only in JavaScript |  | Not started
31 | SEO and GEO Essentials | Remove the noindex tags and robots.txt blocks that hid the new site, the moment it goes public |  | Not started
32 | SEO and GEO Essentials | Check that no staging links or test content made it to production |  | Not started
33 | SEO and GEO Essentials | Submit the new sitemap in Google Search Console right after the release |  | Not started
34 | Integrations | Confirm the full integration list. For each one, decide whether to keep it, replace it, or remove it, and name an owner. |  | Not started
35 | Integrations | Point credentials and webhooks to the new environment |  | Not started
36 | Integrations | Plan a smoke test for each integration on launch day |  | Not started
37 | Integrations | Find out whether switching back the site also means reconfiguring each integration |  | Not started
38 | Integrations | Test that forms submit and every lead lands in your CRM |  | Not started
39 | Integrations | Check that analytics and your tag manager fire on the new templates |  | Not started
40 | Integrations | Check that cookie consent works and scripts wait for it |  | Not started
41 | Integrations | Check that site search returns current content |  | Not started
42 | Integrations | Check that third-party embeds and marketing pixels load |  | Not started
43 | Before Launch Day | Start the content freeze, tell your editors, and set a clear route for urgent changes |  | Not started
44 | Before Launch Day | Run the final tests on the new production environment, hidden behind a VPN or proxy, on desktop, mobile, and tablet |  | Not started
45 | Before Launch Day | Finish user acceptance testing, and give every known issue a priority: A, B, or C |  | Not started
46 | Before Launch Day | Approve the final version on the hidden production environment |  | Not started
47 | Before Launch Day | Write the release and fallback plan, rehearse it, and make sure everyone knows their part |  | Not started
48 | Before Launch Day | Back up the old site, and keep it live until the fallback window closes |  | Not started
49 | Before Launch Day | Turn on monitoring and logging before launch, not after |  | Not started
50 | Before Launch Day | Lower the DNS TTL at least 24 h before the switch |  | Not started
51 | Before Launch Day | Pick a launch window in low-traffic hours |  | Not started
52 | Before Launch Day | Hold a go/no-go meeting the day before |  | Not started
53 | Launch Day | Make sure the whole team is available, and give the hidden production one last check |  | Not started
54 | Launch Day | Pause editors, or put the old site into maintenance mode |  | Not started
55 | Launch Day | Run a final content and media check |  | Not started
56 | Launch Day | Switch over: point the domain to the new production, turn on redirects, and open the site to visitors and search engines |  | Not started
57 | Launch Day | Watch infrastructure, CDN, and error logs during the switch |  | Not started
58 | Launch Day | Run smoke tests on public URLs: homepage, main pages, forms, redirects, and analytics |  | Not started
59 | Launch Day | Decide: keep the new site, or switch back to the old one |  | Not started
60 | After Launch | Watch uptime, errors, analytics, core flows, 404s, and performance for 72 hours |  | Not started
61 | After Launch | Give every post-launch bug a priority: A, B, or C |  | Not started
62 | After Launch | Get a status report at 48 hours and sign off at 72 hours |  | Not started
63 | After Launch | Keep monitoring for at least a week. Editors can publish again, but hold the code freeze, with no new features, until the fallback window closes |  | Not started
64 | After Launch | Remove anything you only needed for the launch, like temporary redirects or old tracking code |  | Not started
65 | After Launch | Shut down the old environment only after everyone confirms the new one is stable |  | Not started
66 | After Launch | Agree who supports the site after launch |  | Not started