## Instructions
Mutual Action Plan Template
Prolifiq CRUSH ¦ prolifiq.com
How to use this template
This workbook has 3 tabs. Fill them in together with your buyer, not alone.
1. MAP Overview — deal header info, objectives, and the stakeholder map.
2. Task Plan — the shared task table. This is the heart of the plan.
3. (This tab) Instructions and legend.
Color legend
Blue italic text = example content. Replace it with your own.
Yellow fill = cells you're expected to fill in.
Black text = labels and structure. Leave as-is.
Best practices
Build this plan with the buyer starting at the validation or proof-of-value stage, not at the end.
Every task needs both an owner AND a due date. A task with neither is just a wish.
Push for genuine buyer-owned tasks, not just seller to-dos. Buyer ownership is your strongest deal-health signal.
Update statuses weekly. A stale plan is worse than no plan, it creates false confidence.
Mark dependencies explicitly so everyone can see the critical path.
Want this to live inside Salesforce instead of a spreadsheet?
Prolifiq CRUSH brings account planning, stakeholder mapping, and mutual action plans natively into Salesforce, so plan health rolls up into your forecast automatically. See prolifiq.com/platform/crush

## MAP Overview
MUTUAL ACTION PLAN — DEAL OVERVIEW
Header Section
Account Name | Acme Manufacturing Co. |  | Executive Sponsor (Buyer) | Jordan Lee, VP Operations
Opportunity Name | Acme — CRUSH Platform Expansion |  | Executive Sponsor (Seller) | Morgan Diaz, AE
Opportunity Value | $185,000 ACV |  | Version Date | 9/2/2026
Target Close / Go-Live Date | 10/31/2026 |  | Plan Status | On Track
Objectives and Success Criteria
In the buyer's own words: what are they trying to achieve, and how will they measure success?
Example: Consolidate three disconnected planning tools into one Salesforce-native platform by Q1, reducing account plan build time from 3 weeks to under 1 week and giving leadership real-time visibility into top-50 account health.
Stakeholder Map
Name | Role / Title | Organization | Stance | What They Need to Say Yes
Jordan Lee | VP Operations | Buyer | Champion | Proof the platform cuts plan build time in half
Priya Nair | CFO | Buyer | Economic Buyer | ROI model showing payback inside 12 months
Sam Ortiz | IT Security Lead | Buyer | Neutral | Completed security questionnaire, SOC 2 report

## Task Plan
MUTUAL ACTION PLAN — TASK PLAN
Total Tasks |  | Complete
% Complete |  | At Risk
Phase | Task | Owner | Owner Org | Due Date | Status | Dependencies
Discovery & Validation | Confirm technical fit with a deep-dive call covering current tool stack | Sam Ortiz | Buyer | 9/10/2026 | Complete | None
Proof of Value | Run 2-week sandbox pilot with defined exit criteria (plan build time <1 week) | Morgan Diaz | Seller | 9/24/2026 | In Progress | Sandbox access provisioned
Business Case & Approval | Present ROI model to CFO for budget sign-off | Jordan Lee | Buyer | 10/8/2026 | Not Started | Pilot results finalized
Procurement & Legal | Complete security questionnaire and SOC 2 review | Sam Ortiz | Buyer | 10/15/2026 | At Risk | None
Signature & Kickoff | Route MSA for e-signature | Morgan Diaz | Seller | 10/29/2026 | Not Started | Legal review complete