## AI Adoption Plan
AI ADOPTION PLAN: 12-WEEK IMPLEMENTATION FRAMEWORK
Week(s) | Activity | Focus | Details
Pre-Start | Preparation & Planning | Foundation Setting | • Define objectives & success criteria (e.g. 80% active by wk 12) • Identify AI Champions across every team • Draft a lightweight AI-usage policy & FAQ • Announce roadmap to team • Stakeholders: Leadership team, department heads, and designated AI champions • Deliverables: Success metrics dashboard (Juma Report Dashboard), AI policy v1.0, champion roster
Weeks 1–2 | Success Manager Onboarding Session 1 | Launch & Alignment | • Kickoff & goal-alignment with CSM • CSM-led meeting • Establish monthly CSM syncs + email communication • Finalize config/billing & workspace policy & FAQ • Complete Goal Alignment Questionnaire • Review Juma resources (video tutorials, case studies) • Strategic discussions: Case studies, integrations, geographic expansion, usage analytics
Week 3 | Internal Workshop #1 | AI Foundations & Ideation | • When to use which model • Prompt-writing basics + prompt builder • Context Window in context of Juma • Brainstorm 1 internal use case for every team • Assign mini-exercise for homework for every team (build context for a project and share where it applies)
Week 4 | Feedback Round 1 | First Check-In | • 30-60 min feedback meeting huddle (structured survey) • Early usage data/observations • Refine Workshop #2 agenda based on pain points • Capture: barriers, wins, usage patterns, pain points, requests
Week 5 | Sync with CSM + Internal Feedback | Mid-Point Reflection | • Sync with CSM to review metrics and adjust strategy • Collecting internal feedback in team channels/informal conversations • Light programming week to give teams space to experiment
Week 6 | Juma Onboarding Session 2 | Targeted Skill Development | • Topic based on internal feedback from Week 4 • May cover: advanced prompting, collaboration features, workflow automation, or integration setup • Fully customized to team needs
Week 7 | Internal Workshop #2 | Applied Learning | Topics TBD based on feedback. Examples: • Competitive Intelligence: competitor research, positioning analysis, market monitoring • Research & Optimization: keyword research & content optimization • Working with different file types (PDF, DOCS, CSV, XLSX etc.) • Live examples with real company data
Week 8 | Feedback Round 2 | Course Correction | • Post-workshop survey + 30-60 min feedback meeting huddle • Optional office hours for drop-in troubleshooting • Capture top 3 requests for Workshop #3 • Ensure program finishes strong
Weeks 9-10 | Sync with CSM + Internal Feedback | Momentum Building | • Sync with CSM to review metrics • Collecting internal feedback in team channels/informal conversations • Usage patterns should be solidifying • Identify power users, laggards, and opportunities to cross-pollinate practices
Week 11 | Internal Workshop #3 | Advanced Applications | Topics TBD. Examples: • AI-powered campaign analysis & forecasting • Hands-on dashboard prototyping (AI-generated insights) • Plan 2–3 next pilot use-cases for each sub-team • Shift from learning to planning for sustained adoption
Week 12 | Final Feedback & Wrap-Up | Closing & Next Phase | • Program-wide survey & final 30-60 min. feedback session • Review KPIs vs. targets (adoption, efficiency gains, outcome lift) • Executive recap & "next-phase" planning • Deliverables: Executive summary report, updated AI policy, roadmap for months 4–6
SUCCESS METRICS TO TRACK
Throughout the program, monitor: • Adoption Rate: % of team members actively using AI tools weekly • Engagement Depth: Average sessions per user, context items created, prompts run • Efficiency Gains: Time saved on specific tasks (measured via surveys or time-tracking) • Business Outcomes: Quality improvements, faster turnaround, new capabilities unlocked • Sentiment: NPS or satisfaction scores from feedback rounds
TIPS FOR SUCCESS
• Celebrate early wins publicly to build momentum. Even small victories should be shared in team channels. • Empower your AI Champions to run mini-sessions within their teams between formal workshops. Peer learning often sticks better than top-down training. • Keep the feedback loop tight. The 2-week cadence ensures you can pivot quickly if something isn't working. • Don't aim for perfection in Week 1. AI adoption is iterative—focus on progress over polish, and normalize experimentation and learning from failures.