## Instructions
Instructions for how to use this tool. This tool has 3 worksheets. This worksheet contains links to an example and templates
Employer Prepare stage ¦ Plan for potential risks
Purpose: Identify potential risks and mitigation strategies to determine what industry currency opportunities can be offered to TTAs
When to use: Before partnership planning meeting with RTOs
Time to complete: Moderate Less than 60 minutes, some preparation required
How to complete: 1. Save a copy of the tool 2. Work with relevant stakeholders to capture identified risks, risk categories, likelihood of occurrence (risk rating), potential impact to stakeholders and organisation, proposed mitigation strategies and acceptance of risk 3. Edit the template to remove or add space as needed
Go to example | Go to template
Go to template | Go to template

## Example
Example content in a table
Plan for potential risks
Potential risks | Risk category | Risk rating | People | Mitigation strategies | Mitigation owner | Risk tolerance
What potential risks might we need to mitigate to give TTAs access to industry currency opportunities? | What classification does the risk meet? Physical safety Psychosocial safety Biological or chemical hazard Legal or compliance Service delivery Reputation | How likely is it the risk will occur? Colour code: Red = high risk rating Orange = medium risk rating Green = low risk rating | Who will be impacted by the risk? Clients, family members, carers or guardians Organisation or staff RTO or TTAs | What strategies will we implement to minimise or prevent the risk? | Who will manage the risk and mitigation strategies? | Based on the risk rating and mitigation strategies, will our organisation tolerate this risk in order to achieve our objectives? Low tolerance (e.g. the risk will not be tolerated) Medium tolerance (e.g. the risk will be tolerated within agreed limitations) High tolerance (e.g. the risk will be tolerated) Colour code: Red = low risk tolerance Orange = medium risk tolerance Green = high risk tolerance
Example: Clients' family members, carers or guardians are unwilling to have TTAs involved in delivery of sports activities | Example: Service delivery Reputation | Example: Medium | Example: Clients, family members carers or guardians Organisation or staff | Example: Develop tailored messaging for clients' family members, carers or guardians Put in place an informed consent process Ensure appropriate staff support TTAs and have ultimate responsibility for child safety standards | Example: John Doe - Head of People & Culture | Example: Medium tolerance

## Template
Template table to fill out
Plan for potential risks
Potential risks | Risk category | Risk rating | People | Mitigation strategies | Mitigation owner | Risk tolerance
What potential risks might we need to mitigate to give TTAs access to industry currency opportunities? | What classification does the risk meet? -Physical safety -Psychosocial safety -Biological or chemical hazard -Legal or compliance -Service delivery -Reputation | How likely is it the risk will occur? Colour code: Red = high risk rating Orange = medium risk rating Green = low risk rating | Who will be impacted by the risk? -Clients, family members, carers or guardians -Organisation or staff -RTO or TTAs | What strategies will we implement to minimise or prevent the risk? | Who will manage the risk and mitigation strategies? | Based on the risk rating and mitigation strategies, will our organisation tolerate this risk in order to achieve our objectives? Low tolerance (e.g. the risk will not be tolerated) Medium tolerance (e.g. the risk will be tolerated within agreed limitations) High tolerance (e.g. the risk will be tolerated) Colour code: Red = low risk tolerance Orange = medium risk tolerance Green = high risk tolerance