Early Childhood Education and Care Qualification Review

Consultation Strategy

June 2025

Table of Contents

1.	Introduction	3

1.1 Project details	3

1.2 Purpose of the Consultation Strategy	3

1.3 Audience	3

2.	Background	3

2.1	Project overview	3

2.2 Importance of stakeholder engagement for project success	4

3	Stakeholder engagement objectives and scope	4

3.1 Stakeholder engagement objectives	4

3.2 Scope of stakeholder engagement activities	4

4	Stakeholder identification and analysis	5

4.1 Stakeholder identification	5

4.2 Stakeholder categories and analysis	5

5	Strategic approach	7

5.1 Engagement methods	7

5.2 Timing	9

5.3 Consultation questions	10

6	Communications	10

6.1 Communications objectives	10

6.2 Communications methods	11

7	Feedback and Consultation Log	12

8	Evaluation	12

# Introduction

## 1.1 Project details

| Project full name and code: | CHC Early Childhood Education Qualification Review (25_010) |
| --- | --- |
| Project shortform name: | ECEC Project |
| Project Manager: | Michelle Csapo |
| Consultation Manager: | TBC |

## 1.2 Purpose of the Consultation Strategy

The purpose of the Consultation Strategy is to support the review of the CHC50121 Diploma of Early Childhood Education and Care and CHC30121 Certificate III in Early Childhood Education and Care. This project will also support the National Children’s Education Workforce Strategy (2022-2031) FA5-3.  HumanAbility is specifically mentioned with regards to consultation regarding skills and workforce needs and recognition of prior learning.

The strategy includes identification and mapping of key stakeholder groups, and outlines consultation objectives, methods and timing of consultation activities. It also includes communication objectives and methods.

The strategy is underpinned by the HumanAbility Stakeholder Engagement Plan and Engagement Principles.

## 1.3 Audience

The audience for this strategy is the Project Manager, Technical Committee, Consultation Manager, Project Team, Department of Employment and Workplace Relations (DEWR) and key stakeholder groups.

# Background

## Project overview

This project responds to the skills, training and workforce-related recommendations in the Job and Skills Australia (2024) ‘The Future of Early Childhood Education Profession Early Childhood Education and Care Workforce Study’ that are within HumanAbility’s scope. The joint consultation conducted by HA and JSA during the development of the workforce study revealed a range of issues with the suitability of the existing qualifications. These issues will be addressed during the functional analysis and training product design and development stages, which will consider the training package content and skill development required at the certificate III and diploma levels. This project also responds to Recommendations in the Australian Government Productivity Commission (2024) ‘A path to universal early childhood education and care: Inquiry report.’

The primary objective of this project is to support the development of the ECEC workforce, which will enable the sector to meet current and future workforce demands. Through the review of the ECEC qualifications, HumanAbility will take into consideration relevant skills, training and workforce development findings and recommendations, that relate to HumanAbility’s role and scope, contained in the recent reports and reviews. This includes, but is not limited to:

- Job and Skills Australia’s ‘The Future of Early Childhood Education Profession Early Childhood Education and Care Workforce Study’ (2024)

- Australian Government Productivity Commission, ‘A path to universal early childhood education and care: Inquiry report’ (2024)

- Australian Children’s Education & Care Quality Authority (2023), ‘Review of child safety arrangements under the National Quality Framework: Final report – findings and recommendations for the NQF and inter-related child safety mechanisms.’

- 2019 National Quality Framework Review Decision Regulation Impact Statement (DRIS): ‘Legislative change to require compulsory training on safe sleep practices for all FDC educators subject to governments undertaking further research, costing and impact analysis of any proposed training and the implementation approach’

The project also aims to complement and build on related initiatives and reform opportunities underway. These include:

- establishment of the TAFE SA-led Centre of Excellence in Early Childhood Education and Care (CoE),

- The National Children’s Education and Care Workforce Strategy (2022-2031) Shaping Our Future,

- The Qualification Reform Design Group (2024) Final Report

- priorities for the ECEC sector identified in HumanAbility’s Workforce Plan (2024)

- Opportunity and Productivity: Towards a Tertiary Harmonisation Roadmap (2025)

- The National Children’s Education and Care Workforce Strategy (2022-2031) ‘Shaping Our Future’.

Due to the size and complexity of this project the implementation will be structured into 2 phases. The project will include a review of the CHC30121 Certificate III in Early Childhood Education and Care and the CHC50121 Diploma of Early Childhood Education and Care and other associated activities that respond to the recommendations and insights as outlined below.

## 2.2 Importance of stakeholder engagement for project success

Successful stakeholder engagement is critical to the project. It is important to hear from a diverse range of voices including employers, peak bodies, regulatory authorities and training providers across all states and territories and including metropolitan, regional and remote settings. Engagement with the Australian and state and territory governments will also be crucial.

HumanAbility will engage with key stakeholders through consultation activities to gather insights and feedback that will play an important role in shaping the qualification.

# Stakeholder engagement objectives and scope

## 3.1 Stakeholder engagement objectives

- Establish and coordinate a Technical Committee with representatives from key stakeholder groups including training providers, employers, unions, industry bodies, and government agencies.

- Foster collaboration and dialogue among stakeholders from diverse sectors including training providers, employers and workers, unions, industry bodies, government agencies and students.

- Gather diverse perspectives and insights to inform the ECEC qualification review.

- Provide effective, timely and transparent communication with stakeholders about consultation opportunities, progress and outcomes of the project.

- Ensure stakeholders feel valued, included and heard throughout the project.

- Monitor and review the impact of the project.

## 3.2 Scope of stakeholder engagement activities

In Scope

- Consultation with key stakeholders across the ECEC sector to aid in the review of the CHC50121 Diploma of Early Childhood Education and Care and CHC30121 Certificate III in Early Childhood Education and Care within the CHC Community Services Training Package - to reflect current skills, knowledge and requirements as well as job roles and units of competency.

- Engagement methods and schedule of activities as outlined in Section 5.

Out of Scope

- Engagement methods and activities outside of the project lifecycle and/or not listed under Section 5.

# Stakeholder identification and analysis

## 4.1 Stakeholder identification

Stakeholder groups have been identified and mapped in accordance with the International Association of Public Participation (IAP2) principles and practices of engagement.

The table below outlines the key stakeholders and the benefits of their involvement.

The mapping exercise identifies how we will engage with each stakeholder group and what methods will be applied - as outlined in Section 5.

Further stakeholder analysis, in consultation with the Technical Committee, will identify key stakeholder organisations and individuals to consult throughout the project lifecycle, including the methods of engagement.

A consultation log will be developed and made available at the end of the project.

## 4.2 Stakeholder categories and analysis

| Stakeholder group | Organisations | Benefits of involvement |
| --- | --- | --- |
| Consultation with the Children’s Education and Care Industry Advisory Committee (IAC) | IAC Committee / Members | Direct experience and understanding of roles and qualifications Provide advice to HumanAbility via expert representatives across the sector |
| Technical Committee with expert representatives from across the sector | See the Terms of Reference for full list | Direct experience and understanding of the roles and qualifications Provide advice to HumanAbility as expert representatives from across the sector |
| RTOs, universities, subject matter and educational experts | - TAFE SA COE - RTO Providers of the CHC50121 Diploma of Early Childhood Education and Care and CHC30121 Certificate III in Early Childhood Education and Care. - Tertiary providers of Early Childhood qualifications - Individuals /groups/organisations with specialist understanding of units - Early Childhood Teacher Education Network - RTO Communities of Practice (NSW, VIC & TAS, QLD, WA) - Subject Matter Experts identified through Expressions of Interest - TAFE NSW Industry Collaboration Reference Group - National Children’s Education and Care Workforce Strategy Stakeholder Reference Group - TAFE Directors Australia (TDA) ECEC Round Table | Direct experience and understanding of the qualifications, needs of industry, pathway opportunities and specialised nature of ECEC skills and knowledge. |
| Assurance and regulatory bodies for ECEC/Children’s Education Sector | Relevant regulatory bodies including: - Australian Children’s Education and Care Quality Authority (ACECQA) - Children’s Education and Care Assurance (CECA) ACT Education Directorate - NSW Early Childhood Education and Care Regulatory Authority, NSW Department of Education - Quality Education and Care NT (QECNT) - QLD Early Childhood Regulatory Authority Early Childhood Division, Department of Education - SA Education Standards Board - TAS Department for Education, Children and Young People - VIC Quality Assessment and Regulation Division (QARD), Department of Education - Department of Communities, Education and Care Regulatory Unit | Directly responsible for influencing ECEC systems and frameworks |
| Industry peak bodies: | Including but not limited to - Community Early Learning Australia (CELA) - Australian Childcare Alliance WA - Queensland Children's Activities Network (QCAN) – Peak for Qld - Network of Community Activities – Peak Body for NSW and ACT - Community Child Care Association – Peak for Vic - Children First Alliance (ACT) - Early Learning and Care Council of Australia - Early Childhood Australia (ECA) - Australian Local Government Association - Family Day Care Australia | Advocates for improved training and pathway opportunities. Opportunities to leverage their memberships for involvement in the project including potential for these bodies to host consultation workshops. |
| Unions | - Australian Education Union - United Workers Union - Independent Education Union | Advocate for improved training and pathway opportunities for ECEC/related roles |
| Relevant commonwealth, state and territory government departments and agencies, along with the skills and training departments | Including but not limited to: - Australian Government Department of Education Workforce Working Group - Australian Skills Quality Authority (ASQA) - Australian Government Department of Education Early Childhood Policy Group (ECPG) - Australian Government Department of Education - VIC Department of Education (Early Childhood Education Group) - SA Department for Education - Government of South Australia Office for Early Childhood Development - WA Department of Communities - TAS Department of Education, Children and Young People - NT Department of Education and Training - ACT Education Directorate - QLD Department of Education - NSW Department of Education - NSW Department of Education Early Childhood Outcomes - NSW Education, Early Childhood Education and Care Directorate - Skills Canberra – ACT Government - Department of Trade, Employment and Training QLD - Skills SA - Skills Tasmania, Department of State Growth - Victorian Skills Authority - Department of Training and Workforce Development WA | Ability to influence and develop state-based ECEC strategies and policies for high impact through funding models and workplace-based initiatives. Opportunities to explore the development of micro-credentials or skill sets. |
| ECEC Centre of Excellence (CoE) | TAFE SA Centre of Excellence Early Childhood Education and Care | Opportunity to co-design training products to eliminate duplication, maximise quality, develop Autism products, translate ECEC concepts. Opportunities for mentoring/leadership for educator growth and retention. |
| Employers / Service Providers | Employers/service providers across all states and territories including metropolitan, regional, remote and very remote delivering ECEC services will be given the opportunity to engage in this project. | Direct experience in attracting, recruiting, and retaining the workforce |
| Priority cohort - Aboriginal and Torres Strait Islanders | Including but not limited to: - SNAICC - ACCOs | Provides First Nations people with the opportunity to actively contribute to project outcomes. |
| Industry Training Advisory Boards | The funded ITAB/ITAC/IAG in each state and territory. | Understanding of the qualification |

# Strategic approach

## 5.1 Engagement methods

| Method | Purpose | Who | Timing |
| --- | --- | --- | --- |
| Consultation with the Children’s Education and Care Industry Advisory Committee (IAC) | To provide advice on the establishment of the Technical Committee, and suggestions for engagement and feedback on project deliverables | HumanAbility Children’s Education and Care Industry Advisory Committee | At scheduled IAC meetings (during the lifecycle of the project) |
| Consultation with the Technical Committee | To support development and provide advice on project deliverables. The Committee will include subject matter experts from key stakeholder groups and national coverage. | As listed in section 4.2 | Technical committee meetings for this project will occur at these points as a minimum: - At project set up - Post functional analysis - Post qualification drafting / pre consultation - Post consultation/pre submission Additional meetings or out of session consultation will be arranged as the need arises |
| Targeted meetings with Regulatory Bodies, Department of Ed, ECEC working group ECPG & Education Ministers. Targeted meetings with STAs and ITABS | To support and provide advice on the project and jurisdictional needs | Dept of Ed, ECEC WWG, ECPG & Education Ministers | Timing and mechanisms to be discussed and agreed with DE/DEWR STA and ITAB targeted meetings to occur post each Technical Committee Meeting. - At project set up - Post functional analysis - Post qualification drafting / pre consultation - Post consultation/pre submission |
| Interviews | A minimum of 16 virtual and potential maximum of 32 interviews- including interviews in each state/territory, metro, regional remote and very remote settings – with interviews sought across representatives for First Nations, Children with a Disability, CALD, and across the various settings in ECEC e.g. LDC, Pre-school, FDC, IHC. This will include interviews with employers to discuss settings, current roles, functions and tasks for ECEC workers, ensuring that nuances between different jurisdictions and regulatory requirements are identified. Minimum 5 virtual functional analysis workshops will be conducted. | Employers / service provider as per 4.2 | June ’25 to July ‘25 |
| Specialist subject focus group workshops | To gain expert knowledge to inform training product development in specialist subject areas. | Employers, employees, academics, peaks, VET trainers and assessors and others with specialist knowledge | Nov 2025 – Feb 2026 |
| Consultation workshops – in person – 16 | To facilitate group discussions to understand challenges and workshop possible solutions 16 face-to-face workshops – including workshops in each state/territory, metropolitan and regional area – 10 metropolitan, 6 regional. | All interested stakeholders | 2 March – 30 May) 2026 |
| Consultation workshops – online -8 | To facilitate group discussions that will help to understand needs, challenges, gaps, solutions and improvements for the qualifications 8 virtual workshops will be undertaken with participants being drawn from across all states and including metropolitan, regional and remote settings. | All interested stakeholders | 2 March – 30 May 2026 |
| Online second round public consultation online | To review draft revisions based on first round of consultation and to facilitate consensus on areas of varying viewpoints. | Public with stakeholders who participated in the previous round of consultation targeted. | June – August 2026 |
| Surveys | To consult with all participants (e.g. employers, training organisations, industry) | All stakeholders | Open throughout consultation period |
| External meetings and events | To leverage opportunities to promote the project, gain buy-in and encourage participation | All stakeholders | As required |
| Professional development workshops | Approximately 5-8 virtual professional development sessions depending on demand. To conduct professional development workshops on the new qualification and good practice for delivery and assessment. | Targeting trainers and assessors | Jan to April 2027 |

## 5.2 Timing

| Project stage | Timing | Engagement methods |
| --- | --- | --- |
| Project set up and initial drafting | May 2025– Feb 2026 | Consultation with Children’s Education and Care IAC – to gather insights on Technical Committee membership and stakeholder identification Consultation with Technical Committee to gather advice on Consultation Strategy and initial draft products/deliverables Functional analysis interviews and functional analysis employee workshops Meetings with Australian Government and State and Territory Education departments, State & Territory Regulators, ITABs, ACECQA, RTOs Written communications/publications Functional analysis report finalised |
| Public and government consultation (minimum of 8 weeks) and incorporating feedback | Mar – Aug 2026 | All methods as above including face to face and online workshops. Consultations will be planned in each state and territory and consider access for metro, regional, remote and very remote locations Technical Committee to gather advice on incorporating feedback Written communications/publications |
| Final submissions and reporting | Sep – Nov 2026 | Technical Committee to gather advice on final draft products/deliverables Consultation with IAC Written communications/publications |
| Senior Officials Check (2 weeks) | Sep 2026 – Oct 2026 | Respond to queries as required |
| Endorsement and release | –Nov 26 April 2027 | Written communications/publications Professional development workshops |

## 5.3 Consultation questions

Consultation questions will be developed by the project team and refined by the Technical Committee.

Consultation with stakeholders will be structured to:

- Understand the current industry and the skills, knowledge, practice and requirements needed for the ECEC qualifications.

- Understand the current challenges, skills gaps, opportunities and potential solutions

- Identify and inform any changes for the qualification and units of competency and skill sets.

- Provide advice on the development of resources, guidance on delivery and pathways information.

# Communications

## 6.1 Communications objectives

- Raise awareness of the project and its objectives among Early Childhood Education and Care industry stakeholders.

- Promote consultation opportunities, key dates, project progress and outcomes to stakeholders through a variety of communications channels.

- Foster the involvement of a diverse range of stakeholders to gather rich and valuable industry insights, experience and expertise to inform the project.

- Build trust and credibility with stakeholders through effective, timely, transparent and accessible communications.

## 6.2 Communications methods

| Communications channel / tool | Purpose / Details |
| --- | --- |
| Key messages | To outline the key details of the project, timelines, activities in preparation for consultation and communication across all channels |
| Frequently asked questions | To outline the key details of the project, timelines, activities in preparation for consultation and communication across all channels |
| Information sheet or flyer | To outline the key details of the project, timelines, consultation activities and how to participate. Including link to website/project page. |
| HumanAbility website | To provide a dedicated webpage where all project information and activities can be accessed easily. This webpage will include an engagement portal for stakeholders to register interest, provide submissions and feedback, register for consultation sessions and access project updates. |
| Email/Email Template or Campaign | To send emails/email template letters, information and updates to stakeholders to participate in consultation / share consultation opportunities. |
| News Alerts | To provide project participants and other key stakeholders with branded news alerts via email when there is a project update. |
| HumanAbility newsletter articles | To provide project updates in HumanAbility’s general newsletter. |
| Social media | To publish project consultation opportunities, updates, and other activities on HumanAbility’s social media channels including LinkedIn and Facebook to reach as many and diverse stakeholders as possible. Social media posts will link to the HumanAbility webpage to encourage engagement on the project. Stakeholders can increase HumanAbility’s social media reach by sharing content on their social media channels. |
| Industry news media | To leverage relationships with key stakeholder organisations with newsletters to share HumanAbility project consultation opportunities and other activities. |
| Connect and communicate with networks | To contact and link in with industry networks, peak bodies, existing workforce committees/groups and IAC networks to promote the opportunity to participate in the project consultation. Identify and connect with communications departments of industry stakeholders to encourage promotion of consultation activities - Email key messages about the project, image/s, information sheet - Tag organisations in social media where relevant – link to website consultation page - Link in with industry events/meetings and hand out material (e.g. info sheet) |
| Events/Speaking engagements | To host regular HumanAbility events/speaking engagements e.g. via webinar or in person – providing updates to industry and project stakeholders |
| Resources | To publish resources - the companion volume will be updated to reflect the new qualifications, skill sets and units of competency, along with guidance on delivery, pathways and mapping information. |

# Feedback and Consultation Log

Stakeholder feedback will be gathered during the consultation via workshops and interviews/surveys. Stakeholders may also submit feedback via the Training Product Advice Service (web form) and the training product project email address trainingproducts@humanability.com.au, which appears on the project page.

Surveys will be the primary mechanism for structured individual feedback during public consultation. This ensures that feedback can be quantified, analysed qualitatively (thematic analysis) and that the outcomes/response can be tracked as required by the Training Package Organising Framework.

Individual feedback will be captured in the Consultation Log. This also captures the organisation name, stakeholder type, State and the method of communication/consultation. Stakeholder names and contact details will also be collected to enable HumanAbility to clarify and follow up on the feedback if needed. However, these are not included in the published version of the Consultation Log and are not submitted to the funding body.

As the feedback is reviewed, the action taken in response to the feedback will be documented in the Consultation Log. Where feedback is not incorporated, the rationale for this will also be documented.

Where feasible, the themes identified from consultation workshops will be added to the Consultation Log.

The Consultation log will be published on the project page after consultations and incorporation of feedback is complete.

# Evaluation

The effectiveness of the Consultation Strategy will be evaluated using the following measures:

- Analysis of stakeholder type and location

- Number of interviews achieved in pre-draft and functional analysis work

- Attendance at consultation workshops

- Number of dedicated website page visits and submissions made in the portal

- Social media posts, engagement and reach (on HumanAbility social media pages and other social media pages)

- Newsletter articles / news items published by stakeholders

- Meetings held / attendance / topics

- An increase in enrolments and completions of the relevant qualifications.

The Technical Committee and Industry Advisory Committee will also be asked to provide advice relating to the effectiveness of the Consultation Strategy in driving project outcomes.