School Based Education Support Qualification Review Consultation Strategy 2026

Table of Contents

1.Introduction	3

1.1	Project details	3

1.2	Purpose of the consultation strategy	3

1.3	Intended audience	3

2	Background	3

2.1	Project overview	3

2.2	Importance of stakeholder engagement for project success	5

2.3	Potential sensitivities	5

3	Stakeholder engagement objectives and scope	6

3.1 Stakeholder engagement objectives	6

3.2	Scope of stakeholder engagement activities	6

4	Stakeholder identification and analysis	7

5	Strategic approach	12

5.1	Engagement methods	12

5.2	Timing	16

5.3	Consultation questions	16

6	Communications	17

6.1	Communications objectives	17

6.2	Communications methods	17

7	Feedback and consultation log	18

8	Evaluation	19

# 1.Introduction

## Project details

| Project full name and code: | 27-003 CHC School Based Education Support Qualification Review Project |
| --- | --- |
| Project shortform name: | SBES Project |
| Project Sponsor: | Michelle Csapo |
| Project Director: | Rosalie Staggard |
| Engagement Manager: | Wendy Allan |

## Purpose of the consultation strategy

The purpose of this Consultation Strategy is to support the review and update the CHC30221 Certificate III in School Based Education Support, and CHC40221 Certificate IV in School Based Education Support, and consider the development of a Diploma of School Based Education Support. The review will also consider the revision of units or the creation of new units to support potential pathway opportunities between school-based education and support (SBES), early childhood education and care (ECEC) and outside school hours care (OSHC) and related sectors.

This strategy is underpinned by the HumanAbility Stakeholder Engagement Plan and Engagement Principles. It identifies and maps key stakeholder groups in line with tripartite and other obligations as set out in the Training Package Organising Framework (TPOF) and HumanAbility’s Technical Committee Terms of Reference, and outlines consultation objectives, engagement and communication methods, and the timing of activities.

## Intended audience

This strategy is written for the Project Team including the Project Manager, Technical Committee, Engagement Manager, Department of Employment and Workplace Relations (DEWR) and key stakeholder groups.

# Background

## 2.1	Project overview

This project will review and update the CHC30221 Certificate III in School Based Education Support, and CHC40221 Certificate IV in School Based Education Support, and consider the development of a Diploma of School Based Education Support. The review will also consider the revision of units or the creation of new units to support potential pathway opportunities between school-based education and support (SBES), early childhood education and care (ECEC) and outside school hours care (OSHC) and related sectors.

The project builds directly on analysis and consultation conducted through the HA 25-006 CHC Outside School Hours Care project, which identified significant workforce movement between teaching assistant roles and OSHC workers. While this highlighted opportunities to strengthen qualification pathways, consultation also identified substantial barriers, including the absence of suitable units and differences between ACECQA licensing requirements and school system policy and operational frameworks. These findings demonstrated the need for a coordinated review of SBES qualifications to better support workforce mobility while recognising distinct sector requirements.

A review of ECEC qualifications is currently underway, with the SBES activity submission to be submitted in the May 2026 round. Because SBES, OSHC, and ECEC are closely connected, reviewing these qualifications together will provide a comprehensive, coordinated assessment of shared skills and knowledge and help identify realistic, meaningful pathway options across sectors. This approach will ensure qualifications meet the specific operational and workforce needs of the OSHC sector while also supporting career progression and cross-sector mobility and will allow qualification design to accommodate the diverse and nuanced policy, regulatory, and operational requirements across states, territories, and school systems.

Child safety is a central consideration of this review. The HumanAbility Children’s Education and Care Industry Advisory Committee (CEC IAC) meeting on 3 July 2025 emphasised the importance of strengthening child safety outcomes through qualification design, including consideration of a new unit of competency to supersede CHCPRT025 Identify and Report Children and Young People at Risk. Consultation undertaken as part of the CHCPRT025 project indicated that the unit does not align well with school-based child safety policies and reporting arrangements, which are typically administered through education systems rather than service based regulatory frameworks. Stakeholders also noted that school-based staff are frequently required to complete additional state or system specific training to meet local obligations.

Further feedback from stakeholders, including from the CEC IAC identified that CHCPRT025 does not adequately prepare school-based staff to respond to incidents, including the application of reporting mandates. In addition, the Review of Child Safety Arrangements under the National Quality Framework (2023) and stakeholder feedback highlighted the need for child safety units to address considerations beyond mandatory reporting alone. Taken together, this evidence supports the development of a new child safety unit specifically designed for school-based contexts.

The review will need to balance the specific needs of the SBES sector with opportunities to support qualification progression and interrelated sector pathways. A coordinated, suite-based approach across SBES, OSHC, and ECEC qualifications will support workforce development and mobility while recognising the distinct roles, responsibilities, and regulatory environments in each setting. This work is occurring in the context of broader sector discussion regarding the future regulatory environment for OSHC, including a position paper from the Australian Primary Principals Association highlighting the developmental and operational distinctions between early childhood and school-aged care and questioning the suitability of current regulatory arrangements for OSHC settings.

Considering this, the project will consider how units of competency can be designed to be as future ready as possible should regulatory settings evolve. Pathway opportunities between OSHC, SBES, and ECEC qualifications will be explored to maintain alignment while allowing flexibility. The Australian Primary Principals Association will be invited to participate in the consultation to inform this work.

## Importance of stakeholder engagement for project success

Successful stakeholder engagement is critical to the project. It is important to hear from a diverse range of voices, including employers, peak bodies, regulatory authorities, training providers, and industry associations, across all states and territories and from various locations, including metropolitan, regional, and remote settings.

HumanAbility will engage with a range of key stakeholders through consultation activities to gather insights and feedback that will help shape the training products.

## Potential sensitivities

A key sensitivity for this project relates to child safety. While child safety is already identified as a central consideration, proposals to reconsider the use of CHCPRT025 Identify and Report Children and Young People at Risk, including the possible development of a new unit and how requirements are addressed at lower qualification levels, may raise concerns among jurisdictions and education systems because child safety obligations are tightly regulated, state-specific, and highly scrutinised. Stakeholders have differing expectations about the role of qualifications versus system-based training in preparing staff to identify, respond to, and report incidents, and perceptions that changes could weaken or complicate existing arrangements will need careful management through consultation and clear scoping.

# Stakeholder engagement objectives and scope

## 3.1 Stakeholder engagement objectives

Establish a Technical Committee comprised of representatives from key, tripartite stakeholder groups, including training providers, employers, unions, peak bodies, and government agencies, reflecting the broader scope of this project and in line with TPOF requirements.

Foster engagement and dialogue among stakeholders from diverse sectors including training providers, employers, learners and workforce, unions, industry bodies, government agencies and students.

Gather diverse perspectives and insights from across the country, including regional, remote and very remote areas, to inform this project.

Provide effective, timely and transparent communication with stakeholders about consultation opportunities, progress and outcomes of the project.

Ensure stakeholders feel valued, included and heard throughout the project.

Monitor and review the impact of the project.

## Scope of stakeholder engagement activities

In Scope

- Consultation with key stakeholders across the schools’ sector to:

review the SBES qualifications to ensure nationally consistent outcomes for learners.

improve the qualification architecture to support skills and workforce mobility

alignment of training products.

engagement with activities as outlined in Section 5.

Out of Scope

Engagement with activities outside of the project lifecycle and/or not listed in Section 5.

# Stakeholder identification and analysis

Stakeholder groups have been identified and mapped in accordance with the International Association of Public Participation (IAP2) principles and practices of engagement.

The table below outlines each stakeholder group along with the benefits of their involvement in this project.

Further stakeholder analysis, in consultation with the Technical Committee, will identify key stakeholder organisations and individuals to consult throughout the project lifecycle and methods of engagement.

A completed consultation log outlining all stakeholder feedback will be made available on completion of the project.

Table 1: Stakeholder categories and analysis

| Stakeholder group | Organisations | Benefits of involvement |
| --- | --- | --- |
| Children’s Education and Care Industry Advisory Committee (IAC) | IAC Committee / Members | Direct experience and understanding of the roles and qualification Provide advice to HumanAbility via expert representatives across the sector |
| Industry Training Advisory Bodies or jurisdiction equivalents | The funded ITAB/ITAC/IAG in each state and territory | Understanding of the qualification. Provide nuanced state/territory advice to HumanAbility as expert representatives from across the sector |
| Technical Committee with expert representatives from across the sector | See the Terms of Reference for full list | Direct experience and understanding of the roles and qualification Provide advice to HumanAbility as expert representatives from across the sector Tripartite composition (where relevant unions have coverage |
| RTOs and educational experts | Current providers of the CHC30221 Certificate III in School Based Education Support and, CHC40221 Certificate IV in Schools Based Education and Support including: TAFE SA as the Centre of Excellence for Early Childhood Education and Care RTOs delivering SBES qualifications | Direct experience and understanding of the qualification/needs of the industry |
| Regulatory bodies for school-based support with the education sector, including occupational or industry regulators as applicable | Relevant regulatory bodies including: Australian Government Department of Education Australian Institute for Teaching and School Leadership (AITSIL) Children’s Education and Care Assurance (CECA) ACT Education Directorate Department of Communities, Education and Care Regulatory Unit NSW Early Childhood Education and Care Regulatory Authority, NSW Department of Education QLD Early Childhood Regulatory Authority Early Childhood Division, Department of Education Quality Education and Care NT (QECNT) SA Education Standards Board TAS Department for Education, Children and Young People Teacher Regulatory Authorities in each jurisdiction Victorian Early Childhood Regulatory Authority (previously QARD) | Have direct influence on the system, any intersecting education system(s), and any application occupation practice standards or regulatory requirements |
| Industry peak bodies | - Including but not limited to: Anglican Schools Australia Association of Independent Schools ACT Association of Independent Schools NSW Association of Independent Schools SA Association of Independent Schools WA Australian Association of Christian Schools Australian Primary Principals Association Australian Secondary School Principals Association Australian Special Education Principals Association (ASEPA) Australian Teacher Aide Catholic Education NT Catholic Education SA Catholic Education Tasmania Catholic Education WA Catholic Schools NSW Independent Schools Australia Independent Schools Northern Territory Independent Schools Queensland Independent Schools Tasmania Independent Schools Victoria National Aboriginal and Torres Strait Islander Education Corporation (NATSIEC) National Aboriginal and Torres Strait Islander Principals Association (NATSIPA) National Catholic Education Commission QLD Catholic Education Commission Victorian Catholic Education Authority | Advocate for improved training and pathway opportunities for OSHC and related roles. Opportunities to leverage their memberships for involvement in the projects including potential for these bodies to host consultation workshops. |
| Unions | Including but not limited to: Australian Education Union Independent Education Union United Workers Union | Advocate for improved training and pathway opportunities for SBES roles |
| Relevant commonwealth, state and territory government departments and agencies, along with the skills and training departments | Including but not limited to: ACT Education Directorate Australian Government Department of Education Department of Employment and Workplace Relations (DEWR) NT Department of Education and Training QLD Department of Education SA Department for Education NSW Department of Education WA Department of Education Schools Policy Group via Department of Employment and Workplace Relations updates TAS Department of Education, Children and Young People VIC Department of Education | Develop state-based strategies that have high impact through funding models and place-based initiatives |
| Employers | Employers (Government, independent, faith-based schools) in all states and territories will be given the opportunity to engage in this project | Direct experience in attracting, recruiting, and retaining the workforce |
| Priority cohorts - Aboriginal and Torres Strait Islanders Children with a Disability | Including but not limited to: Australian Children with a Disability (ACD) Children and Young People with Disability Australia (CYDA) NACCHO SNAICC VAEAI Victorian Aboriginal Education Association Inc | Consultation with and designed in partnership with SNAICC supports culturally responsive engagement with First Nations people and services to actively contribute to project outcomes. Consult with appropriate stakeholder groups noting the importance of education assistance in supporting students with additional needs |

# Strategic approach

## Engagement methods

| Method | Purpose | Who | Timing |
| --- | --- | --- | --- |
| Meetings and consultation with the Children’s Education and Care Industry Advisory Committee (IAC) | To provide advice on the establishment of the Technical Committee, and suggestions for engagement and feedback on project deliverables | HumanAbility Children’s Education and Care Industry Advisory Committee | At scheduled IAC meetings (during the lifecycle of the project) |
| Meetings and consultation with the Technical Committee | To support development and provide advice on project deliverables The Committee will include subject matter experts from key stakeholder groups and national coverage | As listed in Section 4.2 | As needed throughout the project lifecycle Five scheduled meetings Project set-up Post functional analysis Technical Committee meeting pre- publication of the report Post draft materials pre consultation Post consultation Pre-submission |
| Meetings and consultation with STAs, ITABS and other government departments | Update on the project, raise contentions issues, challenges, clockers, seek stakeholder contacts and feedback on design | STAs, ITABS, Government Departments as listed in Section 4.2 | As needed throughout the project lifecycle Five scheduled opportunities Project set-up Post functional analysis Technical Committee meeting pre- publication of the report Post draft materials pre consultation. Post consultation Pre-submission |
| RTO discussions via interviews and focus group interviews utilising existing communities of practice and Centre of Excellence x 5 | To understand current qualification implementation issues, student barriers and recommendations | RTOs currently or likely to deliver the qualifications under review | Stage 1 Project set up |
| Interviews - 20 virtual interviews – at least one (1) interviews in each state/territory, metro, regional and remote settings | Ensuring that nuances between different jurisdictions and regulatory requirements are identified To expand understanding of job roles to inform qualification design | Employers / service provider as per Section 4.2 to discuss settings, current roles, functions and tasks for SBES | Stage 1 Project set-up |
| Employee workshops – 3 online workshops | To facilitate group discussions that will help to understand needs, challenges, gaps, solutions and improvements for the qualifications To gain deep understanding of day in life job task roles and undertake career journey mapping to inform qualification design | All interested stakeholders - participants drawn from across all states and including metropolitan, regional and remote settings | Stage 1 Project set-up |
| SME Workshops - online sessions | To engage subject matter expert involvement in the review and development of qualification packaging rules and units of competency | Subject matter expert pool with expert categories to be established during the functional analysis thematic analysis. EOIs to be sought | Stage 2 Initial development |
| Consultation workshops –12 face-to-face full- day and 3 online workshops in each state/territory, metropolitan and regional/remote depending on heat map analysis of delivery locations | To facilitate group discussions to understand challenges and workshop possible solutions To review draft materials | All interested stakeholders | Stage 3 Public and government consultation |
| Validation process – online surveys and public online sessions | To facilitate validation of the training products post public and government consultation | All interested stakeholders | Stage 4 Incorporating feedback and validation |
| Online consultation portal on the HumanAbility website | To engage all participants This is a two-way channel that enables project documents, including a consultation paper to be publicly available and capture stakeholder feedback, comments, and submissions | All stakeholders | Open throughout consultation period |
| Surveys | To consult with all participants (for example employers, training organisations, industry) | All stakeholders. May be used to support interaction with Technical Committee, SMEs and during consultation | Stage 2 Initial development, Stage 3 Public and government consultation and Stage 4 Incorporating feedback. |
| External meetings and events | To leverage opportunities to promote the project, gain buy-in and encourage participation | Various stakeholders as relevant | As required |
| Five (5) online professional development implementation workshops | To conduct professional development workshops on the new qualification and good practice for delivery and assessment. | Targeting trainers and assessors | Post endorsement |

## Timing

| Project stage | Timing | Engagement methods |
| --- | --- | --- |
| Stages 1 and 2 - Project set up and initial drafting | 3/8/2026 – 12/2/2027 | Consultation with Children’s Education and Care IAC – to gather insights on Technical Committee membership and stakeholder identification Consultation with Technical Committee to gather advice on Consultation Strategy and initial draft products/deliverables Written communications/publications Functional analysis report finalised |
| Stages 3 and 4 - Public and government consultation, incorporating feedback and validation | 15/2/2027 - 24/9/2027 | All methods as above Technical Committee to gather advice on incorporating feedback Written communications/publications Public validation |
| Stages 4 and 5 - Final submissions and reporting | 10/05/2027 - 22/10/2027 | Technical Committee to gather advice on final draft products/deliverables Consultation with IAC Written communications/publications |
| Stages 6, 7 and 8 - Endorsement and release | 25/10/2027 - 28/1/2028 | Written communications/publications Professional development workshops |

## Consultation questions

Consultation questions will be developed by the project team and refined by the Technical Committee.

Consultation with stakeholders will be structured to:

understand industry requirements in terms of skills, knowledge, and practice for SBES qualifications

understand current challenges, skills gaps, opportunities and potential solutions

identify and inform of any changes to training products

provide advice on the development of resources, delivery and pathway information

review draft materials.

# Communications

## Communications objectives

Raise awareness of the project and its objectives among industry stakeholders.

Promote consultation opportunities, key dates, project progress and outcomes to stakeholders through a variety of communications channels.

Foster the involvement of a diverse range of stakeholders to gather rich and valuable industry insights, experience and expertise to inform the project.

Build trust and credibility with stakeholders through effective, timely, transparent and accessible communications.

## Communications methods

| Communications channel / tool | Purpose / Details |
| --- | --- |
| Project webpage | A dedicated webpage where all project information and activities can be accessed easily, stakeholders can register for updates and consultation workshops. |
| Emails | To send information and updates to stakeholders. |
| Newsletter updates | Project updates in HumanAbility’s monthly newsletter. |
| Social media (Facebook, LinkedIn) | To publish project information, workshop opportunities, general updates on the project’s progress. |
| Industry news media | To leverage relationships with key stakeholder organisations with newsletters to share HumanAbility project consultation opportunities and other activities. |

# Feedback and consultation log

Stakeholder feedback will be gathered during the consultation via workshops, interviews, and surveys. Stakeholders may also submit feedback via the Training Product Advice Service (web form) and the training product project email address: trainingproducts@humanability.com.au, which appears on the project page.

HumanAbility’s consultation portal will be the primary mechanism for structured individual feedback during public consultation. This ensures that feedback can be quantified, analysed qualitatively (thematic analysis) and the outcomes/responses can be tracked as required by the Training Package Organising Framework.

Individual feedback will be captured in the Consultation Log. This also captures the organisation name, stakeholder type, State and the method of communication/consultation. Stakeholder names and contact details will also be collected to enable HumanAbility to clarify and follow up on feedback if needed. However, these identifying details are not included in the published version of the Consultation Log and are not submitted to the funding body.

As the feedback is reviewed, the action taken in response to the feedback will be documented in the Consultation Log. Where feedback is not incorporated, the rationale for this will also be documented.

The Consultation Log will be published on the project page after both consultations are completed, and subsequent feedback has been incorporated.

# Evaluation

The effectiveness of the Consultation Strategy will be evaluated using the following measures:

analysis of stakeholder type and location

number of interviews achieved in pre-draft and functional analysis work

attendance at consultation workshops

number of dedicated website page visits and submissions made in the portal

social media posts, engagement and reach (on HumanAbility social media pages and other social media pages)

newsletter articles / news items published by stakeholders

meetings held / attendance / topics

increase in enrolments and reduction in completions of the relevant qualifications.

The Technical Committee and Children’s Education and Care IAC will also be asked to provide advice relating to the effectiveness of the Consultation Strategy in driving project outcomes.

www.humanability.com.au