## Gantt Chart
FY25 planning
| Description | Owner | Start Date | End Date | Days | % Complete | 2024-09-02 |  |  |  |  | 2024-09-09 |  |  |  |  | 2024-09-16 |  |  |  |  | 2024-09-23 |  |  |  |  | 2024-09-30 |  |  |  |  | 2024-10-07 |  |  |  |  | 2024-10-14 |  |  |  |  | 2024-10-21 |  |  |  |  | 2024-10-28 |  |  |  |  | 2024-11-04 |  |  |  |  | 2024-11-11 |  |  |  |  | 2024-11-18 |  |  |  |  | 2024-11-25 |  |  |  |  | 2024-12-02 |  |  |  |  | 2024-12-09 |  |  |  |  | 2024-12-16 |  |  |  |  | 2024-12-23 |  |  |  |  | 2024-12-30 |  |  |  |  | 2025-01-06 |  |  |  |  | 2025-01-13 |  |  |  |  | 2025-01-20 |  |  |  |  | 2025-01-27 |  |  |  |  | 2025-02-03 |  |  |  |  | 2025-02-10 |  |  |  |  | 2025-02-17
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | FY25 Top Down
1.1 | 2/3 Year Target Created | Finance | 2024-09-04 | 2024-09-18 | 14 | 20% | bar: 2024-09-02 M to 2024-09-09 F
1.2 | Finance / RevOps Feedback on inputs & Levers | Finance/RevOps | 2024-09-04 | 2024-09-18 | 14 | 0% | bar: 2024-09-02 M to 2024-09-09 F
1.3 | Communicated to Execs/Sales | Finance | 2024-09-18 | 2024-09-23 | 5 | 0% | bar: 2024-09-16 M to 2024-09-16 F
2 | FY25 Bottoms Up
2.1 | Level Set on Strategy with CRO (Changes, Beliefs, Items to follow up on) | CRO/RevOps | 2024-09-18 | 2024-09-23 | 5 | 0% | bar: 2024-09-16 M to 2024-09-16 F
2.1.1 | Data Gathering, Review FIndings, Align on Top Level Strategy | RevOps/CRO | 2024-09-19 | 2024-10-03 | 14 | 0% | bar: 2024-09-16 T to 2024-09-23 F
2.2 | Provide Strategy / Rough Targets / Guardrails to SVP Geo Sales | CRO | 2024-10-03 | 2024-10-03 | 0 | 0% | bar: 2024-09-30 M
2.2.1 | Provide Capacity Modeler to SVP Geo Sales | RevOps | 2024-10-03 | 2024-10-03 | 0 | 0% | bar: 2024-09-30 M
2.2.2 | Bottoms Up Strategy Developed (Objectives - Start/Stop/Continue) | RevOps / SVPs | 2024-10-03 | 2024-10-21 | 18 | 0% | bar: 2024-09-30 M to 2024-10-14 R
2.2.3 | Present findings back to CRO (Strategy, Projected Revenue, HC Needed) | SVP Sales | 2024-10-21 | 2024-10-21 | 0 | 0% | bar: 2024-10-14 F
2.2.4 | Align Cross Functional Inputs based on Plan | ALL/RevOps | 2024-10-23 | 2024-10-28 | 5 | 0% | bar: 2024-10-21 M to 2024-10-21 F
2.3 | SVP Geo Sales / CRO align on direction & Targets | CRO/RevOps | 2024-10-23 | 2024-10-28 | 5 | 0% | bar: 2024-10-21 M to 2024-10-21 F
3 | Lock on Targets (Revenue & HC)
3.1 | Lock in on Revenue Targets and HC (i.e. Cost's) | CRO/CFO/RevOps | 2024-10-30 | 2024-11-11 | 12 | 0% | bar: 2024-10-28 M to 2024-11-04 F
3.2 | Adjust Geo Design/Hierarchy based on Agreed Rev Targets, Costs & Needs, Priority, Focus | CRO/RevOps | 2024-11-13 | 2024-11-17 | 4 | 0% | bar: 2024-11-11 M to 2024-11-11 F
3.3 | Design Geo HC Based on Needs, Priority, Focus | CRO/RevOps | 2024-11-13 | 2024-11-17 | 4 | 0% | bar: 2024-11-11 M to 2024-11-11 F
3.4 | Determine Geo Revenue targets based on Key Metrics (Capacity, Historicals, Pipeline) | CRO/RevOps | 2024-11-13 | 2024-11-17 | 4 | 0% | bar: 2024-11-11 M to 2024-11-11 F
3.5 | Communicate Geo Revenue targets | CRO/RevOps | 2024-11-20 | 2024-11-24 | 4 | 0% | bar: 2024-11-18 M to 2024-11-18 F
3.5 | Determine Area/Region revenue targets based on Key Metrics and Communicate (1 Week per level in Hierarchy) | CRO/RevOps | 2024-11-27 | 2024-12-01 | 4 | 0% | bar: 2024-11-25 M to 2024-11-25 F
4 | Segmentation & Territories
4.1 | Implement Account Scoring - Methodology (Key Metrics) | RevOps | 2024-10-30 | 2024-11-11 | 12 | 0% | bar: 2024-10-21 M to 2024-10-21 F; 2024-11-04 M to 2024-11-04 F
4.2 | Agreement on Parameters for Territories | RevOps / CRO | 2024-11-13 | 2024-11-17 | 4 | 0% | bar: 2024-11-11 M to 2024-11-11 F
4.3 | Provide design Templates to First Line Managers & Guidance | RevOps | 2024-12-04 | 2024-12-16 | 12 | 0% | bar: 2024-12-02 M to 2024-12-09 F
4.4 | Review Design of Territories - Ensure Optimization | RevOps / Sales Leadership | 2024-12-18 | 2024-12-22 | 4 | 0% | bar: 2024-12-16 M to 2024-12-16 F
4.5 | Lock on HC & Territory Designs | RevOps / Sales Leadership | 2025-01-01 | 2025-01-05 | 4 | 0% | bar: 2024-12-30 M to 2024-12-30 F
5 | Pipeline Targets
5.1 | Determine Desired Coverage (what is your Win Rate?) | RevOps | 2025-01-08 | 2025-01-12 | 4 | 0% | bar: 2025-01-06 M to 2025-01-06 F
5.2 | Determine Source Create Breakdowns (Partner, AE, ISR, Marketing) | RevOps | 2025-01-08 | 2025-01-12 | 4 | 0% | bar: 2025-01-06 M to 2025-01-06 F
5.3 | Take Target by Region and Model Expected Needs | RevOps | 2025-01-08 | 2025-01-12 | 4 | 0% | bar: 2025-01-06 M to 2025-01-06 F
6 | Comp Plans
6.1 | Align on Business Expectations (Cost, Behaviors, Outcomes expected) | CRO/CFO/RevOps | 2024-11-13 | 2024-11-17 | 4 | 0% | bar: 2024-11-11 M to 2024-11-11 F
6.2 | Put together proposal based on inputs from leadership (and trusted 1st line mgrs) | RevOps / Comp | 2024-11-20 | 2024-12-02 | 12 | 0% | bar: 2024-11-18 M to 2024-11-25 F
6.3 | Review with Leadership. Tweak / adjust / Refine. | CRO/CFO/RevOps | 2024-11-27 | 2024-12-09 | 12 | 0% | bar: 2024-11-25 M to 2024-12-02 F
6.4 | Lock on Comp Plan Design | CRO/CFO/Leadership/RevOps | 2024-12-11 | 2024-12-15 | 4 | 0% | bar: 2024-12-09 M to 2024-12-09 F
6.5 | Update Logic in Comp System | Comp/Systems | 2025-02-05 | 2025-02-09 | 4 | 0% | bar: 2025-02-03 M to 2025-02-03 F
6.6.1 | Renewal Scrub #1 | RevOps/Sales Team | 2025-01-01 | 2025-01-05 | 4 | 0% | bar: 2024-12-30 M to 2024-12-30 F
6.6.2 | Renewal Scrub #2 | RevOps/Sales Team | 2025-02-05 | 2025-02-09 | 4 | 0% | bar: 2025-02-03 M to 2025-02-03 F
7 | Final Cross Functional Alignment
7.1 | Ensure Objectives and Actions are Aligned | Leadership / RevOps | 2025-01-08 | 2025-01-12 | 4 | 0% | bar: 2025-01-06 M to 2025-01-06 F
7.2 | Ensure Resources are aligned - within expected SPOC Metric | Cfx Team / RevOps | 2025-01-08 | 2025-01-12 | 4 | 0% | bar: 2025-01-06 M to 2025-01-06 F
8 | Roll Out
8.1 | Design framework for Roll Out to Teams (Sales, Marketing, CS, SE, SDR, etc.) | RevOps/Leadership | 2025-01-15 | 2025-01-27 | 12 | 0% | bar: 2025-01-13 M to 2025-01-20 F
8.2 | Roll out Comp Plan in Smaller Groups (ideally 5-10 for questions) | RevOps/Sales Leadership | 2025-02-12 | 2025-02-16 | 4 | 0% | bar: 2025-02-10 M to 2025-02-10 F
8.3 | Roll Out Territories & Quotas To Teams | Sales Managers | 2025-02-12 | 2025-02-16 | 4 | 0% | bar: 2025-02-10 M to 2025-02-10 F
8.4 | Leverage Sales Kick Off for Strategic Alignment & Key Details | CRO/RevOps | 2025-02-19 | 2025-02-23 | 4 | 0% | bar: 2025-02-17 M to 2025-02-17 F