## Instructions
Developed by Maria Pergolino.
Instructions
Each tab features a brief description of how it should be used.
The prepopulated activities, events, and KPIs throughout the document represent a typical launch process at a later-stage startup. Please adjust them to fit your needs and process.
Detailed directions on how to use this template can be found here.

## 1. Launch Scorecard
Instructions: This dashboard is meant to provide leaders with a real-time view of the status of launch activities, events, and KPIs. Typically, this dashboard would only be used for a major launch.
Launch Scorecard
Product category
Product / feature
Launch level
Report date
Launch date
Launch budget
Product owner
Marketing owner
Code name
Launch Activity |  | Status
Product Development | Roadmap
Beta customers
PRD (Product Requirements Document)
MRD (Market Requirements Document)
Production status
Operations | Pricing
FP&A model updates
Licensing agreements
GTM | Internal communications
Collateral (customer & partner)
Images / video
Promotions plan
Demand generation plan (ABM)
Service & support | Training
Service readiness
Customer service readiness
Education readiness
Post Launch | Post-launch summary
Key Event | Date | Status
Demo release
Available
Internal release
Partner release
External announcement
Launch review date
KPIs | Goal | To Date | Status
Comments

## 2. Launch Plan Prep
Instructions: Start here. Make sure these activities (including adapting the other tabs of this document to your needs) are completed before you kick off the launch process with your team.
Pre-Launch Plan Activity | Owner | Status
Define type of launch (bug fix, feature launch, product launch)
Define goals of launch
Produce PRD (Product Requirements Document)
Product MRD (Market Requirements Document)
Conduct market research and competitive analysis
Develop product positioning and messaging (including name and brand of product)
Develop GTM plan and team RASCI (see Tabs 3a & 3b)
Develop localization plan with marketing (see Tab 5)
Set tentative launch date and outline preliminary timeline for major deliverables
Share upcoming launch with organization and get buy in

## 3a. Launch Activities & RASCI
Instructions: Use this activity tracker to monitor the status or pre- and post-launch activities. The "Reqiured?" columns indicate which activities are required for which types of launches.
Notes: Please update these requirements, the RASCI, and the list of activities themselves to suit your needs.
Most companies use either the activity tracker layout on this tab or the timeline layout on tab 3b, but not both.
Phase | Activity | Required? |  |  | Owner | Due Date | Status | RASCI | [7 empty] | Comments
|  | Small (Bug Fix) | Medium (Feature Release) | Large (Product Release) |  |  |  | Product | Marketing | Operations | Service & Support | Sales & Channel | Legal | Finance | BU Leader / GM
Product & Engineering Team
Pre-launch | Completed release timeline plan | Yes | Yes | Yes
Pre-launch | Articulated datacenter approach / considerations |  | Maybe | Yes
Pre-launch | Built system to measure feature / functionality adoption | Maybe | Yes | Yes
Pre-launch | Drafted detailed release notes | Yes | Yes | Yes
Pre-launch | Provided training for technical teams (services, support, etc.) |  | Maybe | Yes
Pre-launch | Defined localization / applicable markets requirements | Maybe | Maybe | Yes
Pre-launch | Drafted in-product messaging |  | Yes | Yes
Pre-launch | Performed in-product tagging (Amplitude / Pendo) |  | Yes | Yes
Pre-launch | Created demo graphics |  | Maybe | Yes
Pre-launch | Created demo video |  | Maybe | Yes
Pre-launch | Created business case scorecards |  | Yes | Yes
Pre-launch | Managed beta program |  | Maybe | Maybe
Pre-launch | Determined first customer go-live date |  | Yes | Yes
Post launch | Ran post-launch customer survey |  | Yes | Yes
Post launch | Ran post-launch debrief |  | Yes | Yes
Post launch | Ran post-launch sales and service survey |  | Maybe | Yes
Post launch | Tracked product utilization and adoption report |  | Yes | Yes
Marketing Team
Marketing Strategy
Pre-launch | Drafted general messaging | Yes | Yes | Yes
Pre-launch | Identified target customer profiles |  | Yes | Yes
Pre-launch | Articulated competitive differentiation |  | Maybe | Yes
Pre-launch | Created objection handling plan |  | Maybe | Yes
Pre-launch | Defined channel strategy (who is selling what) |  | Maybe | Yes
Press & Analysts
Pre-launch | Sourced and polished customer quotes / validation | Maybe | Yes | Yes
Pre-launch | Created customer remediation plan | Yes | Yes | Yes
Pre-launch | Sourced internal quotes / spokespeople |  | Maybe | Yes
Pre-launch | Drafted analyst briefing plan |  | Quarterly | Yes
Pre-launch | Drafted analyst briefing deck |  | Maybe | Yes
Pre-launch | Created PR strategy |  | Maybe | Yes
Pre-launch | Created PR pitch plan |  | Maybe | Yes
Pre-launch | Created PR graphics and visuals |  | Maybe | Yes
Pre-launch | Approved press release | Maybe | Maybe | Yes
Pre-launch | Drafted social post(s) |  | Maybe | Yes
Marketing Collateral
Pre-launch | Created roadmap deck |  | Maybe | Yes
Pre-launch | Created "sneak peek" content | Maybe | Yes | Yes
Pre-launch | Created data sheet |  | Maybe | Yes
Pre-launch | Created features and benefits brochure |  | Maybe | Yes
Pre-launch | Provided thought leadership for demand gen / campaign use |  | Maybe | Yes
Pre-launch | Reviewed and approved site updates |  | Maybe | Yes
Pre-launch | Drafted localized content according to localization plan | Maybe | Yes | Yes
Website Updates
Pre-launch | Drafted updates to homepage |  |  | Yes
Pre-launch | Drafted updates to product pages |  | Yes | Yes
Pre-launch | Drafted updates to resource pages |  |  | Yes
Pre-launch | Drafted blog post | Maybe | Yes | Yes
Demand & Digital Marketing
Pre-launch | Created digital promotion and advertising plan |  | Maybe | Yes
Pre-launch | Drafted demand gen and ABM campaigns |  | Maybe | Yes
Pre-launch | Drafted campaigns for install base |  | Maybe | Yes
Pre-launch | Created events plan |  | Maybe | Yes
Pre-launch | Created organic social media plan |  | Maybe | Yes
Pre-launch | Created SEO/SEM strategy |  | Maybe | Yes
Post launch | Tracked demand gen and digital promotion results |  | Maybe | Yes
Partner Enablement Materials
Pre-launch | Created and provided pitch deck |  | Yes | Yes
Pre-launch | Provided demo data | Yes | Yes | Yes
Pre-launch | Provided demo video |  | Maybe | Yes
Pre-launch | Provided packaging & pricing |  | Maybe | Yes
Sales Enablement Materials
Pre-launch | Created and provided pitch deck |  | Yes | Yes
Pre-launch | Provided demo data | Yes | Yes | Yes
Pre-launch | Provided demo video |  | Maybe | Yes
Pre-launch | Created and provided packaging & pricing |  | Maybe | Yes
Sales & SE Team
Pre-launch | Trained on features / functionality | Maybe | Yes | Yes
Pre-launch | Trained on new deck and messaging |  |  | Yes
Pre-launch | Trained on technical release information (SEs only) | Maybe | Yes | Yes
Pre-launch | Updated quoting and invoicing process |  | Maybe | Yes
Pre-launch | Prepared demo data |  | Maybe | Yes
Pre-launch | Launched sales promos / SPIFFs |  | Maybe | Yes
Services, Support, & Customer Success
External & Customer Comms
Pre-launch | Drafted partner communications | Maybe | Yes | Yes
Pre-launch | Drafted customer communications |  | Yes | Yes
Pre-launch | Reached out proactively to select customers | Maybe | Yes | Yes
Pre-launch | Drafted user group / community posts | Yes | Yes | Yes
Support, Services, & Training
Pre-launch | Trained on features / functionality | Yes | Yes | Yes
Pre-launch | Updated service packages |  |  | Yes
Pre-launch | Updated training materials / offerings |  | Maybe | Yes
Pre-launch | Updated customer education programs and certifications |  | Maybe | Yes
Pre-launch | Updated support routing / operations |  |  | Yes
G&A & Other
Pre-launch | Legal: Updated licensing agreements |  | Maybe | Yes
Pre-launch | FP&A: Added new SKU, performed QTC updates |  | Maybe | Yes
Pre-launch | FP&A: Updated revenue model |  | Maybe | Yes
Pre-launch | Operations: Performed trademark review |  | Maybe | Yes
Post launch | Operations: Built quality / warranty tracking infrastructure |  | Maybe | Yes
Post launch | Operations: Created pricing strategy |  | Yes | Yes

## 3b. Launch Timeline & RASCI
Instructions: Use this timeline and RASCI to monitor the steps to preparing a launch and tracking the results afterward.
Notes: Please update the RASCI and the list of steps to suit your needs.
Most companies use either the activity tracker layout on tab 3a or this timeline layout, but not both.
Phase | Category | Step | Team | Owner | Due Date | Status | RASCI
[7 empty] | Product | Marketing | Operations | Service & Support | Sales & Channel | Legal | Finance | BU Leader / GM
Pre-launch | Planning | Launch Meetings Begin | Marketing |  |  |  | S | R/A | S |  |  | I | I | I
Pre-launch | Planning | Message Map (Global) | Marketing |  |  |  | S | R/A | I |  |  |  |  | C
Pre-launch | Planning | Launch Strategy/Plan Completion | Product |  |  |  | R/A | S | S |  |  |  |  | C
Pre-launch | Planning | Business Case Scorecards and Metrics | Product |  |  |  | R/A | I | I |  |  |  |  | C
Pre-launch | Planning | Channel Strategy (Who is selling what?) | Product |  |  |  | R/A | S | I |  |  |  |  | C
Pre-launch | Planning | Launch Leveling | Product |  |  |  | R/A | C | I |  |  |  |  | C
Pre-launch | Planning | Market Requirements Document | Product |  |  |  | R/A | C | I |  |  |  |  | C
Pre-launch | Planning | Product Requirements Document | Product |  |  |  | R/A | C | S |  |  |  |  | C
Pre-launch | Planning | Target Customers Strategy | Product |  |  |  | R/A | C | S |  |  |  |  | C
Pre-launch | Planning | Competitive Comparison | Product |  |  |  | R/A | C | I |  |  |  |  | C
Pre-launch | Stage Gate | Launch Strategy Stage Gate Meeting | Product |  |  |  | R/A | I | I | I | I | I | I | I
Pre-launch | Collateral | Collateral Plan & Creation | Marketing |  |  |  | S | R/A | I |  |  |  |  | C
Pre-launch | Collateral | Thought Leadership: E-books, ROI Calculator, etc. | Marketing |  |  |  | S | R/A | [5 empty] | C
Pre-launch | Collateral | Localization Plan & Creation (see tab 5) | Marketing |  |  |  | S | R/A | S |  | C | I | I | C
Pre-launch | Collateral | Demo Plan & Creation | Marketing |  |  |  | S | R/A | S |  | C |  |  | C
Pre-launch | Collateral | New Trademark Review | Product |  |  |  | R/A | S | I |  |  |  |  | C
Pre-launch | Demand Gen | Advertising/PR Plan Aligned | Marketing |  |  |  | S | R/A | I |  | C |  |  | C
Pre-launch | Demand Gen | Marketing Campaigns Planned (DG, Digital, PR, etc.) | Marketing |  |  |  | S | R/A | I |  | C |  |  | C
Pre-launch | Demand Gen | Press Release Drafted & Approved | Marketing |  |  |  | S | R/A | I | I | C | I | I | D
Pre-launch | Enablement | Sales/Channel/Customer Promotion Plan Aligned | Marketing |  |  |  | S | R/A | S | C | C |  |  | C
Pre-launch | Enablement | Internal Communications Plan Complete (see tab 4) | Marketing |  |  |  | S | R/A | S | C | I |  |  | C
Pre-launch | Enablement | Customer Service Communications Plan and Execution | Marketing |  |  |  | S | R/A | S | C | I |  |  | C
Pre-launch | Enablement | Field Sales Communications Plan and Execution | Marketing |  |  |  | S | R/A | S | I | C |  |  | C
Pre-launch | Enablement | Partner & Channel Communications Plan and Execution | Marketing |  |  |  | S | R/A | S | C | C |  |  | C
Pre-launch | Enablement | Pricing Strategy, Quote Templates, etc. | Operations |  |  |  | S | S | R/A |  | I | C | C | C
Pre-launch | Images/Video | Product Shot Plan & Creation | Marketing |  |  |  | S: R/A; R/A: S; I: R/A; D: C
Pre-launch | Images/Video | Demo Scripts/Video Complete | Product |  |  |  | S: R/A; R/A: S; I: S; D: C
Pre-launch | Planning | BU Specific Metrics and Tracking Plan | Operations |  |  |  | S | S | R/A |  | I |  |  | C
Pre-launch | Planning | Post Launch Feedback/Intelligence Plan | Product |  |  |  | R/A | S | I |  | C |  |  | C
Pre-launch | Stage Gate | Launch Readiness Stage Gate Meeting | Product |  |  |  | R/A | I | I | I | I | I | I | I
Launch | Stage Gate | LAUNCH | Product |  |  |  | R/A | I | I | I | I | I | I | I
Post launch | Analytics | Demand Gen & Digital Results Tracking | Marketing |  |  |  | S | R/A | S |  | I |  |  | I
Post launch | Analytics | Quality/Warranty Tracking | Product |  |  |  | S: I; I: R/A; D: C
Post launch | Analytics | Post Launch Customer Survey | Product |  |  |  | S: R/A; R/A: S; I: I; D: C
Post launch | Analytics | Post Launch Debrief/Review | Product |  |  |  | R/A | S | I | C | C | C | C | C
Post launch | Analytics | Post Launch Field Sales & Service Survey | Product |  |  |  | R/A | S | I | C | C |  |  | C
Post launch | Analytics | Product Utilization/Adoption | Product |  |  |  | R/A | I | I |  |  | I | I | C
Post launch | Demand Gen | ABM & Demand Generation Campaigns | Marketing |  |  |  | S | R/A | S |  | I |  |  | I
Post launch | Demand Gen | Digital Marketing & SEO/SEM | Marketing |  |  |  | S | R/A | S |  | I |  |  | I
Post launch | Demand Gen | Install Base Campaign | Marketing |  |  |  | S | R/A | S |  | I |  |  | I
Post launch | Demand Gen | Major Trade Events | Marketing |  |  |  | S | R/A | I |  | I |  |  | I
Post launch | Demand Gen | PR/Earned Media Campaign | Marketing |  |  |  | S | R/A | I |  | I |  |  | I
Post launch | Demand Gen | Social Media Posts (Organic) | Marketing |  |  |  | S | R/A | I |  | I |  |  | I
Post launch | Demand Gen | Social Media Posts (Paid) | Marketing |  |  |  | S | R/A | I |  | I |  |  | I
Post launch | Key Date | First Customer Go Live Date | Operations |  |  |  | I | I | R/A | I | I | I | I | I
Post launch | Key Date | First Order Date | Operations |  |  |  | I | I | R/A | I | I | I | I | I
Post launch | Milestone | Post Launch | Product |  |  |  | R/A | I | I | I | I | I | I | I

## 4. Internal Communications Plan
Instructions: Use this tab to create your internal communications plan, including the audiences for each (see the rightmost columns). Then, use it to track your progress.
Communication | Owner | Days from Launch | Target Date | Type | Status | Audiences
[6 empty] | Company wide | Customer service | Sales | Channel & distributors
Channel and distributor FAQs |  |  |  | Web page |  |  |  |  | Yes
Customer service FAQs |  |  |  | Web page |  |  | Yes
Sales FAQs |  |  |  | Web page |  |  |  | Yes
Internal wiki posting |  |  |  | Web page |  | Yes
Channel & distributor monthly newsletter |  |  |  | Email |  |  |  |  | Yes
Company monthly newsletter |  |  |  | Email |  | Yes
Channel & distributor office hours |  |  |  | Webinar |  |  |  |  | Yes
Customer service office hours |  |  |  | Webinar |  |  | Yes
Sales office hours |  |  |  | Webinar |  |  |  | Yes
Posters / digital signage in facilities |  |  |  | NA |  | Yes
Promo / SPIFF announcement |  |  |  | NA |  |  | If relevant | If relevant | If relevant
Quarterly channel session |  |  |  | Webinar |  |  |  |  | Yes
Quarterly employee update meetings |  |  |  | Webinar |  | Yes
Quarterly product announcement |  |  |  | Webinar |  | Yes
Roadshow |  |  |  | Event |  | If relevant | If relevant | If relevant | If relevant
Channel & distributor training session |  |  |  | Webinar |  |  |  |  | Yes
Customer service training session |  |  |  | Webinar |  |  | Yes
Sales training session |  |  |  | Webinar |  |  |  | Yes
Win stories bulletin |  |  |  | Web page |  | Yes |  |  | Yes

## 5. Localization Plan
Instructions: Determine which languages you'll need to support for this launch.
Region | Language | Needed for this launch?
Americas | English (US)
French (Canada)
Spanish (Latin America)
Portuguese (Brazil)
APAC (Asia-Pacific) | Chinese (Simplified: Mainland China)
Chinese (Traditional: Hong Kong/Taiwan)
Korean
English (Asia e.g., Singapore, Philippines)
English (Australia/New Zealand)
EMEA (Europe, Middle East, and Africa) | English (UK)
Dutch (Netherlands, Belgium)
French (France, Belgium, Switzerland)
German (Germany, Austria, Switzerland)
Italian
Portuguese (Portugal)
Spanish (Spain)
Arabic (Middle East & North Africa)
Turkish
Russian