## How to use
Gather
Construction S-Curve Template
A practical QS-ready template for planned value, actual cost, earned value and forecast outturn.
How to use this template
| Step | Task | What to do
| 1 | Set the job basics | Open the S-Curve Calculator tab and enter the Budget at Completion, number of periods, period type and data date in the pale-yellow cells.
| 2 | Enter your baseline | Fill Planned % complete cumulative by period. Use the ideal curve helper if you need a starter baseline, then refine it to match your programme.
| 3 | Add actuals | Enter cumulative Actual Cost and cumulative Actual % complete from your cost records and site progress records.
| 4 | Read the curves | The chart compares Planned Value, Actual Cost and Earned Value. Negative CV/SV and CPI/SPI below 1 are highlighted automatically.
| 5 | Use the forecast | The summary block uses the data date row to calculate EAC, ETC, VAC and TCPI. It is a guide, not a substitute for commercial judgement. Sadly, Excel still does not attend site meetings.
Free template by Gather — gatherinsights.com
Want these three curves drawn automatically from your site diaries and cost data? → Book a demo

## S-Curve Calculator
Gather
S-Curve Calculator
Blank calculator — enter only the pale-yellow cells.
Inputs |  |  | Forecast summary at data date | [8 empty] | Ideal planned curve helper
Budget at Completion (BAC) — £ | 0 |  | CPI at data date | [8 empty] | Formula used: y = 1 − (1 − x^r)^b. Copy Ideal % into column C to start, then refine.
Number of periods (N) | 12 |  | AC at data date | 0 | [7 empty] | Period # | x | Ideal % | Marker X | Marker Y | Data date marker
Period type | Month |  | EV at data date | [8 empty] | 1 | 0.083333 | 0.51963 | 1 | 0
Data date (period #) | 1 |  | EAC — what the job will cost if today's efficiency holds | [8 empty] | 2 | 0.16667 | 4.0903 | 1 | 0
Curve shape r | 3 |  | ETC — what is left to spend from today | [8 empty] | 3 | 0.25 | 13.2149
Curve shape b | 9 |  | VAC — forecast over/under against budget | [8 empty] | 4 | 0.33333 | 28.799
|  |  | TCPI — efficiency needed to hit BAC | [8 empty] | 5 | 0.41667 | 49.1246
[12 empty] | 6 | 0.5 | 69.9342
[12 empty] | 7 | 0.58333 | 86.3493
Period # | Period label / date | Planned % complete (cum.) | Planned Value — PV (cum. £) | Actual Cost — AC (cum. £) | Actual % complete (cum.) | Earned Value — EV (cum. £) | Cost Variance — CV (£) | Schedule Variance — SV (£) | CPI | SPI | Notes | 8 | 0.66667 | 95.7684 |  |  | Data date
1 | [11 empty] | 9 | 0.75 | 99.2786 |  |  | 0
2 | [11 empty] | 10 | 0.83333 | 99.9582
3 | [11 empty] | 11 | 0.91667 | 99.9998
4 | [11 empty] | 12 | 1 | 100
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27 | [11 empty] | Free template by Gather — gatherinsights.com ¦ Want these curves drawn automatically from your site diaries and cost data? → Book a demo
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Note on B7: Enter the approved Budget at Completion for the project or package.
Note on C16: Enter cumulative planned percent complete as 0-100. The final active period should reach 100.
Note on E7: Cost efficiency index used for the forecast.
Note on E8: Actual cumulative cost at the data date.
Note on E9: Earned value at the data date.
Note on E10: Estimate at Completion = BAC / CPI.
Note on E11: Estimate to Complete = EAC - AC.
Note on E12: Variance at Completion = BAC - EAC.
Note on E13: To-Complete Performance Index = (BAC - EV) / (BAC - AC).
Note on E16: Enter cumulative actual cost from cost records.
Note on F16: Enter cumulative actual percent complete from site progress records.

## Worked Example
Gather
Worked Example
12-month / £2.4M construction example with live formulas and forecast.
Inputs |  |  | Forecast summary at data date | [8 empty] | Ideal planned curve helper
Budget at Completion (BAC) — £ | 2400000 |  | CPI at data date | 0.95909 | [7 empty] | Formula used: y = 1 − (1 − x^r)^b. Copy Ideal % into column C to start, then refine.
Number of periods (N) | 12 |  | AC at data date | 2200000 | [7 empty] | Period # | x | Ideal % | Marker X | Marker Y | Data date marker
Period type | Month |  | EV at data date | 2110000 | [7 empty] | 1 | 0.083333 | 0.51963 | 9 | 0
Data date (period #) | 9 |  | EAC — what the job will cost if today's efficiency holds | 2502369.6682 | [7 empty] | 2 | 0.16667 | 4.0903 | 9 | 2667600
Curve shape r | 3 |  | ETC — what is left to spend from today | 302369.6682 | [7 empty] | 3 | 0.25 | 13.2149
Curve shape b | 9 |  | VAC — forecast over/under against budget | -102369.6682 | [7 empty] | 4 | 0.33333 | 28.799
|  |  | TCPI — efficiency needed to hit BAC | 1.45 | [7 empty] | 5 | 0.41667 | 49.1246
[12 empty] | 6 | 0.5 | 69.9342
[12 empty] | 7 | 0.58333 | 86.3493
Period # | Period label / date | Planned % complete (cum.) | Planned Value — PV (cum. £) | Actual Cost — AC (cum. £) | Actual % complete (cum.) | Earned Value — EV (cum. £) | Cost Variance — CV (£) | Schedule Variance — SV (£) | CPI | SPI | Notes | 8 | 0.66667 | 95.7684 |  |  | Data date
1 | M1 | 2 | 48000 | 52000 | 1.6667 | 40000 | -12000 | -8000 | 0.76923 | 0.83333 | Mobilisation | 9 | 0.75 | 99.2786
2 | M2 | 6 | 144000 | 150000 | 5.4167 | 130000 | -20000 | -14000 | 0.86667 | 0.90278 |  | 10 | 0.83333 | 99.9582
3 | M3 | 13 | 312000 | 330000 | 12.5 | 300000 | -30000 | -12000 | 0.90909 | 0.96154 | Groundworks | 11 | 0.91667 | 99.9998
4 | M4 | 24 | 576000 | 600000 | 23.3333 | 560000 | -40000 | -16000 | 0.93333 | 0.97222 |  | 12 | 1 | 100
5 | M5 | 38 | 912000 | 948000 | 37.0833 | 890000 | -58000 | -22000 | 0.93882 | 0.97588 | Peak begins
6 | M6 | 54 | 1296000 | 1340000 | 52.9167 | 1270000 | -70000 | -26000 | 0.94776 | 0.97994
7 | M7 | 68 | 1632000 | 1690000 | 66.6667 | 1600000 | -90000 | -32000 | 0.94675 | 0.98039 | Peak
8 | M8 | 80 | 1920000 | 1985000 | 78.75 | 1890000 | -95000 | -30000 | 0.95214 | 0.98438
9 | M9 | 89 | 2136000 | 2200000 | 87.9167 | 2110000 | -90000 | -26000 | 0.95909 | 0.98783 | Fit-out | [5 empty] | 2593500
10 | M10 | 95 | 2280000 | 2350000 | 94.1667 | 2260000 | -90000 | -20000 | 0.9617 | 0.99123
11 | M11 | 98 | 2352000 | 2420000 | 97.2917 | 2335000 | -85000 | -17000 | 0.96488 | 0.99277
12 | M12 | 100 | 2400000 | 2470000 | 99.5833 | 2390000 | -80000 | -10000 | 0.96761 | 0.99583 | Practical completion
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27 | [11 empty] | Free template by Gather — gatherinsights.com ¦ Want these curves drawn automatically from your site diaries and cost data? → Book a demo
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Note on B7: Enter the approved Budget at Completion for the project or package.
Note on C16: Enter cumulative planned percent complete as 0-100. The final active period should reach 100.
Note on E7: Cost efficiency index used for the forecast.
Note on E8: Actual cumulative cost at the data date.
Note on E9: Earned value at the data date.
Note on E10: Estimate at Completion = BAC / CPI.
Note on E11: Estimate to Complete = EAC - AC.
Note on E12: Variance at Completion = BAC - EAC.
Note on E13: To-Complete Performance Index = (BAC - EV) / (BAC - AC).
Note on E16: Enter cumulative actual cost from cost records.
Note on F16: Enter cumulative actual percent complete from site progress records.