## How to use
Gather
Site Diary & Allocation Sheet Template
Daily records plus resource allocation tracking for construction teams
What this workbook is for
Use this workbook to capture a clean daily site record and link labour, plant, materials, subcontract and other allocations to dates, work packages and cost codes. It is deliberately formula-only: no macros, no VBA, no dark magic in a hard hat.
How to use it
| 1 | Fill the yellow cells only. Formula cells are grey and protected so the workbook is harder to break.
| 2 | Use Site Diary for the daily record: weather, labour, plant, deliveries, progress, safety, quality, instructions and sign-off.
| 3 | Use Allocation Sheet for cost coding: each row is one resource allocation against a date, work package and cost code.
| 4 | Use the live totals at the top of Allocation Sheet to review labour hours, costs, recoverable value and queried items.
| 5 | Duplicate the Site Diary tab for each day if you want a printable day-by-day record. Keep Allocation Sheet as the running log.
Legend
| Yellow fill | User input
| Grey fill | Formula / protected
| Orange fill | Review / caution
| Green fill | Approved / positive
Free template by Gather — gatherinsights.com
Want site diaries, allocations and cost records captured automatically from your teams? → Book a demo
Tip: keep one master blank copy of this workbook, then save a project copy before you start entering live data.

## Site Diary
Gather
Site Diary Template
Daily record for labour, plant, deliveries, progress, events and sign-off
Project & Day Details
Project name |  |  |  | Project no. |  |  | Diary date |  | Prepared by
Site location |  |  |  | Contractor |  |  | Day no. |  | Shift
Weather AM |  |  |  | Weather PM |  |  | Temp °C |  | Site open?
Working hours |  |  |  | Ground conditions |  |  | Delay impact? |  | RAG
Overall progress % |  |  |  | Progress narrative
Labour on Site
Company / crew | Trade | Direct / sub | Operatives | Hours each | Total hours | Work area | Main activity | Notes
Total labour hours |  |  |  |  | 0 | This should reconcile to the Allocation Sheet labour hours.
Plant & Equipment
Plant / equipment | Owner / hirer | Quantity | Hours used | Idle hours | Status | Off-hire? | Work area | Notes
Total plant hours |  |  | 0 | 0 | Track idle time separately: it is often where the argument starts.
Materials & Deliveries
Supplier | Material | Delivery note ref | Quantity | Unit | Accepted? | Location | Received by | Notes
Work Completed / Progress
Work package | Location | Activity completed | Planned? | % complete | Constraint / cause | Photos / evidence ref | Responsible | Notes
Safety / Quality / Commercial Events
Type | Time | Description | Raised by | Action owner | Due date | Status | Potential cost/time impact | Notes
Instructions / RFIs / Changes
Ref | Type | Summary | Issued by | Received by | Status | Cost code / WP | Action / next step | Notes
Sign-off
Prepared by |  |  | Position |  |  | Signature |  |  | Date
Reviewed by |  |  | Position |  |  | Signature |  |  | Date
Free template by Gather — gatherinsights.com ¦ Want this captured automatically from site teams? Book a demo: gatherinsights.com/en/book-a-demo

## Allocation Sheet
Gather
Allocation Sheet Template
Labour, plant, material and subcontract allocation log with live totals
Project Setup
Project name |  |  |  | Project no. |  |  | Reporting period |  |  | Currency | £ | Default labour rate £/h | 45 | Default OT multiplier | 1.5 | Default plant rate £/h | 0 | Prepared by
Notes | Enter one resource allocation per row. Labour uses normal/overtime hours x rate. Plant, materials, subcontract and other costs use quantity x rate. Use status to separate draft, approved and queried costs.
Live Totals
Total labour hours | 0 | Labour cost £ | 0 | Plant cost £ | 0 | Materials cost £ | 0 | Subcontract cost £ | 0 | Other cost £ | 0 | Total allocated £ | 0 | Recoverable £ | 0 | Approved £ | 0 | Queried / draft £ | 0 | Row count | 0
Date | Diary Ref | Cost Code | Work Package / Activity | Location | Resource Type | Company / Supplier | Resource / Name / Item | Role / Category | Quantity | Unit | Normal Hrs | Overtime Hrs | Rate £/unit | OT Multiplier | Labour Cost £ | Other Cost £ | Total Cost £ | Billable? | Recoverable £ | Status | Notes
Free template by Gather — gatherinsights.com ¦ Want diaries, allocations and cost records linked automatically? Book a demo: gatherinsights.com/en/book-a-demo
Note on P15: For Labour rows: normal hours x rate plus overtime hours x rate x OT multiplier. Uses the default labour rate if the row rate is blank.
Note on Q15: For Plant, Materials, Subcontract and Other rows: quantity x rate.
Note on R15: Total of labour and other cost for the row.
Note on T15: Recoverable amount if Billable? is Y.

## Worked Example
Gather
Worked Example — Allocation Sheet
Labour, plant, material and subcontract allocation log with live totals
Project Setup
Project name | Gather House Refurbishment |  |  | Project no. | GHR-024 |  | Reporting period | Jul 2026 |  | Currency | £ | Default labour rate £/h | 47.5 | Default OT multiplier | 1.5 | Default plant rate £/h | 85 | Prepared by | Site Manager
Notes | Example entries only. Delete this tab or copy it when you want a quick test set.
Live Totals
Total labour hours | 118 | Labour cost £ | 6027 | Plant cost £ | 736 | Materials cost £ | 2664 | Subcontract cost £ | 650 | Other cost £ | 280 | Total allocated £ | 10357 | Recoverable £ | 10077 | Approved £ | 6763 | Queried / draft £ | 1118 | Row count | 8
Date | Diary Ref | Cost Code | Work Package / Activity | Location | Resource Type | Company / Supplier | Resource / Name / Item | Role / Category | Quantity | Unit | Normal Hrs | Overtime Hrs | Rate £/unit | OT Multiplier | Labour Cost £ | Other Cost £ | Total Cost £ | Billable? | Recoverable £ | Status | Notes
2026-07-01 | SD-001 | 1000-LAB | Groundworks | Plot A | Labour | Direct | Operative team A | Groundworker |  | hrs | 40 | 4 | 47.5 | 1.5 | 2185 | 0 | 2185 | Y | 2185 | Approved | Trench excavation and blinding.
2026-07-01 | SD-001 | 2000-PLT | Groundworks | Plot A | Plant | HireCo | 13t excavator | Excavator | 8 | hrs |  |  | 92 |  | 0 | 736 | 736 | Y | 736 | Approved | Includes operator by hire agreement.
2026-07-02 | SD-002 | 3000-MAT | Concrete | Plot A | Materials | ReadyMix Ltd | C30 concrete | Concrete | 18 | m3 |  |  | 122 |  | 0 | 2196 | 2196 | Y | 2196 | Submitted | Pour ticket attached.
2026-07-03 | SD-003 | 1000-LAB | Drainage | Plot B | Labour | Direct | Operative team B | Groundworker |  | hrs | 36 | 0 | 47.5 | 1.5 | 1710 | 0 | 1710 | Y | 1710 | Approved | Drain run installed.
2026-07-03 | SD-003 | 4000-SUB | Scaffolding | Front elevation | Subcontract | SafeScaf | Scaffold adjustment | Scaffold | 1 | each |  |  | 650 |  | 0 | 650 | 650 | Y | 650 | Queried | Awaiting variation confirmation.
2026-07-04 | SD-004 | 3000-MAT | Drainage | Plot B | Materials | BuildMerchant | 110mm drainage pipe | Pipework | 48 | m |  |  | 9.75 |  | 0 | 468 | 468 | Y | 468 | Draft | Check wastage allowance.
2026-07-05 | SD-005 | 5000-OTH | General | Site-wide | Other | WasteCo | Mixed waste skip | Waste | 1 | load |  |  | 280 |  | 0 | 280 | 280 | N | 0 | Submitted | Non-recoverable internal allowance.
2026-07-06 | SD-006 | 1000-LAB | Fit-out | Level 1 | Labour | Direct | Carpentry team | Carpenter |  | hrs | 32 | 6 | 52 | 1.5 | 2132 | 0 | 2132 | Y | 2132 | Approved | First fix framing.
Free template by Gather — gatherinsights.com ¦ Want diaries, allocations and cost records linked automatically? Book a demo: gatherinsights.com/en/book-a-demo
Note on P15: For Labour rows: normal hours x rate plus overtime hours x rate x OT multiplier. Uses the default labour rate if the row rate is blank.
Note on Q15: For Plant, Materials, Subcontract and Other rows: quantity x rate.
Note on R15: Total of labour and other cost for the row.
Note on T15: Recoverable amount if Billable? is Y.