## How to use
Gather ¦ NEC Compensation Event Log Template
Track compensation events from notification to assessment, with ageing, value, time impact and evidence readiness.
What this template is for
| 1. Log every compensation event early |  | Capture the trigger, notification date, owner and status before it disappears into email fog.
| 2. Keep quotations and assessments visible |  | Track submitted value, accepted value, time impact and whether the quotation is due or overdue.
| 3. Keep evidence claim-ready |  | Link each event to diary entries, instructions, photos, drawings, weather records, programmes and cost records.
| 4. Use the dashboard in weekly commercial reviews |  | The dashboard rolls up open events, overdue actions, disputed value and time impact automatically.
Colour key
| Yellow fill | User input cells
| Grey fill | Formula / calculated cells
| Red flag | Overdue, rejected or negative variance
| Green flag | Accepted, submitted or resolved
Gather CTA
Free template by Gather — gatherinsights.com. Want site diaries, evidence and commercial records connected automatically? Book a demo: https://www.gatherinsights.com/en/book-a-demo

## Dashboard
Gather ¦ Compensation Event Dashboard
Live summary from the CE Log sheet. Use this in weekly commercial reviews.
Project snapshot |  |  |  | Key metrics
Project | 0 |  |  | Total CEs | 0 |  | Accepted value | 0
Contract | NEC4 ECC |  |  | Open / active | 0 |  | Disputed / unagreed value | 0
Data Date | 0 |  |  | Overdue actions | 0 |  | Net value variance | 0
Commercial Period | 0 |  |  | High/Critical risk | 0 |  | Total time impact days | 0
|  |  |  | Submitted value | 0
Status summary |  |  |  | Risk summary
Status | Count | Submitted £ | Accepted £ | Risk | Count | Open value £
New | 0 | 0 | 0 | Low | 0 | 0
Notified | 0 | 0 | 0 | Medium | 0 | 0
Quotation due | 0 | 0 | 0 | High | 0 | 0
Submitted | 0 | 0 | 0 | Critical | 0 | 0
Assessed | 0 | 0 | 0
Accepted | 0 | 0 | 0
Rejected | 0 | 0 | 0
Disputed | 0 | 0 | 0
Closed | 0 | 0 | 0

## CE Log
Gather ¦ NEC Compensation Event Log
Blank log: enter events, due dates, values and evidence. Formula cells are protected; input cells are yellow.
Project details
Project |  |  | Reviewed by
Contract | NEC4 ECC |  | Commercial period
Client |  |  | Notes
CE Ref | Package / Area | Trigger Date | Notification Date | Event Source | Clause / Reason | Short Description | Owner | Status | Quote Due Date | Assessment Due Date | Days Open | Days to Quote Due | Submitted? | Submitted Value (£) | Accepted Value (£) | Variance (£) | Time Impact (days) | Programme Impact | Evidence Status | Evidence Link / Ref | Linked Diary Ref | Risk Rating | Next Action | Action Owner | Action Due | Action Overdue? | Notes
Note on B6: Change contract type as required. Default shown for NEC-friendly use.
Note on F8: Use your project contract and internal process. This template is a practical tracker, not legal advice.

## Worked Example
Gather ¦ NEC Compensation Event Log — Worked Example
Example data shows open, disputed and accepted events so the dashboard and flags have something to chew on.
Project details
Project | Riverside Apartments Phase 2 |  | Reviewed by | Commercial Manager
Contract | NEC4 ECC Option C |  | Commercial period | July 2026
Client | 2026-07-23 |  | Notes | Example only — replace with your project details.
CE Ref | Package / Area | Trigger Date | Notification Date | Event Source | Clause / Reason | Short Description | Owner | Status | Quote Due Date | Assessment Due Date | Days Open | Days to Quote Due | Submitted? | Submitted Value (£) | Accepted Value (£) | Variance (£) | Time Impact (days) | Programme Impact | Evidence Status | Evidence Link / Ref | Linked Diary Ref | Risk Rating | Next Action | Action Owner | Action Due | Action Overdue? | Notes
CE-001 | Groundworks | 2026-05-03 | 2026-05-04 | Site condition | Unexpected obstruction | Concrete obstruction found during reduced level dig | J. Patel | Accepted | 2026-05-18 | 2026-05-25 | 80 | -66 | Yes | 18500 | 17200 | -1300 | 3 | Minor delay absorbed by resequence | Submitted | Diary 2026-05-03 / Photos GW-14 | SD-042 | Low | File final assessment | J. Patel | 2026-07-26 |  | Accepted below submitted value.
CE-002 | Envelope | 2026-05-21 | 2026-05-22 | Design change | Drawing revision | Curtain wall bracket redesign | A. Morgan | Submitted | 2026-06-05 | 2026-06-12 | 62 | -48 | Yes | 64200 | 0 | -64200 | 8 | Potential critical path impact | Partial | RFI-118 / Rev C drawings | SD-057 | High | Chase PM assessment | A. Morgan | 2026-07-20 | Overdue | Assessment overdue.
CE-003 | M&E | 2026-06-02 | 2026-06-03 | Client change | Additional scope | Extra containment to retail unit | S. Ahmed | Quotation due | 2026-07-29 | 2026-08-05 | 50 | 6 | No | 0 | 0 | 0 | 0 | No programme impact expected | Partial | Instruction PMI-027 | SD-068 | Medium | Prepare quotation | S. Ahmed | 2026-07-28 |  | Need subcontractor quote.
CE-004 | External works | 2026-06-10 | 2026-06-11 | Weather | Exceptional weather | Flooding affected drainage trench works | L. Evans | Disputed | 2026-06-25 | 2026-07-02 | 42 | -28 | Yes | 32800 | 0 | -32800 | 5 | Float nearly exhausted | Ready | Weather log / photos EXT-22 | SD-075 | High | Agree entitlement position | L. Evans | 2026-07-24 |  | PM queried weather threshold.
CE-005 | Fit-out | 2026-06-15 | 2026-06-16 | Access | Late access | Level 4 access delayed by preceding trade | M. Brown | Notified | 2026-07-01 | 2026-07-08 | 37 | -22 | No | 0 | 0 | 0 | 4 | May affect handover sequence | Missing | Diary only | SD-081 | Critical | Collect photos and programme extract | M. Brown | 2026-07-19 | Overdue | Evidence gap.
CE-006 | Substructure | 2026-06-29 | 2026-06-30 | Instruction | PM instruction | Additional waterproofing detail | J. Patel | Assessed | 2026-07-14 | 2026-07-21 | 23 | -9 | Yes | 22100 | 19800 | -2300 | 2 | No critical path impact | Submitted | PMI-034 / Waterproofing quote | SD-090 | Medium | Review assessment | J. Patel | 2026-07-25 |  | Commercial review required.
CE-007 | Roofing | 2026-07-05 | 2026-07-06 | Design change | Specification change | Roof insulation upgraded | A. Morgan | New | 2026-07-31 | 2026-08-07 | 17 | 8 | No | 0 | 0 | 0 | 1 | Possible procurement lead-time risk | Partial | Drawing A-602 Rev D | SD-096 | Medium | Confirm subcontractor cost | A. Morgan | 2026-07-30
CE-008 | M&E | 2026-07-08 | 2026-07-09 | Other | Coordination issue | Reroute ductwork around steel clash | S. Ahmed | Rejected | 2026-07-23 | 2026-07-30 | 14 | 0 | Yes | 14750 | 0 | -14750 | 2 | Potential night shift recovery | Ready | BIM clash report / photos | SD-101 | High | Prepare dispute note | S. Ahmed | 2026-07-27 |  | Rejected as contractor risk.
CE-009 | Finishes | 2026-07-13 | 2026-07-13 | Client change | Finish sample change | Lobby floor finish changed | M. Brown | Quotation due | 2026-08-03 | 2026-08-10 | 10 | 11 | No | 0 | 0 | 0 | 0 | No current programme impact | Partial | Client email / sample board | SD-106 | Low | Price variation | M. Brown | 2026-08-01
CE-010 | General | 2026-07-18 | 2026-07-18 | Programme change | Acceleration request | Request to recover two weeks | L. Evans | Submitted | 2026-08-01 | 2026-08-08 | 5 | 9 | Yes | 86000 | 0 | -86000 | -10 | Acceleration proposed | Ready | Programme rev P07 / labour plan | SD-112 | Critical | Review acceleration quotation | L. Evans | 2026-07-29 |  | High commercial exposure.
Note on B6: Change contract type as required. Default shown for NEC-friendly use.
Note on F8: Use your project contract and internal process. This template is a practical tracker, not legal advice.

## Guidance
Gather ¦ Guidance & Interpretation
Plain-English guide for using the log in commercial and project reviews.
How to read the log
Days Open | Counts from notification date to the data date. Long-running open items are commercial drag. Chase them.
Days to Quote Due | Negative means the quote due date has passed. Red cells are not decorative; they are a cry for help.
Submitted Value | The amount submitted in the quotation or assessment.
Accepted Value | The agreed/assessed value. Difference to submitted value is shown as variance.
Evidence Status | Use Missing / Partial / Ready / Submitted to avoid discovering gaps only when the claim matters.
Linked Diary Ref | Tie every event to site records, photos, instructions, weather, programme snapshots and labour/plant allocation records.
Action Overdue? | Driven by Action Due and status. Accepted and Closed events are excluded.
Suggested weekly review rhythm
1. Sort by Action Overdue? and Days to Quote Due.
2. Review High/Critical events before the nice, easy stuff.
3. Check every Submitted, Disputed and Rejected item has evidence linked.
4. Update accepted value and time impact after each assessment.
5. Use the dashboard chart in the commercial meeting pack.
CTA
Free template by Gather — gatherinsights.com. Want diary evidence, allocation records and compensation events connected automatically? Book a demo: https://www.gatherinsights.com/en/book-a-demo